## data
12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 12 | 12 | 9 | 8 | 4 | 3 | 0 | 12 | 0 | 12 | 12 | 10 | 10 | 10 | 10 | 6 | 8 | 6 | 0 | 1 | 12 | 7 | 0 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 12 | 12 | 6 | 12 | 12
[16 empty] | PMO | PMO | PMO |  | from TCO tracker as of Jan.8,2026 | [10 empty] | Tempo | [10 empty] | D |  | Permanent
FTAP SITE ID | MNO Site ID | Search Ring | POC | COOP ABBR. | Project | Territory | Island Group | Region | Province | Municipality | Address | Lat | Long | PMO Milestone | CME Milestone | GRID Category | Project Status | CME Milestone | Approved TSSR | PMO Milestone | Approved TSSR update | BP secured | BP secured date | Construction Started | Construction Completed | Post Con Secured | Post Con on ST | Tap to lessor | Grid Vendor | Vendor Allocated Date | Tempo PQ Raised | PQ Number | Tempo PO Issued | PO Number | COOP Surveyed | Tempo Permit Released | Tempo Energized | Cancelled Tempo | Advance Build | Milestone | Aging Days | Issues | Remarks | Permanent BoQ Submitted | Permanent BoQ approved | Permanent PQ Raised | PQ Number | Permanent PO Issued | PO Number | Line Construction Started | Line Construction Completed | Bill deposit Paid | Permanent Energized | Milestone | Aging Days | Remarks |  | Delay Issues
PH140222 | CO-A-BM-37 | BrgyBialong_ShariffAguak_Maguindanao | Marlone | MAGELCO | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | Shariff Aguak (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110560 | NS-BIZ18-D02 | Brgy.Mandug02_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110548 | NS-BIZ18-D04 | Brgy.Bucana02_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.0541 | 125.5917 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH110582 | NS-BIZ18-D08 | Baluarte_TDCProperty_BrgyPanacan_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | 0 | 0 | 0 | a.10 For Justi submission to GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110558 | NS-BIZ18-D10 | Brgy.Waan02_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110553 | NS-BIZ18-D21 | Brgy.Buhangin(Pob.)01_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p.2 LGU Applied- Advance build | ADV. RTB | Yes | 2025-10-02 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110547 | NS-BIZ18-D31 | Brgy.Pampanga_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070479 | NS-BIZ18-D55 | Baluarte_TempleofLeah_BrgyBusay_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH031093 | NS-BIZ18-D88 | BrgyBatasanBata_SanMiguel_Bulacan | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | San Miguel | 0 | 0 | 0 | c. Ongoing candidate pre-approval | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH080348 | NS-BIZ18-E69 | Roxas_st_corner_Bonifacio_st_Catarman_NorthernSamar | Ralph | NORSAMELCO | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Northern Samar | Catarman (Capital) | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010320 | NS-BIZ19-A09 | BRGYLINGSAT_SANTAMARIA_ILOCOSSUR | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | 0 | 0 | 17.3774 | 120.458 | t. BP secured | J - Pending SKOM | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-09-03 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-10-17 | 2025-11-18 | 2025-11-26 |  |  | Tempo Energized | 119 |  |  | 2025-12-03 | 2026-01-26 | 2026-01-26 | FTAPPQ0014814 | [6 empty] | PQ Raised | #N/A |  | BK ENGINEERING | #REF!
PH070386 | NS-BIZ19-A37 | BrgyDamolog_Sogod_Cebu | Ralph | #N/A | BTS 7 | T6 | VIS | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes | 2025-04-22 |  |  |  | #REF! |  | Optisolv Electrical Construction Corp. | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-29 | 2025-07-27 |  | 2025-07-30 | [5 empty] | PO Issued | 72 |  | #N/A
PH080355 | NS-BIZ19-A63 | BrgySanIsidro_Maasin_Leyte | Ralph | 0 | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Southern Leyte | 0 | 0 | 10.1555 | 124.8523 | t. BP secured | 0 | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-30 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140242 | NS-BIZ19-A99 | Brgy.Nalil_Bongao(Capital)_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | Bongao (Capital) | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100349 | NS-BIZ19-B36 | Brgy.Magting01_Mambajao(Capital)_Camiguin | Marlone | CAMELCO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Camiguin | Mambajao (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH090083 | NS-BIZ19-B69 | Brgy.Ayala01_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 6.9929 | 121.9463 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-18 |  | 2025-09-09 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH080356 | NS-BIZ19-B99 | Brgy93Bagacay_TaclobanCity_Leyte | Ralph | 0 | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Leyte | 0 | 0 | 0 | 0 | r. BP applied | 0 | #REF! | #REF! | #REF! |  | r. BP applied | For BP release | [5 empty] | #REF! |  | Renagmec Power Corporation | 2025-10-27 | 2025-10-27 | FTAPPQ0013327 | 2025-11-03 | FTAPPO0012433 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A
PH110606 | NS-BIZ19-C19 | Brgy.Poblacion_Malita(Capital)_DavaoOccidental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | Malita (Capital) | 0 | 6.4146 | 125.6012 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-07-31 | 2025-08-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH070521 | NS-BIZ19-C56 | BrgyCogon_Tagbilaran_Bohol | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Bohol | City of Tagbilaran (Capital) | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150158 | NS-BIZ19-C94 | BrgyGobgob_TabukCity_Kalinga | Marilyn | KAELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk (Capital) | 0 | 17.4737 | 121.4321 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Carlson Electrical Supply and Services | [10 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A | #REF!
PH140219 | NS-BIZ19-D61 | Brgy.Lebbuh_LamitanCity(Capital)_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Lamitan (Capital) | 0 | 6.5645 | 122.1741 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-08-04 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH020194 | NS-BIZ19-E27 | BrgyAguiguican_Gattaran_Cagayan | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Gattaran | 0 | 18.1017 | 121.6631 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-07-04 |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012901 | 2025-10-06 | FTAPPO0012036 | 2025-12-19 | 2025-09-15 | 2025-12-23 |  |  | Tempo Energized |  |  | 10/6/25: Waiting for TTC energization; Transformer Testing 10/15/25 10/5/25: PQ raised, takeover from Northflash | 2025-10-01 | 2025-10-15 | 2025-10-15 | FTAPPQ0013136 | 2025-10-28 | FTAPPO0012305 |  |  |  |  | PO Issued | 9 | 10/6/26: Waiting Signed Staking sheet release/ Waiver for permanent construction | #N/A | #REF!
PH130150 | NS-BIZ19-F71 | TouristRoad_BrgyPoblacionVGenLuna_SDN | Marlone | SIARELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | General Luna | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH030880 | NS-BIZ20-A20 | MtSamatShrine_BrgyDiwa_Pilar_Bataan_LGU | CJ | PENELCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bataan | Pilar | 0 | 0 | 0 | e.1. Pending JTSS Actual | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.2. Long lead time | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130011 | NS-BIZ20-A96 | Brgy.Cortes_Basilisa(Rizal)_DinagatIslands | Marlone | DIELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Dinagat Islands | Basilisa | 0 | 10.0724 | 125.5383 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-09-05 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH070512 | NS-BIZ20-B27 | BrgySanta Cruz_SAN FRANCISCO_CEBU | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030865 | NS-BIZ20-C97 | BrgyDiome_MariaAurora_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Maria Aurora | 0 | 15.7648 | 121.4709 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-30 |  | 20/08/2025 |  | #REF! |  | Bangayan Electrical Services | 2025-09-12 | 2025-10-13 | FTAPPQ0013085 | 2025-10-15 | FTAPPO0012250 | 2025-10-06 | 2025-10-10 | 2025-12-16 |  |  | Tempo Energized | 99 | Original BP, EP needed. Requested to SAQ team. | 10/20/2025: Applied TTC. JTSS done, LC done, for energization once restoration in the area is done due to typhoon. 10/12/2025: Applied TTC, for temperament solution | 2025-09-03 | 2025-09-29 | 2025-09-29 | FTAPPQ0012845 | 2025-10-03 | FTAPPO0011986 |  |  |  |  | PO Issued | 7 | 10/20/2025: Postcon permits needed. For transformer testing. 10/6/2025: Waiting for NTP release for Construction | #N/A | CFEI, OP
PH010343 | NS-BIZ20-D02 | BrgyNapu_Badoc_IlocosNorte | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Badoc | 0 | 17.9422 | 120.4962 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 | 2025-05-07 | 29/09/2025 |  | #REF! |  | BK Engineering Services | 2025-09-05 | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 | [5 empty] | PO Issued | FALSE |  |  | 2025-09-12 | 2025-10-09 | 2025-10-09 | FTAPPQ0013022 | 2025-10-13 | FTAPPO0012152 |  |  |  |  | PO Issued | 1 | 10/17/25: RoW ongoing 10/7/25: Waiting BoQ Approval | #N/A | #REF!
PH010364 | NS-BIZ20-D26 | BrgySarmingan_Narvacan_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Narvacan | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! |  | BK Engineering Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | BK ENGINEERING | #REF!
PH030789 | NS-BIZ20-E55 | BrgyDuale_Limay_Bataan | Marilyn | PENELCO | BTS 7 | T2 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Permanent Energized | #REF! | #REF! |  | 0 | RTB | Yes | 2025-01-20 |  |  |  | #REF! |  | Larc Telecoms, Inc. | [10 empty] | BP Secured | FALSE |  | Permanent power energized | 2025-10-29 | 2025-10-29 | 2025-10-29 | FTAPPQ0013390 | 2025-11-03 | FTAPPO0012506 | 2025-11-10 | 2025-11-15 | 2025-11-20 | 2025-11-27 | Permanent Energized |  |  | #N/A
PH100353 | NS-BIZ20-F83 | Brgy.ApoMacote_MalaybalayCity(Capital)_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay (Capital) | Purok 6 | 7.9762 | 125.2084 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-04-07 |  | 20/07/2025 |  | #REF! |  | Diomon Electrical Services | [5 empty] | 2025-04-08 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-05-04 | 2025-05-06 |  | 2025-05-09 | [5 empty] | PO Issued | 154 |  | #N/A
PH100351 | NS-BIZ20-G10 | Brgy.SaintPeter_MalaybalayCity(Capital)_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay (Capital) | 0 | 0 | 0 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140255 | NS-BIZ20-G54 | Brgy.Makir_DatuOdinSinsuat(Dinaig)_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 7.0474 | 124.3144 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-08-15 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140268 | NS-BIZ20-G55 | Brgy.Kusiong01_DatuOdinSinsuat(Dinaig)_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | a.8. PSH done- For re-hunting | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140258 | NS-BIZ20-G74 | Brgy.Magsaysay_Parang_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110279 | NS-BIZ20-G76 | Brgy.Subasta03_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | Balingaeng | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120083 | NS-BIZ20-H16 | Baymax2020_BrgyPoblacion7_Midsayap_NCOT | Marlone | COTELCO – PPALMA | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Midsayap | Purok 2 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH120087 | NS-BIZ20-H43 | Brgy.Siguel01_GeneralSantosCity_SouthCotabato | Marlone | SOCOTECO II | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060453 | NS-BIZ20-H89 | BrgyJibao-an_Pavia_Iloilo(2) | Ralph | ILECO I | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Iloilo | Pavia | 0 | 10.7556 | 122.5037 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-15 |  | 19/05/2025 | 2025-06-10 | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110235 | NS-BIZ20-H95 | Brgy.Kidalapong_Malita(Capital)_DavaoOccidental | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | Malita (Capital) | 0 | 6.424 | 125.5845 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-18 |  |  |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | 2025-09-23 | [9 empty] | BoQ Submitted | 17 |  | #N/A
PH140257 | NS-BIZ21-A28 | Brgy.Pura01_DatuBlahT.Sinsuat_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | a.8. PSH done- For re-hunting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030827 | NS-BIZ22-A05 | BrgyVentenilla_Paniqui_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Paniqui | 0 | 15.6781 | 120.5423 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-30 | 2025-11-06 | 2025-05-08 | 2025-10-03 | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-06-06 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-10-20 | 2025-11-06 | 2025-11-06 | FTAPPQ0013528 | 2025-11-07 | FTAPPO0012650 | 2025-11-27 |  |  |  | Line Construction Started | 126 | 10/20/2025: BOM submitted. For BOM review. 10/5/2025: Awaiting coop SOA. | #N/A
PH010396 | NS-BIZ22-A07 | BrgyPalacpalac_Pozorrubio_Pangasinan | Marilyn | PANELCO III | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Nama Road | 16.1288 | 120.533 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-08-28 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-30 |  |  |  | Tempo Permit Released |  | With neighbor Issue | 10/13: With neighbor concent /complaint 10/9/25: Waiting energization schedule 10/5/25: COOP applied; waiting COOP Assessment | 2025-09-22 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 |  |  |  |  | PO Issued | 4 |  | #N/A | #REF!
PH010395 | NS-BIZ22-A09 | BrgyAngatel_Urbiztondo_Pangasinan | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan |  | 0 | 15.8044 | 120.3452 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-07-22 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-23 | 2025-10-17 |  |  | Tempo Energized |  |  | 10/13 waiting for energization schedule 10/9/25; Waiting Tempo Energization | 2025-09-15 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 | 2025-10-10 | 2025-10-15 |  |  | Line Construction Completed | 4 |  | #N/A | #REF!
PH010392 | NS-BIZ22-A10 | BrgyBuenlag2nd_Bayambang_Pangasinan | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Bayambang | 0 | 0 | 0 | e.1. Pending JTSS Actual | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! |  | LARC | [10 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH010397 | NS-BIZ22-A14 | BrgyLareg-lareg_Malasiqui_Pangasinan | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Malasiqui | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! |  | LARC | [10 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH010326 | NS-BIZ22-A16 | BrgySagayaden_Cabugao_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Cabugao | 0 | 17.7719 | 120.4606 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | w. For OP application | RTB | Yes | 2025-08-28 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-10-29 | 2025-10-31 |  |  | Tempo Energized |  |  | 10/6/25: Installed SEP; Waiting LGU Inspection 10/5/25: for installation SEP; Waiting LGU inspection | 2025-10-10 | 2025-11-19 | 2025-11-19 | FTAPPQ0013740 | 2025-11-21 | FTAPPO0012891 |  |  |  |  | PO Issued | 8 |  | #N/A | #REF!
PH010349 | NS-BIZ22-A37 | BrgyBorobor_Galimuyod_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Galimuyod | 0 | 0 | 0 | d. Site re-hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH070510 | NS-BIZ22-A39 | BrgyMasulog_CanlaonCity_NegrosOriental_MACRO_COV2021 | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Negros Oriental | 0 | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070513 | NS-BIZ22-A53 | BrgyMinolos_Barili_Cebu_MACRO_COV2021 | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH050300 | NS-BIZ22-B13 | NearBrgyLuklukanSurBoundary_BrgySantaRosaNorte_JosePanganiban_CamarinesNorte | Marilyn | CANORECO | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | [5 empty] | #REF! |  | North Flash Power And Builds Inc. | [10 empty] | Not yet endorsed | FALSE |  | PERMANENT Power energized |  | 2025-05-28 | 2025-05-28 | FTAPPQ0010592 | 2025-05-31 | FTAPPO0009859 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | Permanent Energized | 28 | ENERGIZED | #N/A
PH050294 | NS-BIZ22-B14 | NearGovFelixAFuentebellaNtlHwy_BrgySanSebastian_Lagonoy_CamarinesSur | Marilyn | CASURECO IV | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes | 2024-07-25 |  |  | 2025-07-14 | #REF! |  | North Flash Power And Builds Inc. | [10 empty] | BP Secured | FALSE |  | PERMANENT Power energized | 2025-05-28 | 2025-05-28 | 2025-05-28 | FTAPPQ0010592 | 2025-05-31 | FTAPPO0009859 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | Permanent Energized | 65 | ENERGIZED | #N/A
PH050298 | NS-BIZ22-B19 | NearLarapRd_BrgyLarap_JosePanganiban_CamarinesNorte | Marilyn | CANORECO | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  |  | #REF! |  | North Flash Power And Builds Inc. |  |  | direct to Permanent | [7 empty] | BP Secured | FALSE |  | PERMANENT Power energized | 2025-09-02 | 2025-09-02 | 2025-09-04 | FTAPPO0011402 | 2025-09-04 | FTAPPO0011402 | 2025-09-16 | 2025-09-18 | 2025-11-15 | 2025-11-28 | Permanent Energized | 22 | Waiting for COOP SOA and CFIA approval from NEA prior energization | #N/A
PH401049 | NS-BIZ22-B31 | BrgySaguing_Mabini_Batangas | Marilyn | BATELEC II | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-10-08 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  | Waiting for BP and EP permits need for application | [10 empty] | Vendor Allocated |  | Waiting for EP, EPPLan and CFEI | #N/A
PH120362 | NS-BIZ22-B57 | Brgy.PatadonWest_Matalam_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | 0 | 0 | 7.0805 | 124.9365 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-09-09 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120369 | NS-BIZ22-B60 | Brgy.Pigcawaran_Alamada_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | 0 | 0 | 0 | 0 | p. LGU Applied | 0 | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130183 | NS-BIZ22-B72 | Brgy.Maygatasan_BayuganCity_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH110579 | NS-BIZ22-B90 | Brgy.Elizalde(Somil)_Maco_DavaoDeOro | Marlone | NORDECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao de Oro | Maco | Purok 2-A | 7.3877 | 125.9809 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-08 |  | 2025-01-06 |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-07 | 2025-05-06 |  | 2025-05-09 | [5 empty] | PO Issued | 154 |  | #N/A
PH140224 | NS-BIZ22-B94 | Brgy.KabatuhanTiis_Talipao_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Talipao | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100327 | NS-BIZ22-C03 | Brgy.Bugcaon_Lantapan_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Lantapan | Zone 1 | 8.0426 | 125.113 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-21 |  | 2025-07-06 | 2025-09-26 | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-07 | 2025-05-06 |  | 2025-05-09 | [5 empty] | PO Issued | 154 |  | #N/A
PH120345 | NS-BIZ22-C04 | BrgyMalinao_Banisilan_Cotabato (North Cotabato) | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Banisilan | 0 | 7.558 | 124.7048 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-13 | 2025-06-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120352 | NS-BIZ22-C05 | BrgyMinapan_Tulunan_Cotabato (North Cotabato) | Marlone | COTELCO | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Tulunan | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120367 | NS-BIZ22-C12 | Brgy.Simsiman_Pigkawayan_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Pigkawayan | 0 | 7.2322 | 124.3807 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-09 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120351 | NS-BIZ22-C14 | BrgyDoroluman_Arakan_Cotabato (North Cotabato) | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | 0 | 0 | 0 | 0 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH120343 | NS-BIZ22-C17 | Brgy.Alegria01_Alabel(Capital)_Sarangani | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sarangani | Alabel (Capital) | 0 | 6.151 | 125.2878 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-31 | 2025-04-06 | 17/07/2025 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | 2025-09-11 | 2025-09-15 | [8 empty] | BoQ Approved | 25 |  | #N/A
PH120356 | NS-BIZ22-C23 | Brgy.Baliango_Palimbang_SultanKudarat | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | 0 | 0 | 6.1984 | 124.2083 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-08-27 | 2025-07-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH150179 | NS-BIZ22-C51 | LGU-VIP_BrgyIli_Conner_Apayao | Marilyn | KAELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Apayao | Conner | 0 | 17.8316 | 121.2663 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-06-23 | 2025-04-08 |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 | 2025-10-14 | 2025-11-08 |  |  | Tempo Energized |  |  | 10/14 target until next wk energization | [10 empty] | Vendor Allocated | 32 | 10/13 Application applied waiting COOP SOA and staking sheet prior Submission of BOQ | #N/A | #REF!
PH130141 | NS-BIZ22-C59 | Brgy.Carromata_SanMiguel_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | San Miguel | 0 | 8.9679 | 125.9773 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 |  | 20/08/2025 |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-29 | 2025-08-04 |  | 2025-08-07 | [5 empty] | PO Issued | 64 |  | #N/A
PH130143 | NS-BIZ22-C60 | Brgy.Bolhoon_SanMiguel_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | San Miguel | Purok 3 | 8.8659 | 125.9762 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-08 |  | 26/04/2025 | 2025-09-26 | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-04-23 | 2025-04-22 |  | 2025-04-25 | [5 empty] | PO Issued | 168 |  | #N/A
PH030825 | NS-BIZ23-A12 | BrgyBrillante_Paniqui_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Paniqui | 0 | 15.6427 | 120.5232 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-30 |  | 2025-06-09 |  | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-06-06 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-10-27 | 2025-11-05 | 2025-11-05 | FTAPPQ0013496 | 2025-11-05 | FTAPPO0012623 | 2025-12-15 |  |  |  | Line Construction Started | 126 | 10/20/2025: For submission of vendor BOM.10/12/2025: Awaiting coop BOM. | #N/A
PH030826 | NS-BIZ23-A13 | BrgyColibangbang_Paniqui_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Paniqui | 0 | 15.6303 | 120.5492 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-11 |  |  |  | #REF! |  | JRJA Builders Supply and Services Co. | 2025-09-08 | 2025-09-08 | FTAPPQ0012308 | 2025-09-09 | FTAPPO0011519 | 2025-10-01 | 2025-09-15 | 2025-09-26 |  |  | Tempo Energized |  |  | 9/23/2025: Temporary power applied. JTSS done. For line construction once weather is ok. | 2025-10-27 | 2025-11-05 | 2025-11-05 | FTAPPQ0013496 | 2025-11-05 | FTAPPO0012623 |  |  |  |  | PO Issued |  | 10/20/2026: Awaiting coop BOM. | #N/A
PH030802 | NS-BIZ23-A14 | BrgyCut-cutII_TarlacCity_Tarlac | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 15.4723 | 120.6455 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-09 |  |  |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 |  |  |  |  | COOP Surveyed |  | CME on hold | 10/12/2025: CME has not yet started, with DDD issue 10/5/25: Waiting for Tempo Permit release 10/3/2025: For JTSS sched | [10 empty] | Vendor Allocated |  |  | #N/A
PH030819 | NS-BIZ23-A15 | BrgyQuezon_Gerona_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Gerona | 0 | 15.62 | 120.4961 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-30 |  |  | 2025-09-29 | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-07-07 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-11-14 | 2025-12-15 | 2025-12-15 | FTAPPQ0014218 | 2025-12-18 | FTAPPO0013321 |  |  |  |  | PO Issued | 95 | 10/20/2026: Awaiting coop BOM. | #N/A
PH120358 | NS-BIZ23-A18 | Brgy.Badiangon_Palimbang_SultanKudarat | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | 0 | 0 | 6.2234 | 124.1997 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-08-09 | 2025-02-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH070514 | NS-BIZ23-A25 | BIZMobile2023_BrgySulangan_Bantayan_Cebu_MACRO_COV2023 | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010352 | NS-BIZ23-A40 | LGU_BrgyManueva_Santa_Ilocos Sur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Santa | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes |  |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 |  |  |  |  | No BP in ST | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 |  | BK ENGINEERING | #REF!
PH150170 | NS-BIZ23-A42 | BrgyButigue_Paracelis_ Mountain Province_LGU | Arjay | MOPRECO | BTS 8 | T2 | NLZ | Cordillera Administrative Region (CAR) | Mountain Province | Paracelis | 0 | 0 | 0 | f. TSSR submitted to DNE & PMO | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH120368 | NS-NTG18-A76 | Brgy.PoblacionI_Pigkawayan_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | 0 | 0 | 7.2731 | 124.4196 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-08-27 | 2025-11-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH401053 | NS-NTG18-F92 | BrgySanVicente_SanPedro_Laguna | Marilyn | MERALCO | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-10-08 | 2025-10-16 | FTAPPQ0013161 | 2025-10-20 | FTAPPO0012289 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 | For JTSS
PH070482 | NS-NTG18-G18 | Brgy_Lorega_San_Miguel_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.307 | 123.9029 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! |  | Jodan Electrical Services | 2025-10-27 | 2025-10-27 | FTAPPQ0013324 | 2025-11-03 | FTAPPO0012432 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | #VALUE! |  | #N/A
PH110554 | NS-NTG18-G79 | Brgy.Cabantian01_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.1223 | 125.6184 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100317 | NS-NTG18-G90 | Brgy.Patag_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! |  | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130134 | NS-NTG18-H14 | Brgy.Bonbon_ButuanCity(Capital)_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | City of Butuan (Capital) | 0 | 8.9304 | 125.5082 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-10-02 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100279 | NS-NTG18-P80 | Brgy.Indahag04_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH401048 | NS-NTG18-P85 | BrgyKumintangIbaba_BatangasCity_Batangas | Marilyn | MERALCO | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  |  | #REF! |  | Golden Design Konstrukt and Trading |  |  | direct to Permanent | [7 empty] | BP Secured | FALSE |  | For PP application waiting for MERALCO construction and energization | 2025-09-13 | 2025-09-13 | 2025-02-16 | FTAPPQ0009350 | 2025-02-16 | FTAPPO0008590 | 2025-09-18 | 2025-09-24 |  |  | Line Construction Completed |  | Waiting for implementation and installation of MERALCO | #N/A
PH110563 | NS-NTG18-P91 | Brgy.Tigatto01_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.1236 | 125.5879 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-08-27 | 2025-11-09 | 2025-01-10 |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | 2025-09-23 | [9 empty] | BoQ Submitted | 17 |  | #N/A
PH031091 | NS-NTG18-R35 | BRGYPARULAN_PULILAN_BULACAN | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | Plaridel | 0 | 0 | 0 | c. Ongoing candidate pre-approval | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060478 | NS-NTG19-AA62 | Brgy8_Kabankalan_NegOcc | Ralph | 0 | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | u. RTB | RTB | [5 empty] | #REF! |  | Tripower Elecrical Services | 2025-10-27 | 2025-10-27 | FTAPPQ0013328 | 2025-11-03 | FTAPPO0012434 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A
PH070437 | NS-NTG19-AB05 | BrgyLahug2_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070371 | NS-NTG19-AB15 | BrgyBulacao_Talisay_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH010344 | NS-NTG19-AC09 | OrenceRd_BrgyOrence_Narvacan_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Narvacan | 0 | 17.4211 | 120.4886 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-08-09 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-10-14 | 2025-10-17 |  |  | Tempo Energized |  |  | 10/6/25: Installed SEP; Waiting LGU Inspection 10/5/25: for installation SEP; Waiting LGU inspection | 2025-10-10 | 2025-11-19 | 2025-11-19 | FTAPPQ0013740 | 2025-11-21 | FTAPPO0012891 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH030851 | NS-NTG19-AC72 | Purok1_BrgySanIsidro_CabanatuanCity_NuevaEcija | CJ | CELCOR | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Purok 4 | 15.4909 | 121.0001 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-01 |  | 30/09/2025 |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0012307 | 2025-09-09 | FTAPPO0011518 | 2025-09-23 | 2025-09-23 | 2025-11-04 |  |  | Tempo Energized |  |  | 11/4/2025: Energized. 10/20/2026: Permanent LC done, for final inspection of coop. 10/12/2025: Permanent line construction on going. For survey again of coop once done with the LC. 10/5/25: For Line Construction 9/23/2025: Temporary power applied. For coop JTSS schedule once weather is okay. | 2025-10-28 | 2025-11-12 | 2025-11-12 | FTAPPQ0013619 | 2025-11-18 | FTAPPO0012764 |  |  |  |  | PO Issued |  | 10/20/2025: Permanent line construction done. For final inspection of coop. 10/12/2025: LC ongoing for termperament solution. | #N/A
PH010406 | NS-NTG19-AC76 | BrgyLabitProper_UrdanetaCity_Pangasinan | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | 0 | 15.9503 | 120.5338 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-25 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-10-02 | 2025-10-15 |  |  | Tempo Energized |  |  | 10/9/25: Waiting energization schedule 10/5/25: COOP applied; waiting COOP Assessment | 2025-09-22 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 | 2025-10-10 | 2025-10-15 |  |  | Line Construction Completed | 4 |  | #N/A | #REF!
PH010449 | NS-NTG19-AC92 | BRGYNANCAYASAN_URDANETACITY_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | 0 | 0 | 0 | b. Candidate Secured | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010450 | NS-NTG19-AC93 | NEARBINALONANAIRPORT_BRGYCANARVACANAN_BINALONAN_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | f. TSSR submitted to DNE & PMO | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030869 | NS-NTG19-AD70 | BRGYTIBAG_TARLACCITY_TARLAC | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 15.4884 | 120.5787 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-04 |  |  |  | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-10-08 | 2025-11-14 | FTAPPQ0013674 | 2025-11-18 | FTAPPO0012813 | 2025-11-19 | 2025-11-18 | 2025-12-11 |  |  | Tempo Energized | 104 | [12 empty] | Vendor Allocated | 2 |  | Interlink Power
PH030868 | NS-NTG19-AD72 | BRGYDOLORES_TARLACCITY_TARLAC | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 15.5233 | 120.5754 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-15 | 2025-12-09 |  |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 |  |  |  | Yes | COOP Surveyed |  | Lacking PreCon Permits | 9/23/2025:Advanced build. Awaiting precon permits from SAQ. | [10 empty] | Vendor Allocated |  |  | #N/A
PH050297 | NS-NTG19-AE97 | BrgyMotherlode_JOSE_PANGANIBAN_CAMARINES_NORTE | Marilyn | CANORECO | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  | 2025-08-14 | #REF! |  | North Flash Power And Builds Inc. |  |  | direct to Permanent | [7 empty] | BP Secured | FALSE |  | PERMANENT Power energized | 2025-09-02 | 2025-09-02 | 2025-09-01 | FTAPPQ0012194 | 2025-09-04 | FTAPPO0011402 | 2025-09-16 | 2025-09-18 | 2025-11-15 | 2025-11-28 | Permanent Energized | 36 | Waiting for COOP SOA and CFIA approval from NEA prior energization | #N/A
PH401065 | NS-NTG19-AF16 | BrgyManguisian_Lopez_Quezon | Marilyn | QUEZELCO I | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  |  | #REF! |  | ALS | 2025-10-08 | 2025-12-01 | FTAPPQ0014035 | 2025-12-02 | FTAPPO0013120 | 2025-11-21 | 2025-11-25 |  |  |  | Tempo Permit Released | 120 |  | Waiting for PO issuance C done | 2025-12-11 | 2025-12-12 | 2025-12-12 | FTAPPQ0014193 | 2025-12-15 | FTAPPO0013306 | 2026-01-05 | 2026-01-08 |  |  | Line Construction Completed | 2 |  | TEC
PH120350 | NS-NTG19-AF87 | Brgy.Calumpang_GeneralSantosCity_SouthCotabato | Marlone | SOCOTECO II | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | 0 | 0 | 6.087 | 125.1334 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p.2 LGU Applied- Advance build | ADV. RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110561 | NS-NTG19-AF99 | Brgy.VisayanVillage02_TagumCity(Capital)_DavaoDelNorte | Marlone | NORDECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Norte | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090080 | NS-NTG19-AG49 | Brgy.Gulayon_DipologCity(Capital)_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | City of Dipolog (Capital) | 0 | 8.5664 | 123.3691 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140191 | NS-NTG19-AG51 | Brgy.Kalanganan02_CotabatoCity_Maguindanao | Marlone | MAGELCO | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | e. Approved candidates-Awaiting JTSS schedule | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100277 | NS-NTG19-AH28 | Brgy.Kauswagan02_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100320 | NS-NTG19-AH33 | Brgy.Carangan_OzamizCity_MisamisOccidental | Marlone | MOELCI II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Occidental | City of Ozamiz | Brgy. Carangan, Ozamiz City, Misamis Occidental | 8.1588 | 123.8282 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100049 | NS-NTG19-AH34 | Brgy.DoñaConsuelo_OzamizCity_MisamisOccidental | Marlone | MOELCI II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Occidental | City of Ozamiz | 0 | 0 | 0 | p. LGU Applied | #N/A | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070520 | NS-NTG19-AI98 | Tinaan_Naga_Cebu | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | r.2. BP applied-Advance Build | ADV. RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030886 | NS-NTG19-AM04 | Clark_Donggwangtemp_Permanent | CJ | CEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of Angeles | 0 | 0 | 0 | h. Pending GT TSSR Approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070475 | NS-NTG19-C20 | BrgyPuntaPrincesa_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.2983 | 123.8714 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070458 | NS-NTG19-C22 | BrgyTisa_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.3052 | 123.8666 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070449 | NS-NTG19-C23 | BrgyPuntaPrincesa3_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.2923 | 123.8641 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110357 | NS-NTG19-C74 | Brgy.BagoOshiro01_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110208 | NS-NTG19-C75 | 2019CapSite_BrgyDaliao_DAVAO CITY_DAVAO DEL SUR | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | St. Jude Village | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110577 | NS-NTG19-C77 | Brgy.SantoNiño_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | Purok Makogihon 3, Katipunan | 7.0827 | 125.5104 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-06 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110216 | NS-NTG19-C87 | Brgy.Talomo(Pob.)03_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | 0 | 7.0691 | 125.5569 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-06 | 2025-04-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110206 | NS-NTG19-C91 | Brgy.BagoGallera02_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | Purok 16, Sitio Durian | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030864 | NS-NTG19-I41 | NearBakeroES_BrgyBakero_CabanatuanCity_NuevaEcija | CJ | CELCOR | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | 0 | 15.5137 | 121.0262 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-05-09 |  | 15/09/2025 |  | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-05-16 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 147 | 10/20/2025: Need CFEI prior to proceeding with the PP application | #N/A | POSTCON PERMITS NEEDED
PH100281 | NS-NTG19-J79 | Brgy.Bulua_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100318 | NS-NTG19-J81 | Brgy.Kauswagan03_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH060452 | NS-NTG19-K22 | BrgyTangub_BacolodCity_NegrosOccidental | Ralph | NEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | City of Bacolod (Capital) | 0 | 10.6254 | 122.9503 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-30 | 2025-05-05 | 2025-02-07 | 2025-07-16 | #REF! |  | Tripower Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-09 | 2025-09-06 |  | 2025-09-09 | [5 empty] | PO Issued | 31 |  | #N/A
PH060449 | NS-NTG19-O74 | Puregold_San Juan St., corner BS Aquino Drive Sto. Nino Bacolod City | Ralph | NEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | City of Bacolod (Capital) | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! |  | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030882 | NS-NTG19-O75 | Puregold_BrgyReformista_Limay_Bataan | CJ | PENELCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bataan | Limay | 0 | 14.5628 | 120.5933 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-31 |  |  |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-09-08 | direct to permanent | 2025-09-09 | FTAPPO0011520 | 2025-09-16 |  |  | Yes |  | COOP Surveyed |  | Survey Schedule | 10/03/2025: Applied permanent power, awaiting JTSS sched. 9/23/2025: LGU did not allow us to apply for temporary power since site is already done. Applied for permanent power. | 2025-09-27 | 2025-10-09 | 2025-10-09 | FTAPPQ0013028 | 2025-10-13 | FTAPPO0012151 | 2025-10-08 | 2025-10-10 | 2025-10-13 | 2025-10-23 | Permanent Energized |  | 10/20/2025: Coop SOA released. BD requested. 10/12/2025: Awaiting completion of CME. | #N/A | CME Service entrance
PH031092 | NS-NTG19-O77 | PUREGOLD_BRGYBUNSURANI_PANDI_BULACAN | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | Pandi | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030904 | NS-NTG19-R69 | Alfamart_CDeJesusSt_BrgyParada_SantaMaria_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Santa Maria | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | L - Under pre-construction | #REF! | #REF! | #REF! |  | f. TSSR submitted to DNE & PMO | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150129 | NS-NTG19-S36 | Shell_Ilocos-AbraRd_BrgyZone5_Bangued_Abra | Marilyn | ABRECO | BTS 7 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  |  | #REF! |  | BK Engineering Services |  | 2025-10-14 | FTAPPQ0013121 | 2025-10-15 | FTAPPO0012247 | 2025-11-10 | 2025-11-20 | 2025-12-11 |  |  | Tempo Energized | 104 |  | ENERGIZED | 2025-11-18 | 2025-12-10 | 2025-12-10 | FTAPPQ0014151 | 2025-12-12 | FTAPPO0013266 |  |  |  |  | PO Issued |  | No permit doe BOQ submission | #N/A
PH010339 | NS-NTG19-S50 | UnitedNeon_ManilaNorthRd_BrgyCabaroan_Bantay_IlocosNorte | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Bantay | 0 | 17.5797 | 120.3987 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-14 |  |  |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-15 | 2025-10-05 |  |  | Tempo Energized |  |  |  | 2025-09-15 | 2025-09-25 | 2025-09-30 | FTAPPQ0012674 | 2025-10-03 | FTAPPO0011939 |  |  |  |  | PO Issued | 7 |  | 10/9/2025: Construction 10/13/25 | #REF!
PH010359 | NS-NTG19-S85 | UnitedNeon_BrgyCaranglaan_DagupanCity_Pangasinan | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | 2025-11-15 |  |  |  |  | COOP Surveyed | #VALUE! | [12 empty] | Vendor Allocated | 2 |  | Larc Telecoms Inc. | #REF!
PH120341 | NS-NTG19-T31 | Brgy.Apopong03_GeneralSantosCity_SouthCotabato | Marlone | SOCOTECO II | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | 0 | 0 | 0 | 0 | h. Pending GT TSSR Approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100294 | NS-NTG19-T40 | Brgy.Bolobolo01_ElSalvadorCity_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | 0 | 0 | 0 | a. Ongoing site hunting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH120382 | NS-NTG19-T56 | Brgy.Buenaflor_TacurongCity_SultanKudarat | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | 0 | 0 | 0 | p. LGU Applied | 0 | #REF! | #REF! | #REF! |  | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030892 | NS-NTG19-U09 | SMC_L0066_BrgyPanducot_Calumpit_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Calumpit | 0 | 0 | 0 | e.1. Pending JTSS Actual | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH010451 | NS-NTG19-X31 | BryArnedo_Bolinao_Pangasinan | Marilyn | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Bolinao | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH110581 | NS-NTG19-X48 | Brgy.Apokon01_TagumCity(Capital)_DavaoDelNorte | Marlone | NORDECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Norte | City of Tagum (Capital) | 0 | 7.4193 | 125.8353 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-17 |  | 2025-02-08 |  | #REF! |  | C-8 Construction Services | [5 empty] | 2025-07-08 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-07-29 | 2025-08-04 |  | 2025-08-07 | [5 empty] | PO Issued | 64 |  | #N/A
PH110556 | NS-NTG19-X54 | Brgy.MagugpoSouth_TagumCity(Capital)_DavaoDelNorte | Marlone | NORDECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Norte | City of Tagum (Capital) | 0 | 7.4418 | 125.7949 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-03 | 2025-11-07 |  |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-29 | 2025-08-04 |  | 2025-08-07 | [5 empty] | PO Issued | 64 |  | #N/A
PH110572 | NS-NTG20-AA26 | 2023Capsite_GaisanoMall_Brgy13B_DavaoCity_DDS | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | a.8. PSH done- For re-hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100377 | NS-NTG20-AA33 | Brgy.Barangay24-A(Pob.)_GingoogCity_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070515 | NS-NTG20-AB86 | BrgyNaalad_NagaCity_Cebu | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070516 | NS-NTG20-AB99 | BrgyCasili_Consolacion_Cebu_2 | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130139 | NS-NTG20-AG01 | Brgy.Poblacion(Bahbah)_Prosperidad(Capital)_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | Prosperidad (Capital) | 0 | 8.6057 | 125.9104 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-05-20 |  | 2025-05-07 |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-11 | 2025-09-09 |  | 2025-09-12 | [5 empty] | PO Issued | 28 |  | #N/A
PH130170 | NS-NTG20-AG03 | Brgy.SanNicolas(Pob.)_Talacogon_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | Talacogon | 0 | 8.4588 | 125.7816 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-16 | 2025-05-08 |  |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-03 | 2025-09-01 |  | 2025-09-04 | [5 empty] | PO Issued | 36 |  | #N/A
PH090069 | NS-NTG20-AK59 | Brgy.LowerIpilHeights_Ipil(Capital)_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil (Capital) | 0 | 7.788 | 122.5837 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140243 | NS-NTG20-AK62 | Brgy.SanRaymundo_Jolo(Capital)_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Jolo (Capital) | 0 | 6.0497 | 121.0087 | a. Ongoing site hunting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH130148 | NS-NTG20-AK84 | Brgy.SantaCruz_Rosario_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | Rosario | 0 | 8.3605 | 126.0157 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-06-25 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130157 | NS-NTG20-AK85 | Brgy.Poblacion_Trento_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | Trento | 0 | 8.0413 | 126.0543 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-04-30 | 2025-06-05 | 30/06/2025 |  | #REF! |  | C-8 Construction Services | [5 empty] | 2025-07-29 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-06-16 | 2025-06-17 |  | 2025-06-20 | [5 empty] | PO Issued | 112 |  | #N/A
PH100346 | NS-NTG20-AK97 | Brgy.LuzBanzon03_Jasaan_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH110303 | NS-NTG20-AQ84 | 2020Capsite_BrgyTibanban01_GOVGEN_DVOR | Marlone | DORECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Oriental | Governor Generoso | 0 | 6.6328 | 126.0753 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-08-25 |  |  |  | #REF! |  | SG Dynamics Construction | [10 empty] | BP Secured | FALSE |  |  | 2025-09-27 | 2025-09-27 | 2025-09-29 |  | 2025-10-02 | [5 empty] | PO Issued | 8 |  | #N/A
PH140244 | NS-NTG20-AT52 | 2020CapSite_BrgyGang_SULTANKUDARAT(NULING)_MGDN | Marlone | MAGELCO | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | Sultan Kudarat | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010311 | NS-NTG20-AU15 | BrgyQuilingSur_Batac_IlocosNorte | Marilyn | INEC | BTS 7 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  |  | #REF! |  | BK Engineering Services |  | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 | 2025-10-25 | 2025-11-05 | 2025-11-14 |  |  | Tempo Energized | 131 |  | ENERGIZED | 2025-05-13 | 2025-05-21 | 2025-05-23 | FTAPPQ0010498 | 2025-05-26 | FTAPPO0009745 |  |  |  |  | PO Issued | 137 | 10/17/25: RoW Issue;Waitiing NTP from COOP for line con | #N/A
PH030894 | NS-NTG20-E19 | NearProvenceCamellaHomes_BrgyLook1st_Malolos_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | City of Malolos (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH020207 | NS-NTG20-E64 | BrgyImeldaBlissVillage_IlaganCity_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | City of Ilagan (Capital) | 0 | 17.1147 | 121.8804 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | w. For OP application | RTB | Yes | 2025-06-23 |  |  |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-06-30 | 2025-10-13 | FTAPPQ0013086 | 2025-10-15 | FTAPPO0012249 | 2025-10-03 | 2025-10-15 |  |  |  | Tempo Permit Released | 161 | For TTC PO issuance | 11/21 For primary line construction of COOP waiting for COOP 1017 Secured Tempo CFEI for line con next week 10/13 Ongoing securing tempo CFEI 10/10 Survey done, LOI submitted to COOP to proceed TTC, For TTC tempo PO | 2025-10-13 | [9 empty] | BoQ Submitted | 102 | 10/28 Wairting NTP for line con 10/17 For BOQ submission nextweek tuesday waiting for COOP SOA | #N/A | #REF!
PH020206 | NS-NTG20-E70 | BrgyCabeseria9and11_IlaganCity_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | City of Ilagan (Capital) | 0 | 17.0562 | 121.9713 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-11 |  | 23/08/2025 |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-12 | 2025-10-13 | FTAPPQ0013093 | 2025-10-15 | FTAPPO0012248 | 2025-10-03 | 2025-11-25 |  |  |  | Tempo Permit Released | 120 | For TTC PO issuance | 11/21 For primary line construction of COOP 10/13 Ongoing securing tempo CFEI 10/10 LOI submitted to COOP | 2025-09-19 | 2025-10-20 | 2025-10-20 | FTAPPQ0013230 | 2025-10-20 | FTAPPO0012353 |  |  |  |  | PO Issued | 21 | 10/28 waiting for NTP for Line con 10/7/25: Vendor to review counter offer procurement | #N/A | #REF!
PH150150 | NS-NTG20-E89 | BrgyBulo_TabukCity_Kalinga | Marilyn | KAELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk (Capital) | 0 | 17.371 | 121.514 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-07 |  | 2025-10-07 | 2025-08-11 | #REF! |  | Carlson Electrical Supply and Services | 2025-04-14 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  | PERMANENT Power energized | 2025-08-18 | 2025-08-18 | 2025-08-17 | FTAPPQ0011976 | 2025-08-20 | FTAPPO0011198 | 2025-08-16 | 2025-08-20 | 2025-08-25 | 2025-09-06 | Permanent Energized | 282 | ENERGIZED | #N/A | #REF!
PH150151 | NS-NTG20-E92 | BrgyMagsaysay_TabukCity_Kalinga | Marilyn | KAELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk (Capital) | 0 | 17.4583 | 121.4599 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-07 |  | 21/06/2025 | 2025-08-05 | #REF! |  | Carlson Electrical Supply and Services | 2025-04-14 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  | PERMANENT Power energized | 2025-08-20 | 2025-08-20 | 2025-08-23 | FTAPPQ0012000 | 2025-08-26 | FTAPPO0011234 | 2025-08-16 | 2025-08-20 | 2025-08-25 | 2025-09-06 | Permanent Energized | 282 | ENERGIZED | #N/A | #REF!
PH030848 | NS-NTG20-F40 | Clark_NearSolarField_BrgyBalibago_AngelesCity_Pampanga | CJ | CEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of Angeles | 0 | 0 | 0 | a.6. Long lead time lessor | L - Under pre-construction | #REF! | #REF! | #REF! |  | e.1. Pending JTSS Actual | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030839 | NS-NTG20-F43 | Clark_PAF1stAirDivision_BrgyBalibago_AngelesCity_Pampanga | CJ | CEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of Angeles | 0 | 0 | 0 | a.6. Long lead time lessor | L - Under pre-construction | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010460 | NS-NTG20-F94 | BrgyPangdel_Bayambang_Pangasinan | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Bayambang | 0 | 0 | 0 | c. Ongoing candidate pre-approval | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010362 | NS-NTG20-G02 | BrgyBatangcawa_Bayambang_Pangasinan | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Bayambang | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-10-02 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-16 | FTAPPQ0013162 | 2025-10-20 | FTAPPO0012293 | 2025-10-09 |  |  |  |  | COOP Surveyed | #VALUE! |  | 10/13 ongoing securing tempo CFEI permits | 2025-12-03 | 2025-12-03 | 2025-12-03 | FTAPPQ0014069 | 2025-12-04 | FTAPPO0013167 |  |  |  |  | PO Issued | 2 |  | Larc Telecoms Inc. | #REF!
PH060465 | NS-NTG20-N99 | BrgyYapak_Malay_Aklan(2) | Ralph | AKELCO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Aklan | Malay | Brgy. Yapak, Malay, Aklan | 11.9821 | 121.9143 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-30 |  |  |  | #REF! |  | ALT Electrical Engineering Services | 2025-10-27 | 2025-10-27 | FTAPPQ0013329 | 2025-11-03 | FTAPPO0012435 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | #VALUE! |  | #N/A
PH120138 | NS-NTG20-O13 | Brgy.Singao02_KidapawanCity(Capital)_NorthCotabato | Marlone | COTELCO | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan (Capital) | Purok Durian | 6.9962 | 125.0525 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-07-21 | 2025-02-08 | 2025-08-09 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120365 | NS-NTG20-O16 | Brgy.Kiwanan_Midsayap_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Midsayap | Purok Daisy | 7.2044 | 124.5543 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-27 | 2025-07-07 | 2025-12-08 |  | #REF! |  | Angkat Construction And Supply | [10 empty] | BP Secured | FALSE |  |  | 2025-09-17 | 2025-09-29 | 2025-09-29 |  | 2025-10-02 | [5 empty] | PO Issued | 8 |  | #N/A
PH120381 | NS-NTG20-O18 | Brgy.Agriculture_Midsayap_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Midsayap | Purok 4 | 7.1582 | 124.5123 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-08-06 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140192 | NS-NTG20-O90 | Brgy.Sumagdang01_IsabelaCity_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 6.6865 | 121.9517 | t. BP secured | A - Energized | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-07-18 |  | 20/09/2025 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120151 | NS-NTG20-Q55 | Brgy.Kayaga_Kabacan_NorthCotabato | Marlone | COTELCO | BTS 8 | T7 | MIN | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | a.9. PSH Done- For GT final disposition | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130135 | NS-NTG20-R23 | RobinsonsPlace_ButuanCity_ADN | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | City of Butuan (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030843 | NS-NTG20-Y80 | STOTSENBERG_OutdoorColoc | CJ | CEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of Angeles | 0 | 0 | 0 | a.6. Long lead time lessor | L - Under pre-construction | #REF! | #REF! | #REF! |  | e.1. Pending JTSS Actual | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100280 | NS-NTG21-A34 | Brgy.Macasandig_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100390 | NS-NTG21-A71 | Brgy.Tankulan(Pob.)_ManoloFortich_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Purok Kihare | 8.3593 | 124.8662 | t. BP secured | A - Energized | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-06-23 | 2025-03-07 | 21/08/2025 |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-30 | 2025-07-29 |  | 2025-08-01 | [5 empty] | PO Issued | 70 |  | #N/A
PH010361 | NS-NTG21-C86 | AlongPerezBlvd_BrgyHerrero_DagupanCity_Pangasinan | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 |  | Larc Telecoms Inc. | #REF!
PH070518 | NS-NTG21-D41 | BrgyPuntaEngano_LapuLapuCity_Cebu_MACRO | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | 0 | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070478 | NS-NTG21-D43 | BrgyMactan_LapuLapuCity_Cebu_HBM_1 | Ralph | MECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | 0 | 10.299 | 124.0046 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070470 | NS-NTG21-D53 | BrgyPajac_LapuLapuCity_Cebu_MACRO_1 | Ralph | MECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | 0 | 10.2968 | 123.9836 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070456 | NS-NTG21-D57 | BasakMarigondonRd_BrgyBasak_LapuLapuCity_Cebu_HBM | Ralph | MECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060464 | NS-NTG21-E45 | BrgyManoc-Manoc_Malay_Aklan_HBM | Ralph | AKELCO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Aklan | Malay | Brgy. Manoc-Manoc, Malay, Aklan | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-28 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH070460 | NS-NTG21-E48 | BrgyCentro(Pob.)_MandaueCity_Cebu_HBM_1 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | a.6. Long lead time lessor | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070450 | NS-NTG21-E50 | BrgyCentro(Pob.)_MandaueCity_Cebu_HBM_2 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 10.3267 | 123.9435 | a.6. Long lead time lessor | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070519 | NS-NTG21-E55 | BrgyMactan_LapuLapuCity_Cebu_HBM_2 | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070462 | NS-NTG21-E57 | BrgyYati_Liloan_Cebu_MACRO | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | Liloan | 0 | 10.3909 | 123.9773 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | [5 empty] | #REF! |  | Jodan Electrical Services | 2025-10-27 | 2025-10-27 | FTAPPQ0013324 | 2025-11-03 | FTAPPO0012432 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | #VALUE! |  | #N/A
PH070453 | NS-NTG21-E60 | BrgyUmapad_MandaueCity_Cebu_HBM_2 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070432 | NS-NTG21-E61 | BrgyCasuntingan_MandaueCity_Cebu_HBM_2 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH060488 | NS-NTG21-E75 | PookSeaPort_BrgyPook_Kalibo_Aklan_MACRO | Ralph | #N/A | BTS 8 | T6 | VIS | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060487 | NS-NTG21-F08 | BrgyPoblacion_Caluya_Antique_HBM | Ralph | 0 | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Antique | Caluya | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070427 | NS-NTG21-F70 | BrgyIbabaoEstancia_MandaueCity_Cebu_HBM_2 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Jodan Electrical Services | 2025-10-27 | 2025-10-27 | FTAPPQ0013324 | 2025-11-03 | FTAPPO0012432 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A
PH060460 | NS-NTG21-F80 | BrgyBuhangTaftNorth_IloiloCity_Iloilo_HBM | Ralph | MEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Iloilo | City of Iloilo (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070455 | NS-NTG21-G28 | BrgyGuadalupe_CebuCity_Cebu_HBM_1 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.3234 | 123.8786 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070445 | NS-NTG21-G47 | BrgyPardo(Pob.)_CebuCity_Cebu_HBM_2 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.2767 | 123.8561 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070467 | NS-NTG21-G54 | BrgyTisa_CebuCity_Cebu_HBM_2 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.3009 | 123.8632 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070451 | NS-NTG21-G55 | BrgyTalamban_CebuCity_Cebu_HBM_3 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | a. Ongoing site hunting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140225 | NS-NTG21-L16 | Brgy.Paiksa_PanglimaEstino(NewPanamao)_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Panglima Estino | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140206 | NS-NTG21-L17 | Brgy.Kalang(Pob.)_Tapul_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Tapul | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030844 | NS-NTG21-L56 | LazadaWH_BrgyIba_Meycauayan_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | City of Meycauayan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110612 | NS-NTG21-L59 | Brgy.LosAmigos01_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060481 | NS-NTG22-D47 | MTF_BrgyRizal_SanCarlosCity_NegrosOccidental_MACRO_CAP2022 | Ralph | 0 | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | 0 | 0 | 0 | 0 | b. Candidate Secured | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110565 | NS-NTG22-D50 | Brgy.Cogon02_DigosCity(Capital)_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110574 | NS-NTG22-D99 | 2023Capsite_BrgyMa-a_DavaoCity_DDS | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100288 | NS-NTG22-E01 | JMCHouse_BrgyAgusanCanyon_ManoloFortich_BUK | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140223 | NS-NTG22-E08 | Brgy.Masantong_Bongao(Capital)_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | Bongao (Capital) | 0 | 5.0773 | 119.7878 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140221 | NS-NTG22-E09 | Brgy.Bakong_Languyan_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | Languyan | 0 | 5.2216 | 119.9668 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010350 | NS-NTG22-F62 | BrgyBigbiga_Santiago_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Santiago | 0 | 17.307 | 120.4447 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-13 |  | 20/08/2025 |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-10-16 | FTAPPQ0013162 | 2025-10-20 | FTAPPO0012293 | 2025-10-21 | 2025-10-23 | 2025-10-28 |  |  | Tempo Energized | 148 |  |  | 2025-09-15 | 2025-09-25 | 2025-09-30 | FTAPPQ0012674 | 2025-10-03 | FTAPPO0011939 |  |  |  |  | PO Issued | 7 |  | #N/A | #REF!
PH140201 | NS-NTG22-F94 | Brgy.Lanote_IsabelaCity_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | e. Approved candidates-Awaiting JTSS schedule | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH030811 | NS-NTG22-G03 | BrgyLaungcupang_LaPaz_Tarlac | CJ | TARELCO II | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | La Paz | Sitio Maranak | 15.4555 | 120.7013 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-07-30 |  | 28/09/2025 |  | #REF! |  | JRJA Builders Supply and Services Co. | 2025-09-08 | 2025-09-08 | FTAPPQ0012308 | 2025-09-09 | FTAPPO0011519 | 2025-09-16 | 2025-09-15 | 2025-09-23 |  |  | Tempo Energized |  |  | 10/12/2025: For PP application awaiting postcon permits. 10/2/2025: Energized 9/23/2025: Temporary power applied. JTSS done. For LC once weather is ok. | 2025-09-05 | 2025-10-28 | 2025-10-29 | FTAPPQ0013379 | 2025-11-03 | FTAPPO0012504 |  |  |  |  | PO Issued |  | 10/20/2025: Awaiting postcon permits | #N/A | POSTCON PERMITS NEEDED
PH010398 | NS-NTG22-G39 | BrgyBonuanBoquig_DagupanCity_Pangasinan_MM | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! |  | LARC | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030840 | NS-NTG22-G40 | VOAHousing_BrgyBalibago_AngelesCity_Pampanga_MM | CJ | CEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of Angeles | 0 | 0 | 0 | a.6. Long lead time lessor | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.2. Long lead time | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030849 | NS-NTG22-G41 | SantaMariaSubd_BrgySanFrancisco_MabalacatCity_Pampanga_MM | CJ | AEC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | Mabalacat City | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH150157 | NS-NTG22-G43 | AteneoDeMapaway_BrgyBulanaoNorte_TabukCity_Kalinga_MM | Marilyn | KAELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk (Capital) | 0 | 17.4232 | 121.476 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-07-16 | 2025-12-08 |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 | 2025-10-14 |  |  |  | Tempo Permit Released |  |  | 10/14 target until next wk energization | 2026-01-12 | 2026-01-13 | 2026-01-13 | FTAPPQ0014563 | 2026-01-14 | FTAPPO0013683 |  |  |  |  | PO Issued | 32 | 10/13 Application applied waiting COOP SOA and staking sheet prior Submission of BOQ | #N/A | #REF!
PH010378 | NS-NTG22-G92 | BrgyMagnuang_Batac_IlocosNorte | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | City of Batac | 0 | 18.0166 | 120.5299 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 |  |  |  | No BP in ST | COOP Surveyed |  |  |  | 2025-10-10 | 2025-11-19 | 2025-11-19 | FTAPPQ0013740 | 2025-11-21 | FTAPPO0012891 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH010373 | NS-NTG22-G94 | BrgyMaglaoiSur_Currimao_IlocosNOrte | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Currimao | 0 | 17.978 | 120.484 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 |  | 2025-08-08 |  | #REF! |  | BK Engineering Services | 2025-08-29 | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 | 2025-10-22 | 2025-10-27 | 2025-11-04 |  |  | Tempo Energized | 141 |  |  | 2025-09-12 | 2025-10-29 | 2025-10-29 | FTAPPQ0013381 | 2025-11-03 | FTAPPO0012505 |  |  |  |  | PO Issued | 28 | 10/7/25: Waiting BoQ Approval | #N/A | #REF!
PH150215 | NS-NTG23-B55 | BrgyChupac_Barlig_MountainProvince_RURALSTAR_POC | Arjay | 0 | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Barlig | 0 | 0 | 0 | a.4. LOI to possible lessor | 0 | #REF! | #REF! | #REF! |  | a.2. Long lead time | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH090239 | NS-NTG23-D20 | Brgy.Lingasad01_Polanco_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Polanco | 0 | 8.4973 | 123.4022 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-09 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100305 | NS-NTG23-D21 | Brgy.Kisolon_Sumilao_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Sumilao | Purok 1 | 8.3366 | 124.975 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 | 2025-07-06 | 21/07/2025 |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-04 | 2025-07-04 |  | 2025-07-07 | [5 empty] | PO Issued | 95 |  | #N/A
PH090213 | NS-NTG23-D23 | Brgy.Punta_DipologCity(Capital)_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | City of Dipolog (Capital) | 0 | 8.5114 | 123.3152 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100409 | NS-NTG23-D34 | Highway_laFortuna_Impasug-ong_bukidnon | Marlone | 0 | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | 0 | 0 | 8.2699 | 124.9992 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-09-24 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130140 | NS-NTG23-D40 | Brgy.Manat_Trento_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | Trento | 0 | 8.0915 | 126.086 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-04-28 | 2025-05-05 | 29/06/2025 |  | #REF! |  | Angkat Construction and Supplies | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-06-26 | 2025-06-28 |  | 2025-07-01 | [5 empty] | PO Issued | 101 |  | #N/A
PH110559 | NS-NTG23-D49 | Brgy.Langub01_DavaoCity_DDS | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.1007 | 125.5653 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120342 | NS-NTG23-D51 | Brgy.Sinawal04_GeneralSantosCity_SouthCotabato | Marlone | SOCOTECO II | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120378 | NS-NTG23-D52 | Brgy.Sadsalan_Lambayong(MarianoMarcos)_SultanKudarat | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | 0 | 0 | 6.8091 | 124.6105 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-15 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110613 | NS-NTG23-D82 | Brgy.BiaoEscuela_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.1625 | 125.5164 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140266 | NS-NTG23-D83 | Brgy.Kapinpilan_Ampatuan_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100313 | NS-NTG23-D90 | Brgy.Sankanan_ManoloFortich_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | 0 | 8.3154 | 124.8598 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-07 |  | 17/07/2025 |  | #REF! |  | Angkat Construction and Supplies | [5 empty] | 2025-04-30 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-05-25 | 2025-05-23 |  | 2025-05-26 | [5 empty] | PO Issued | 137 |  | #N/A
PH090231 | NS-NTG23-D98 | Brgy.Victoria02_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 7.0479 | 122.1842 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | [5 empty] | #REF! | [7 empty] | 2025-04-23 |  |  |  |  | COOP Surveyed | #VALUE! | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140249 | NS-NTG23-E05 | Brgy.Tukanalipao_Mamasapano_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090228 | NS-NTG23-E08 | Brgy.Buenavista01_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 7.2233 | 122.2456 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-10-02 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110610 | NS-NTG23-E11 | Brgy.Mulig02_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120340 | NS-NTG23-E26 | Brgy.Katangawan01_GeneralSantosCity_SouthCotabato | Marlone | SOCOTECO II | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | 0 | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110616 | NS-NTG23-E48 | Brgy.SanIsidro(Licanan)_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.2597 | 125.6226 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120349 | NS-NTG23-E62 | Brgy.Fatima02_GeneralSantosCity_SouthCotabato | Marlone | SOCOTECO II | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | 0 | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p.2 LGU Applied- Advance build | ADV. RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090209 | NS-NTG23-E72 | Brgy.Ilaya_DapitanCity_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | City of Dapitan | 0 | 8.5444 | 123.4337 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-06-18 | 2025-02-07 |  |  | #REF! |  | SGDynamics Construction OPC | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-20 | 2025-08-23 |  | 2025-08-26 | [5 empty] | PO Issued | 45 |  | #N/A
PH100303 | NS-NTG23-E96 | Brgy.Alae_ManoloFortich_BUKIDNON | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | 0 | 8.434 | 124.8052 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-08 |  | 21/08/2025 |  | #REF! |  | Angkat Construction and Supplies | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-25 | 2025-05-23 |  | 2025-05-26 | [5 empty] | PO Issued | 137 |  | #N/A
PH100336 | NS-NTG23-E97 | Brgy.Cabangahan_MalaybalayCity(Capital)_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay (Capital) | Purok 4 | 8.0212 | 125.1402 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-04-03 | 2025-10-04 | 2025-05-06 |  | #REF! |  | BC Ubarco Engineering Consultancy | [5 empty] | 2025-04-28 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-05-07 | 2025-05-06 |  | 2025-05-09 | [5 empty] | PO Issued | 154 |  | #N/A
PH100360 | NS-NTG23-F04 | Brgy.Robocon_Linamon_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Linamon | Brgy. Taytay, Ditucalan, Iligan City | 8.1638 | 124.1894 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130179 | NS-NTG23-F06 | Brgy.Garcia_SantaMonica(Sapao)_SurigaoDelNorte | Marlone | SIARELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | Santa Monica | 0 | 10.0505 | 126.0621 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-07-16 | 2025-07-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100315 | NS-NTG23-F10 | TcoColoc_Brgy.Magoong_Linamon_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Linamon | 0 | 8.1822 | 124.1445 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-04 | 2025-01-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100376 | NS-NTG23-F23 | Brgy.Poblacion_Impasug-ong_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Impasug-ong | Sitio CMK | 8.2843 | 124.9903 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-27 |  |  |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-20 | 2025-08-23 |  | 2025-08-26 | [5 empty] | PO Issued | 45 |  | #N/A
PH140234 | NS-NTG23-F24 | Brgy.Tanum_Patikul_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Patikul | 0 | 6.0843 | 121.0676 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-04 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090216 | NS-NTG23-F25 | Brgy.Sulangon_DapitanCity_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | City of Dapitan | Purok Molave | 8.6041 | 123.4172 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-18 |  | 16/09/2025 |  | #REF! |  | SGDynamics Construction OPC | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-18 | 2025-08-17 |  | 2025-08-20 | [5 empty] | PO Issued | 51 |  | #N/A
PH090225 | NS-NTG23-F28 | Brgy.Lantian_Labangan_ZamboangaDelSur | Marlone | ZAMSURECO I | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Labangan | 0 | 7.8848 | 123.4947 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-06-25 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100275 | NS-NTG23-F53 | Brgy.Lapasan03_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100326 | NS-NTG23-F85 | Brgy.Bacusanon_Pangantucan_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Pangantucan | 0 | 7.8712 | 124.7367 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-15 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130180 | NS-NTG23-G24 | Brgy.SantaFe_GeneralLuna_SurigaoDelNorte | Marlone | SIARELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | General Luna | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070523 | NS-NTG23-H06 | T6BU_BrgySabang_LARENA_SIQUIJOR | Ralph | #N/A | BTS 8 | T6 | VIS | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060456 | NS-NTG23-H45 | T6BU_BrgyBarangay5(Pob.)_SanJose_Antique_MACRO_CAPCOV2023 | Ralph | ANTECO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Antique | San Jose (Capital) | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-27 |  |  |  | #REF! |  | ALT Electrical Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-26 | 2025-08-25 |  | 2025-08-28 | [5 empty] | PO Issued | 43 |  | #N/A
PH100389 | NS-NTG23-J12 | Brgy.Dahilayan_ManoloFortich_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Purok 2 | 8.2239 | 124.8498 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 | 2025-02-06 | 21/07/2025 |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-04 | 2025-07-04 |  | 2025-07-07 | [5 empty] | PO Issued | 95 |  | #N/A
PH070438 | NS-NTG23-J35 | T6BU_BrgyCabulihan_TUBIGON_BOHOL_MACRO_COV2023 | Ralph | BOHECO I | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Bohol | Tubigon | 0 | 9.9476 | 123.9775 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-08 | 2025-12-03 | 2025-12-04 | 2025-04-28 | #REF! |  | Abba Electricware Corp. | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-13 | 2025-05-12 |  | 2025-05-15 | [5 empty] | PO Issued | 148 |  | #N/A
PH140265 | NS-NTG23-J86 | Brgy.Katil_DatuPaglas_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110617 | NS-NTG23-K03 | MarilogDistrictHostpital_BrgyMarilog_DavaoCity_DDS | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH050295 | NS-NTG23-K63 | 2023CapSite_BrgyPanaytayan_Ragay_CamarinesSur | Marilyn | CASURECO I | BTS 7 | T5 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  |  | #REF! |  | North Flash Power And Builds Inc. |  |  | direct to Permanent | [7 empty] | BP Secured | FALSE | [12 empty] | BP Secured |  | Waiting for ROW nego to INC | #N/A
PH110564 | NS-NTG23-K65 | Brgy.Langub02_DavaoCity_DDS | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.1173 | 125.5559 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH130146 | NS-NTG23-O16 | Brgy.Bretania_SanAgustin_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | San Agustin | Purok 5 | 8.6951 | 126.2074 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 | 2025-05-07 | 2025-10-09 |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-11 | 2025-09-12 |  | 2025-09-15 | [5 empty] | PO Issued | 25 |  | #N/A
PH030845 | NS-NTG23-O43 | BrgyDuhat_Bocaue_Bulacan_PhArena | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Bocaue | 0 | 14.7886 | 120.9561 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-25 | 2025-09-08 | 2025-09-09 |  | #REF! |  | JRJA Builders Supply and Services Co. | 2025-09-08 | 2025-09-08 | direct to permanent | 2025-09-09 | FTAPPO0011519 | 2025-09-16 |  |  | Yes |  | COOP Surveyed |  |  | 10/03/2025: Applied permanent power, awaiting JTSS sched. 9/23/2025: LGU did not allow us to apply for temporary power since site is already done. Applied for permanent power. | 2025-08-18 | 2025-08-19 | 2025-10-06 | FTAPPQ0012925 | 2025-10-08 | FTAPPO0012058 | 2025-11-20 | 2025-11-23 |  |  | Line Construction Completed |  | 10/20/2025: Awaiting survey design from Meralco. | #N/A
PH030828 | NS-NTG23-P03 | BrgyBawa_Gerona_Tarlac_T2 | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Gerona | 0 | 0 | 0 | TSSR Approved by D&E/PMO | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH010401 | NS-NTG23-P13 | BrgyLasip_Lingayen (Capital)_Pangasinan_T2 | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Lingayen (Capital) | 0 | 15.9414 | 120.2451 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-05-26 | 2025-10-06 |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-15 | 2025-10-24 |  |  | Tempo Energized |  | Billing Arrears | 10/20 waiting for energization schedule for TTC 10/13 waiting for energization schedule 10/9/25; Waiting Tempo Energization | 2025-09-22 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 | 2025-09-29 | 2025-10-05 |  |  | Line Construction Completed | 5 | 10/13 for transformer testing and materials and final inspection, follow up postcon permits | #N/A | #REF!
PH010461 | NS-NTG23-P14 | BrgyLucao_DagupanCity_Pangasinan_BangusFest | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | b. Candidate Secured | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030807 | NS-NTG23-P29 | BrgySanJose_TarlacCity_Tarlac_Shout | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150125 | NS-NTG23-P37 | TCO_BrgyTinoc_Ifugao_Benguet | Marilyn | IFELCO | BTS 7 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  | 2025-07-22 | #REF! |  | Carlson Electrical Supply and Services |  |  | direct to Permanent | [7 empty] | BP Secured | FALSE |  | For Permanent power | 2025-07-25 | 2025-07-25 | 2025-07-25 | FTAPPQ0011572 | 2025-07-28 | FTAPPO0010801 | 2025-09-14 | 2025-09-16 | 2025-10-01 | 2026-01-27 | Permanent Energized | 24 | 10/6/25: Waiting for COOP inspection prior to energizationon schedule and approval of NEA. | #N/A
PH010337 | NS-NTG23-P98 | BrgyNavotasSouth_LaoagCIty_IlocosNorte_SandDunes | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | City of Laoag (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! |  | BK Engineering Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | BK ENGINEERING | #REF!
PH010305 | NS-NTG23-Q01 | BrgyPoblacion2_Pasuquin_IlocosNorte | Marilyn | INEC | BTS 7 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | RTB | Yes |  |  |  | 2025-08-13 | #REF! |  | BK Engineering Services |  |  | direct to Permanent | [7 empty] | BP Secured | FALSE |  | Permanent power energized | 2025-07-22 | 2025-07-23 | 2025-07-20 | FTAPPQ0011524 | 2025-07-23 | FTAPPO0010746 | 2025-10-01 | 2025-10-01 |  | 2025-11-21 | Permanent Energized | 79 |  | #N/A
PH030842 | NS-NTG23-Q06 | BrgyBalibago_AngelesCity_Pampanga_HotAirFest3 | CJ | CEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of Angeles | 0 | 0 | 0 | a.6. Long lead time lessor | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110611 | NS-NTG23-Q25 | BrgyMulig02_DavaoCity_DDS | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110627 | NS-NTG23-Q27 | Brgy.NewValencia02_DavaoCity_DDS | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110578 | NS-NTG23-Q30 | Quality_BrgyAplaya02_DigosCity_DDS | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Digos (Capital) | Luna Bataan Street | 6.7474 | 125.3647 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-18 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100325 | NS-NTG23-Q32 | BrgyMiglamin_Malaybalay_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay (Capital) | Purok 1A | 8.0388 | 125.2442 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-03-29 | 2025-07-04 | 2025-01-07 |  | #REF! |  | BC Ubarco Engineering Consultancy | [5 empty] | 2025-04-29 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-05-13 | 2025-05-12 |  | 2025-05-15 | [5 empty] | PO Issued | 148 |  | #N/A
PH140193 | NS-NTG23-Q34 | BrgyCabasaran_MarawiCity_LanaodelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | City of Marawi (Capital) | P-3 | 8.0357 | 124.2958 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-09 |  |  |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | 2025-09-26 | 2025-10-02 | [8 empty] | BoQ Approved | 8 |  | #N/A
PH100328 | NS-NTG23-Q38 | BrgySinuda (Simod)_Kitaotao_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Kitaotao | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100348 | NS-NTG23-Q43 | BrgyMaraymaray_DON CARLOS_BUK | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Don Carlos | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH130137 | NS-NTG23-Q46 | BrgyDoongan_ButuanCity_AGN | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | City of Butuan (Capital) | Brgy. Ambago, Butuan City, Agusan del Norte | 8.9594 | 125.5131 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110567 | NS-NTG23-Q54 | Brgy.Magatos01_Asuncion(Saug)_DavaoDelNorte | Marlone | NORDECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Norte | Asuncion | 0 | 7.5555 | 125.7267 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-11 | 2025-04-05 | 2025-08-06 |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-13 | 2025-05-12 |  | 2025-05-15 | [5 empty] | PO Issued | 148 |  | #N/A
PH090215 | NS-NTG23-Q89 | Brgy.Tiayon_Ipil(Capital)_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil (Capital) | 0 | 7.7598 | 122.5637 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-10 |  |  |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-28 | 2025-08-30 |  | 2025-09-02 | [5 empty] | PO Issued | 38 |  | #N/A
PH090210 | NS-NTG23-Q91 | Brgy.Obay_Polanco_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Polanco | 0 | 8.5455 | 123.3613 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090233 | NS-NTG23-Q98 | Brgy.LowerBayao_Tukuran_ZamboangaDelSur | Marlone | ZAMSURECO I | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tukuran | 0 | 7.8525 | 123.5594 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-05 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090238 | NS-NTG23-R09 | Brgy.Guilawa_Malangas_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Malangas | 0 | 7.6718 | 123.0062 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 | 2025-03-07 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100387 | NS-TER24-A102 | Brgy.Pook_Talisayan_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100367 | NS-TER24-A124 | Brgy.SantaAna01_Tagoloan_MisamisOriental | Marlone | LASURECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Zone 3 | 8.5343 | 124.7942 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-17 |  | 19/09/2025 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-14 | 2025-08-15 |  | 2025-08-18 | [5 empty] | PO Issued | 53 |  | #N/A
PH100278 | NS-TER24-A141 | Brgy.Tablon02_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH120357 | NS-TER24-A142 | Brgy.Klubi_LakeSebu_SouthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | 0 | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100293 | NS-TER24-A152 | Brgy.Ulaliman_ElSalvadorCity_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | 0 | 0 | 0 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100366 | NS-TER24-A160 | Brgy.Natubo01_Jasaan_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100337 | NS-TER24-A168 | Brgy.Pagawan01_Manticao_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Purok 1 | 8.3885 | 124.2987 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-21 |  | 19/08/2025 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-30 | 2025-07-29 |  | 2025-08-01 | [5 empty] | PO Issued | 70 |  | #N/A
PH110625 | NS-TER24-A182 | Brgy.Subasta01_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | p.2 LGU Applied- Advance build | ADV. RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100323 | NS-TER24-A201 | Brgy.Matangad_Gitagum_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | Brgy. Matangad, Gitagum, Misamis Oriental | 8.5765 | 124.3722 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100329 | NS-TER24-A209 | Brgy.Tambagan_Medina_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Medina | 0 | 8.9074 | 125.0127 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-30 |  | 2025-01-07 |  | #REF! |  | S.A.S Electrical Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-04 | 2025-07-04 |  | 2025-07-07 | [5 empty] | PO Issued | 95 |  | #N/A
PH100365 | NS-TER24-A226 | Brgy.Baybay_Alubijid_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Purok 4 | 8.5873 | 124.4766 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-14 |  | 2025-12-09 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | 2025-09-26 | 2025-10-01 | [8 empty] | BoQ Approved | 9 |  | #N/A
PH100401 | NS-TER24-A244 | Brgy.SanJuan_GingoogCity_MisamisOriental | Marlone | 0 | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100382 | NS-TER24-A251 | Brgy.Gimaylan_Libertad_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Purok 2 | 8.5498 | 124.3397 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-06-18 | 2025-09-07 |  |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-29 | 2025-08-30 |  | 2025-09-02 | [5 empty] | PO Issued | 38 |  | #N/A
PH100379 | NS-TER24-A264 | Brgy.Hinaplanan01_Claveria_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Claveria | 0 | 8.6448 | 124.841 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-09 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100332 | NS-TER24-A273 | Brgy.Poblacion_Gitagum_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | 0 | 8.5884 | 124.4191 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100291 | NS-TER24-A285 | Brgy.Lumbia03_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 8.3961 | 124.6045 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-18 | 2025-04-08 | 25/09/2025 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | 2025-09-15 | 2025-09-30 | 2025-09-29 |  | 2025-10-02 | [5 empty] | PO Issued | 8 |  | #N/A
PH100308 | NS-TER24-A286 | Brgy.SantaCruz01_Claveria_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Claveria | 0 | 8.6225 | 124.9081 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-21 |  | 26/09/2025 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-12 | 2025-09-12 |  | 2025-09-15 | [5 empty] | PO Issued | 25 |  | #N/A
PH100363 | NS-TER24-A319 | Brgy.Cabalantian02_Manticao_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Purok Bougainvilla | 8.3686 | 124.3289 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-29 | 2025-05-06 | 25/07/2025 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-30 | 2025-07-29 |  | 2025-08-01 | [5 empty] | PO Issued | 70 |  | #N/A
PH110628 | NS-TER24-A325 | Brgy.Saloy_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | p.2 LGU Applied- Advance build | ADV. RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100372 | NS-TER24-A33 | Brgy.Puerto01_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 8.458 | 124.7846 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-22 | 2025-11-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110614 | NS-TER24-A331 | Brgy.Tamugan_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | p. LGU Applied | 0 | #REF! | #REF! | #REF! |  | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110621 | NS-TER24-A333 | Brgy.Maraga-a_Kiblawan_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | Kiblawan | Purok 4 | 6.5892 | 125.2398 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-07-28 | 2025-07-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090230 | NS-TER24-A354 | Brgy.Baluno_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 6.9812 | 122 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-10-02 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110607 | NS-TER24-A355 | Brgy.Litos_Kiblawan_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 6.5169 | 125.2445 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-08-15 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100364 | NS-TER24-A398 | Brgy.Tubajon02_Laguindingan_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | 0 | 8.6216 | 124.4591 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | [5 empty] | #REF! |  | BC Ubarco Engineering Consultancy |  | 2025-10-30 | FTAPPQ0013406 | 2025-11-03 | FTAPPO0012512 | [5 empty] | PO Issued | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100380 | NS-TER24-A415 | Brgy.Pagatpat03_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 8.4446 | 124.5973 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100331 | NS-TER24-A43 | Brgy.Patag_Manticao_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Manticao | 0 | 8.3889 | 124.2826 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-09 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100378 | NS-TER24-A435 | Brgy.Dulong_Libertad_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Purok 1 | 8.5669 | 124.3609 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-18 |  | 2025-05-09 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-29 | 2025-08-30 |  | 2025-09-02 | [5 empty] | PO Issued | 38 |  | #N/A
PH100344 | NS-TER24-A458 | Brgy.Alipuaton01_Salay_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Salay | 0 | 8.8624 | 124.7933 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-21 | 2025-11-06 | 2025-02-08 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-14 | 2025-07-14 |  | 2025-07-17 | [5 empty] | PO Issued | 85 |  | #N/A
PH100388 | NS-TER24-A469 | Brgy.Lanise03_Claveria_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Claveria | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100307 | NS-TER24-A47 | Brgy.Jampason_Jasaan_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100296 | NS-TER24-A49 | Brgy.Malanang01_Opol_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Opol | 0 | 8.5032 | 124.5847 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-09-05 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100309 | NS-TER24-A496 | Brgy.Balubal_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 8.4752 | 124.7687 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-25 |  |  |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-14 | 2025-08-15 |  | 2025-08-18 | [5 empty] | PO Issued | 53 |  | #N/A
PH110562 | NS-TER24-A546 | Brgy.Magtuod_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.1292 | 125.5592 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-10-02 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100374 | NS-TER24-A548 | Brgy.Agusan_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 8.4866 | 124.7502 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 0 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100289 | NS-TER24-A57 | Brgy.Ani-e01_Claveria_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Claveria | Brgy. Patrocino, Claveria, Misamis Oriental | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100370 | NS-TER24-A62 | Brgy.Hinigdaan_ElSalvadorCity_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Zone 1 | 8.5007 | 124.4628 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-07-07 | 2025-07-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110624 | NS-TER24-A632 | Brgy.Binaton02_DigosCity(Capital)_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | f. TSSR submitted to DNE & PMO | 0 | #REF! | #REF! | #REF! |  | g. JTSS Done- Pending TSSR submission | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110615 | NS-TER24-A639 | Brgy.Dacudao01_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | p. LGU Applied | 0 | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110608 | NS-TER24-A664 | Brgy.Kimlawis02_Kiblawan_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090223 | NS-TER24-A72 | Brgy.Esperanza_RamonMagsaysay(Liargo)_ZamboangaDelSur | Marlone | ZAMSURECO I | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Ramon Magsaysay | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140250 | NS-TER24-A757 | Brgy.Salbu_DatuSaudi-Ampatuan_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110622 | NS-TER24-A76 | Brgy.Managa_Bansalan_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | f. TSSR submitted to DNE & PMO | 0 | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140264 | NS-TER24-A789 | Brgy.Mapayag_DatuAnggalMidtimbang_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | a.8. PSH done- For re-hunting | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090218 | NS-TER24-A831 | Brgy.Talinga_Bacungan(LeonT.Postigo)_ZamboangaDelNorte | Marlone | 0 | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Bacungan | 0 | 8.1664 | 122.9421 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-06-19 | 2025-02-07 |  |  | #REF! |  | SGDynamics Construction OPC | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-14 | 2025-08-15 |  | 2025-08-18 | [5 empty] | PO Issued | 53 |  | #N/A
PH100298 | NS-TER24-A84 | Brgy.Kalabaylabay_ElSalvadorCity_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-10-02 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100355 | NS-TER24-A898 | Brgy.Butong02_Quezon_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Quezon | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100362 | NS-TER24-A928 | Brgy.Gango_OzamizCity_MisamisOccidental | Marlone | MOELCI II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Occidental | City of Ozamiz | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p.2 LGU Applied- Advance build | ADV. RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH020184 | NS-TER24-B101 | HT_MP_BrgyVillaColoma(Pob.)_Bagabag_NuevaVizcaya | Arjay | NUVELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Nueva Vizcaya | Bagabag | Purok 1 | 16.641 | 121.2492 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-25 | 2025-08-08 |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 | 2025-09-15 | 2025-10-06 |  |  | Tempo Energized |  |  |  | 2025-09-26 | 2025-10-20 | 2025-10-20 | FTAPPQ0013223 | 2025-10-20 | FTAPPO0012350 |  |  |  |  | PO Issued | 14 |  | #N/A | #REF!
PH150165 | NS-TER24-B105 | HT_MP1_BrgyPaoay_Atok_Benguet | Marilyn | BENECO | BTS 8 | T2 | NLZ | Cordillera Administrative Region (CAR) | Benguet | Atok | 0 | 0 | 0 | e.1. Pending JTSS Actual | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010324 | NS-TER24-B106 | HT_MP_BrgyLubnac_Vintar_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Vintar | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | p.2 LGU Applied- Advance build | ADV. RTB | Yes | 2025-10-02 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 |  |  |  |  | No BP in ST | PO Issued | FALSE |  |  | 2025-12-03 | 2026-01-26 | 2026-01-26 | FTAPPQ0014814 | [6 empty] | PQ Raised | 2 |  | BK ENGINEERING | #REF!
PH020188 | NS-TER24-B107 | HT_MP_BrgyBoneSouth_Aritao_NuevaVizcaya | Arjay | NUVELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | 0 | 16.2381 | 120.9898 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-15 | 2025-02-09 |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 | 2025-10-13 | 2025-10-16 |  |  | Tempo Energized |  |  |  | 2025-11-17 | 2025-11-24 | 2025-11-24 | FTAPPQ0013864 | 2025-11-26 | FTAPPO0012993 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH010341 | NS-TER24-B108 | HT_MP_BrgyBanbanaal_Banayoyo_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Banayoyo | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p.2 LGU Applied- Advance build | ADV. RTB | Yes | 2025-10-02 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 |  |  |  |  | No BP in ST | PO Issued | FALSE |  |  | 2025-12-03 | 2026-01-26 | 2026-01-26 | FTAPPQ0014814 | [6 empty] | PQ Raised | 2 |  | BK ENGINEERING | #REF!
PH150207 | NS-TER24-B109 | HT_MP_Mainit_Bontoc(Capital)_MountainProvince | Arjay | 0 | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc (Capital) | 0 | 0 | 0 | a.4. LOI to possible lessor | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010407 | NS-TER24-B110 | HT_MP_BrgyBatnag_Infanta_PANGASINAN | Marilyn | PANELCO I | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Infanta | 0 | 15.8625 | 119.9083 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | w. For OP application | RTB | Yes | 2025-08-09 | 2025-08-09 |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-10-02 |  |  |  | Tempo Permit Released |  |  | 10/13 waiting for energization schedule 10/11 COL contract signed notarized 10/5/25: COOP applied; waiting COOP Assessment | 2025-12-03 | 2025-12-03 | 2025-12-03 | FTAPPQ0014069 | 2025-12-04 | FTAPPO0013167 | 2025-11-15 | 2025-11-25 |  |  | Line Construction Completed | 32 | 10/13 waiting COOP SOA prior to submit the BOQ | #N/A | #REF!
PH020190 | NS-TER24-B112 | HT_MP_BrgyTabueng_Aritao_NuevaVizcaya | Arjay | NUVELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | 0 | 16.2643 | 121.0422 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-07-25 | 2025-12-08 |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 | 2025-09-15 | 2025-10-07 |  |  | Tempo Energized |  |  |  | 2025-09-26 | 2025-10-20 | 2025-10-20 | FTAPPQ0013223 | 2025-10-20 | FTAPPO0012350 |  |  |  |  | PO Issued | 14 |  | #N/A | #REF!
PH010335 | NS-TER24-B115 | 208WT_BrgySantiago_Marcos_IlocosNorte | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Marcos | 0 | 17.9823 | 120.7202 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-06-23 | 2025-07-07 |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-23 | 2025-10-02 |  |  | Tempo Energized |  |  | #N/A | 2025-09-07 | 2025-11-06 | 2025-11-06 | FTAPPQ0013534 | 2025-11-10 | FTAPPO0012680 |  |  |  |  | PO Issued | 33 | 10/7/25: Waiting BoQ Approval & Submission of Signed Staking Sheet | #N/A | #REF!
PH010453 | NS-TER24-B121 | HT_MP_BrgyDalumpinas_SanNicolas_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030821 | NS-TER24-B124 | HT_MP_Mamonit_Mayantoc_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Mayantoc | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-11-25 |  |  |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-10-08 | 2026-01-14 | FTAPPQ0014580 | 2026-01-16 | FTAPPO0013709 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 |  | MCEES CONSTRUCTION
PH010381 | NS-TER24-B131 | HT_MP_BrgyComillasSouth_Cervantes_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Cervantes | 0 | 16.9263 | 120.7419 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-08-09 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-30 | 2025-10-15 |  |  | Tempo Energized |  | Lacking PreCon Permits | 10/7/25: BP just released; To submit it to COOP; Pending energization as it is located in remote area 10/5/25: Tempo Connection Permit secured; waiting BP copy for energization | 2025-10-10 | 2025-11-26 | 2025-11-26 | FTAPPQ0013919 | 2025-11-27 | FTAPPO0013027 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH020199 | NS-TER24-B133 | HT_MP_BrgyMaguirig_SOLANA_CAGAYAN | Marilyn | CAGELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Solana | Zone 3 | 17.672 | 121.6535 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-07-04 |  | 2025-02-10 | 2025-11-21 | #REF! |  | Bangayan Electrical Services | 2025-08-29 | 2025-10-16 | FTAPPQ0013158 | 2025-10-20 | FTAPPO0012291 | 2025-10-03 | 2025-11-15 | 2025-11-18 |  |  | Tempo Energized | 127 |  | 11/18 Energized 10/6/25: Transformer Testing schedule 10/15/25; Waiting for power interruption schedule on pole insertion | 2025-09-05 | 2025-10-13 | 2025-10-13 | FTAPPQ0013088 | 2025-10-15 | FTAPPO0012215 |  |  |  |  | PO Issued | 35 | 10/6/25: Waiting COOP signed staking sheet for BoQ evaluation | #N/A | #REF!
PH010331 | NS-TER24-B139 | HT_MP_BrgyBantugo_Nagbukel_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Nagbukel | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-10-02 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 |  |  |  |  | No BP in ST | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 |  | BK ENGINEERING | #REF!
PH010365 | NS-TER24-B140 | HT_MP_BrgyElefante_Banayoyo_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Banayoyo | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! |  | BK Engineering Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | BK ENGINEERING | #REF!
PH150166 | NS-TER24-B142 | HT_MP_Tocucan_Bontoc(Capital)_MountainProvince | Arjay | MOPRECO | BTS 8 | T2 | NLZ | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc (Capital) | 0 | 0 | 0 | a. Ongoing site hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010347 | NS-TER24-B144 | HT_MP_BrgyCaraisan_Magsingal_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Magsingal | 0 | 17.7088 | 120.4623 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-10 | 2025-10-07 | 30/08/2025 |  | #REF! |  | Larc Telecoms Inc. | 2025-09-19 | 2025-10-16 | FTAPPQ0013162 | 2025-10-20 | FTAPPO0012293 | 2025-10-20 | 2025-10-22 | 2025-10-24 |  |  | Tempo Energized | 152 |  |  | 2025-09-15 | 2025-09-25 | 2025-09-30 | FTAPPQ0012674 | 2025-10-03 | FTAPPO0011939 |  |  |  |  | PO Issued | 7 |  | #N/A | #REF!
PH010454 | NS-TER24-B146 | HT_MP_BrgyPetal_Dasol_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Dasol | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010368 | NS-TER24-B153 | HT_MP_BrgyAg-agrao_SantaMaria_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Santa Maria | 0 | 17.3845 | 120.519 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-08-09 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-10-14 | 2025-10-17 |  |  | Tempo Energized |  |  | 10/6/25: Installed SEP; Waiting LGU Inspection 10/5/25: for installation SEP; Waiting LGU inspection | 2025-10-10 | 2025-11-26 | 2025-11-26 | FTAPPQ0013919 | 2025-11-27 | FTAPPO0013027 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH030809 | NS-TER24-B157 | HT_MP_Bobon2nd_Camiling_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Camiling | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes |  |  |  |  | #REF! |  | MPS Construction and Trading | 2025-10-08 | 2025-10-16 | FTAPPQ0013164 | 2025-10-20 | FTAPPO0012287 | 2025-11-25 | 2025-11-24 | 2025-12-12 |  |  | Tempo Energized | 103 | [12 empty] | Vendor Allocated | 2 |  | MPS
PH010342 | NS-TER24-B159 | HT_MP_BrgyBao-as_SantaLucia_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Santa Lucia | 0 | 17.1052 | 120.4373 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-04 | 2025-05-08 |  |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-15 | 2025-09-30 |  |  | Tempo Energized |  |  | #N/A | 2025-09-15 | 2025-09-25 | 2025-09-30 | FTAPPQ0012674 | 2025-10-03 | FTAPPO0011939 |  |  |  |  | PO Issued | 7 |  | 10/9/2025: Construction 10/13/25 | #REF!
PH010325 | NS-TER24-B165 | HT_MP_BrgyManayon_Bangui_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Bangui | 0 | 18.5133 | 120.7345 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 |  | 27/08/2025 |  | #REF! |  | BK Engineering Services | 2025-09-05 | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 | 2025-10-23 | 2025-11-05 | 2025-11-18 |  |  | Tempo Energized | 127 |  |  | 2025-09-12 | 2025-10-20 | 2025-10-20 | FTAPPQ0013222 | 2025-10-20 | FTAPPO0012349 |  |  |  |  | PO Issued | 28 | 10/7/25: Waiting BoQ Approval | #N/A | #REF!
PH150208 | NS-TER24-B174 | HT_MP1_Bun-ayan_Sabangan_MountainProvince | Arjay | 0 | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Sabangan | 0 | 0 | 0 | a. Ongoing site hunting | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010348 | NS-TER24-B176 | HT_MP_BrgyCuliong_Salcedo(Baugen)_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Salcedo | 0 | 17.1195 | 120.5059 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-08 | 2025-10-03 | 19/04/2025 | 2025-07-01 | #REF! |  | BK Engineering Services | 2025-05-06 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-05-13 | 2025-05-21 | 2025-05-23 | FTAPPQ0010498 | 2025-05-26 | FTAPPO0009745 |  |  |  | 2025-01-01 | Permanent Energized | 282 |  | #N/A | #REF!
PH010455 | NS-TER24-B178 | HT_MP_BrgyBaquioen01_Sual_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Sual | 0 | 0 | 0 | d. Site re-hunting | 0 | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010375 | NS-TER24-B183 | HT_MP_BrgyRosario(Pob.)_Cervantes_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Cervantes | 0 | 16.9755 | 120.7398 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-08-27 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-30 | 2025-10-15 |  |  | Tempo Energized |  | Lacking PreCon Permits | 10/7/25: BP just released; To submit it to COOP; Pending energization as it is located in remote area 10/5/25: Tempo Connection Permit secured; waiting BP copy for energization | 2025-10-10 | 2025-11-26 | 2025-11-26 | FTAPPQ0013919 | 2025-11-27 | FTAPPO0013027 |  |  |  |  | PO Issued | 32 | 10/7/25: BP just released; To submit it to COOP; Pending energization as it is located in remote area | #N/A | #REF!
PH020198 | NS-TER24-B188 | HT_MP_BrgySanPedro_LASAM_CAGAYAN | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Lasam | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes |  |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-10-08 | 2025-10-16 | FTAPPQ0013158 | 2025-10-20 | FTAPPO0012291 |  | 2025-10-03 |  |  | No BP in ST | Tempo Permit Released | 173 | [12 empty] | Vendor Allocated | 2 |  | BANGAYAN | #REF!
PH020195 | NS-TER24-B200 | HT_MP_BrgyDalena_SanPablo_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | San Pablo | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH010408 | NS-TER24-B208 | HT_MP_BrgyBayambang_Infanta_PANGASINAN | Marilyn | PANELCO I | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Infanta | 0 | 0 | 0 | e.1. Pending JTSS Actual | L - Under pre-construction | #REF! | #REF! | #REF! |  | e.3. TSSR submitted to SAQ, awaiting VO input | 0 | [5 empty] | #REF! |  | LARC | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH150209 | NS-TER24-B211 | HT_MP1_OtucanSur_Bauko_MountainProvince | Arjay | 0 | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | 0 | 0 | 0 | a.4. LOI to possible lessor | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH150153 | NS-TER24-B213 | HT_MP_BrgyNagtupacan_Lagangilang_Abra | Arjay | ABRECO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Abra | Lagangilang | 0 | 17.5908 | 120.7376 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-05-27 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-23 | 2025-10-23 |  |  | Tempo Energized |  |  | 10/5/25: Waiting for Tempo Energization; Tempo CFEI released | 2025-11-18 | 2025-12-10 | 2025-12-10 | FTAPPQ0014151 | 2025-12-12 | FTAPPO0013266 |  |  |  |  | PO Issued | 28 | 10/7/25: Waiting BoQ Approval | #N/A | #REF!
PH020210 | NS-TER24-B216 | HT_MP_BrgyParug-parug_SOLANA_CAGAYAN | Marilyn | CAGELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Solana | 0 | 17.58 | 121.5977 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-07-04 | 2025-02-08 |  |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012299 | 2025-09-09 | FTAPPO0011515 | 2025-09-16 | 2025-09-15 | 2025-10-13 |  |  | Tempo Energized |  |  | 10/7/25: Rescheduled by COOP to 10/13/25 10/6/25: Transformer Testing schedule 10/15/25; Waiting for power interruption schedule on pole insertion | 2025-09-04 | 2025-10-15 | 2025-10-15 | FTAPPQ0013136 | 2025-10-28 | FTAPPO0012305 | 2025-09-29 | 2025-10-02 |  |  | Line Construction Completed | 8 | 10/6/25: Waiting BoQ Approval; signed staking sheet complied | #N/A | #REF!
PH010336 | NS-TER24-B220 | 208WT_BrgyEscoda_Marcos_IlocosNorte | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Marcos | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010340 | NS-TER24-B223 | HT_MP_BrgyBoyboy_Piddig_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Piddig | 0 | 18.1412 | 120.7199 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-07-05 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-15 | 2025-09-01 |  |  | Tempo Energized |  |  |  | 2025-09-07 | 2025-10-30 | 2025-10-30 | FTAPPQ0013399 | 2025-10-31 | FTAPPO0012507 |  |  |  |  | PO Issued | 33 | 10/7/25: Waiting BoQ Approval & Submission of Signed Staking Sheet | #N/A | #REF!
PH020200 | NS-TER24-B225 | HT_MP_BrgyBackiling_Appari_Cagayan | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Aparri | Purok 4 | 18.2867 | 121.5854 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-09 | 2025-05-06 | 2025-07-08 |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-10-16 | FTAPPQ0013158 | 2025-10-20 | FTAPPO0012291 | [5 empty] | PO Issued | FALSE |  | 10/6/25:takeover site from Northflash to Bangayan; Tempo permit | 2025-10-27 | 2025-11-06 | 2025-11-06 | FTAPPQ0013533 | 2025-11-10 | FTAPPO0012683 |  |  |  |  | PO Issued | 25 |  | #N/A | #REF!
PH150163 | NS-TER24-B230 | HT_MP_BrgyPoblacionEast_Pidigan_Abra | Arjay | ABRECO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Abra | Pidigan | 0 | 17.559 | 120.6089 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-08-25 | 2025-06-09 |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 |  |  |  | Yes | COOP Surveyed |  |  |  | 2025-11-18 | 2025-12-10 | 2025-12-10 | FTAPPQ0014151 | 2025-12-12 | FTAPPO0013266 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH150152 | NS-TER24-B240 | HT_MP_BrgyTabiog_Bucay_Abra | Arjay | ABRECO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Abra | Bucay | 0 | 17.5679 | 120.7467 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-11-26 | 2025-12-10 |  | Yes | Tempo Energized |  |  |  | 2025-11-18 | 2025-12-10 | 2025-12-10 | FTAPPQ0014151 | 2025-12-12 | FTAPPO0013266 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH020185 | NS-TER24-B242 | HT_MP_BrgyTubunganEste_GATTARAN_CAGAYAN | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Gattaran | 0 | 18.0424 | 121.6733 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012299 | 2025-09-09 | FTAPPO0011515 | 2025-09-16 | 2025-09-15 |  |  |  | Tempo Permit Released |  |  | 10/7/25: Rescheduled by COOP to 10/13/25 10/6/25: Transformer Testing schedule 10/15/25; Waiting for power interruption schedule on pole insertion | 2025-10-01 | 2025-10-15 | 2025-10-15 | FTAPPQ0013136 | 2025-10-28 | FTAPPO0012305 |  |  |  |  | PO Issued | 9 | 10/6/26: Waiting Signed Staking sheet release/ Waiver for permanent construction | #N/A | #REF!
PH010377 | NS-TER24-B243 | HT_MP_BrgyDinaratan_Salcedo(Baugen)_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Salcedo | 0 | 17.117 | 120.5306 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-14 |  | 30/08/2025 |  | #REF! |  | Larc Telecoms Inc. | 2025-09-15 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 |  |  | 2025-10-14 |  |  | Tempo Energized | 162 |  |  | 2025-09-15 | 2025-09-25 | 2025-09-30 | FTAPPQ0012674 | 2025-10-03 | FTAPPO0011939 |  |  |  |  | PO Issued | 7 |  | #N/A | #REF!
PH010330 | NS-TER24-B251 | HT_MP_BrgyPatac_Galimuyod_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Galimuyod | 0 | 0 | 0 | d. Site re-hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | BK Engineering Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | BK ENGINEERING | #REF!
PH020191 | NS-TER24-B260 | HT_MP_BrgyTresReyes_SAGUDAY_QUIRINO | Marilyn | QUIRELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Quirino | Saguday | 0 | 16.541 | 121.5998 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-30 |  |  | 2025-12-05 | #REF! |  | Carlson Electrical Supply and Services | 2025-08-05 | 2025-11-18 | FTAPPQ0013712 | 2025-11-18 | FTAPPO0012862 | 2025-10-10 | 2025-11-25 | 2025-11-07 |  |  | Tempo Energized | 138 |  | Ongoing seciuring tempo CFEI | 2025-09-23 | 2025-10-03 | 2025-10-09 | FTAPPQ0013017 | 2025-10-13 | FTAPPO0012148 |  |  |  |  | PO Issued | 1 | 10/13/2025 waiting for COOP SOA 10/6/25: Waiting BoQ approval | #N/A | #REF!
PH020189 | NS-TER24-B262 | HT_MP_BrgyPinaripadSur_AGLIPAY_QUIRINO | Marilyn | QUIRELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Quirino | Aglipay | 0 | 16.4672 | 121.6117 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-05-29 |  |  | 2025-10-23 | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-11-04 | FTAPPQ0013482 | 2025-11-05 | FTAPPO0012611 | 2025-09-27 | 2025-10-27 | 2025-10-30 |  |  | Tempo Energized | 146 |  | For issuance of TTC PO while waiting for Permit | 2025-09-15 | 2025-09-23 | 2025-09-27 | FTAPPQ0012678 | 2025-09-30 | FTAPPO0011937 | 2025-10-30 |  |  |  | Line Construction Started | 10 | 10/13/2025 waiting for COOP SOA | #N/A | #REF!
PH020211 | NS-TER24-B264 | HT_MP_BrgyAndabuen_BenitoSoliven_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | Benito Soliven | 0 | 16.8687 | 121.9735 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-15 | 2025-05-06 | 2025-08-08 |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-01 | 2025-10-13 | FTAPPQ0013086 | 2025-10-15 | FTAPPO0012249 | 2025-10-03 | 2025-10-15 | 2026-02-19 |  |  | Tempo Energized | 34 | For TTC PO issuance | 11/21 Line con done 10/20 Waiting COOP SOA released 10/13 - Line con done for transformer testing . 10/17 Line con done for transformer testing today and waiting for COOP SOA 10/4 For application of Tempo CFEI and COOP application tempo permanent facilities | 2025-09-08 | 2025-09-19 | 2025-09-26 | FTAPPQ0012666 | 2025-09-29 | FTAPPO0011865 | 2025-10-08 | 2025-10-13 |  |  | Line Construction Completed | 11 | 10/28 Waiting COOP SOA 10/17 while waiting for Postcon permit proceed for energization for TTC 10/5 For line con and awaiting released of SOA 10/8 Line con done transformr testing and COOP SOA | #N/A | #REF!
PH010379 | NS-TER24-B281 | HT_MP_BrgyBonbon_Burgos_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Burgos | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | e.1. Pending JTSS Actual | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH020212 | NS-TER24-B282 | HT_MP_BrgyLattac_SANTONINO_CAGAYAN | Marilyn | CAGELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Santo Niño | 0 | 0 | 0 | a.4. LOI to possible lessor | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-11-21 |  |  |  | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A | #REF!
PH010374 | NS-TER24-B283 | 208WT_BrgyPaayas_Burgos_IlocosNorte | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Burgos | 0 | 18.4957 | 120.5706 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-08-09 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-29 | 2025-10-07 |  |  | Tempo Energized |  |  | 10/5/25: Waiting for energization TTC; | 2025-10-10 | 2025-11-19 | 2025-11-19 | FTAPPQ0013740 | 2025-11-21 | FTAPPO0012891 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH010369 | NS-TER24-B286 | HT_MP_BrgyBarikir_NuevaEra_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | 0 | 17.9304 | 120.6812 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | w. For OP application | RTB | Yes | 2025-06-25 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-23 | 2025-10-05 |  |  | Tempo Energized |  |  | #N/A | 2025-09-07 | 2025-10-30 | 2025-10-30 | FTAPPQ0013399 | 2025-10-31 | FTAPPO0012507 |  |  |  |  | PO Issued | 33 | 10/7/25: Waiting BoQ Approval & Submission of Signed Staking Sheet | #N/A | #REF!
PH020213 | NS-TER24-B288 | HT_MP_BrgySanRoque_PEÑABLANCA_CAGAYAN | Marilyn | CAGELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Peñablanca | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH150210 | NS-TER24-B292 | HT_MP_Sacasacan_Sadanga_MountainProvince | Arjay | 0 | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | 0 | 0 | 0 | a.1. For Re-Site Hunting (Option Disapproved) | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010366 | NS-TER24-B296 | HT_MP_BrgyValdez_Banna_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Banna | 0 | 17.9647 | 120.7103 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-11 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-10-20 | 2025-11-10 | 2025-11-20 |  |  | Tempo Energized | 125 |  |  | 2025-12-03 | [9 empty] | BoQ Submitted | 2 |  | BK ENGINEERING | #REF!
PH010456 | NS-TER24-B299 | HT_MP_BrgySanVicente_ROSALES_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | f. TSSR submitted to DNE & PMO | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH020197 | NS-TER24-B300 | HT_MP_BrgySanPedro_Mallig_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | Quezon | 0 | 17.2313 | 121.6077 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-05-21 |  |  |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-12 | 2025-10-13 | FTAPPQ0013086 | 2025-10-15 | FTAPPO0012249 | 2025-10-06 | 2025-10-15 | 2025-11-17 |  |  | Tempo Energized | 128 | For TTC PO issuance | 11/17 Energized 10/20 Waiting COOP SOA released 10/17 For ine con next week 10/13 Ongoing securing tempo CFEI 10/10 LOI submitted to COOP | 2025-09-24 | 2025-10-20 | 2025-10-20 | FTAPPQ0013230 | 2025-10-20 | FTAPPO0012353 | 2025-10-30 | 2025-11-07 | 2025-11-10 |  | Bill deposit Paid | 21 | 10/28 COOP SOA for payment prior transformer installation 10/17 Waiting for PO issuance 10/7 Vendor to review counter offer procurement | #N/A | #REF!
PH020214 | NS-TER24-B303 | HT_MP1_BrgyBagongSikat_SanMateo_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | San Mateo | 0 | 16.9479 | 121.5594 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-08-28 |  |  |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0012307 | 2025-09-09 | FTAPPO0011518 | 2025-09-16 |  |  |  | Yes | COOP Surveyed |  |  | 10/13 still waiting for precon permit 10/6/25: cannot proceed works; no BP released | [10 empty] | Vendor Allocated | 32 | 10/13 Survey done waiting for COOP SOA prior BOQ submission | #N/A | #REF!
PH150160 | NS-TER24-B305 | HT_MP_BrgyNamillangan1_ALFONSO LISTA (POTIA)_IFUGAO | Marilyn | IFELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Ifugao | Alfonso Lista | 0 | 0 | 0 | TSSR Approved by D&E/PMO | L - Under pre-construction | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! |  | Carlson Electrical Supply and Services | [10 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A | #REF!
PH150168 | NS-TER24-B307 | HT_MP2_BrgySapid_Mankayan_Benguet | Marilyn | BENECO | BTS 8 | T2 | NLZ | Cordillera Administrative Region (CAR) | Benguet | Mankayan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH020215 | NS-TER24-B312 | HT_MP_BrgyMasipiWest_Cabagan_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | Cabagan | 0 | 17.3821 | 121.8532 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-20 |  |  | 2025-12-05 | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-01 | 2025-10-13 | FTAPPQ0013093 | 2025-10-15 | FTAPPO0012248 | 2025-10-03 | 2025-11-10 |  |  |  | Tempo Permit Released | 135 | For TTC PO issuance | 11/17 For primary construction 0f coop 10/13 - Ongoing line con 10/4 For application of Tempo CFEI and COOP application tempo permanent facilities | 2025-09-08 | 2025-09-19 | 2025-09-26 | FTAPPQ0012666 | 2025-09-29 | FTAPPO0011865 | 2025-10-13 | 2025-11-07 |  |  | Line Construction Completed | 11 | 10/5 For line con and awaiting released of SOA 10/8 Line con done transformr testing and COOP SOA | #N/A | #REF!
PH020216 | NS-TER24-B315 | HT_MP_BrgyAneg_DelfinAlbano(Magsaysay)_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | Delfin Albano | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-11-21 |  |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | CARLSON | #REF!
PH010321 | NS-TER24-B319 | HT_MP_BrgySaoit_Burgos_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Burgos | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes |  |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-11-14 | FTAPPQ0013675 | 2025-11-18 | FTAPPO0012821 | 2025-11-12 | 2025-11-17 | 2025-11-27 |  |  | Tempo Energized | 118 |  |  | 2025-12-03 | [9 empty] | BoQ Submitted | 2 |  | BK ENGINEERING | #REF!
PH020217 | NS-TER24-B322 | HT_MP_BrgyRogus_CauayanCity_Isabela | Marilyn | ISELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | City of Cauayan | 0 | 16.7944 | 121.9482 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | a.3. for Final dispo | 0 | [5 empty] | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0012307 | 2025-09-09 | FTAPPO0011518 | 2025-09-16 |  |  |  | Yes | COOP Surveyed |  |  | 10/13 Waiting for BP and EP permits need for application of Tempo CFEi. | 2025-10-13 | [9 empty] | BoQ Submitted | 32 | For BOQ submission | #N/A | #REF!
PH150167 | NS-TER24-B323 | HT_MP_KayanEast_Tadian_MountainProvince | Arjay | MOPRECO | BTS 8 | T2 | NLZ | Cordillera Administrative Region (CAR) | Mountain Province | Tadian | 0 | 0 | 0 | f. TSSR submitted to DNE & PMO | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH020209 | NS-TER24-B338 | HT_MP_BrgySanJuan_Quezon_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | Quezon | 0 | 17.2586 | 121.6338 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-14 | 2025-08-07 |  |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-12 | 2025-10-13 | FTAPPQ0013093 | 2025-10-15 | FTAPPO0012248 | 2025-10-06 | 2025-10-20 | 2025-11-17 |  |  | Tempo Energized | 128 | For TTC PO issuance | 11/17 Energized 10/13 Ongoing securing tempo CFEI 10/20 Waiting COOP SOA released 10/10 LOI submitted to COOP | 2025-09-19 | 2025-10-20 | 2025-10-20 | FTAPPQ0013230 | 2025-10-20 | FTAPPO0012353 | 2025-10-30 | 2025-11-07 | 2025-11-10 |  | Bill deposit Paid | 21 | 10/7/25: Vendor to review counter offer procurement | #N/A | #REF!
PH020218 | NS-TER24-B342 | HT_MP_BrgyMaraburab_ALCALA_CAGAYAN | Marilyn | CAGELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Alcala | 0 | 17.9455 | 121.6457 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-07-25 |  |  |  | #REF! |  | North Flash Power And Builds Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012313 | 2025-09-09 | FTAPPO0011523 | 2025-09-16 | 2025-09-30 | 2025-10-07 |  |  | Tempo Energized |  |  | TEMPO TO COOP Enenrgized | 2025-09-15 | [9 empty] | BoQ Submitted | 25 |  | #N/A | #REF!
PH010382 | NS-TER24-B344 | HT_MP_BrgyPoblacionSur_Lidlidda_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Lidlidda | 0 | 17.2499 | 120.5215 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-08-25 |  |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-10-22 | 2025-10-29 |  |  | Tempo Energized |  |  | 10/6/25: Installed SEP; Waiting LGU Inspection 10/5/25: for installation SEP; Waiting LGU inspection | 2025-10-15 | 2025-11-07 | 2025-11-07 | FTAPPQ0013554 | 2025-11-10 | FTAPPO0012682 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH010370 | NS-TER24-B354 | HT_MP_BrgySanta Maria_Piddig_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Piddig | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! |  | BK Engineering Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | BK ENGINEERING | #REF!
PH010367 | NS-TER24-B368 | HT_MP_BrgyAblanSarat_Burgos_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Burgos | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-02 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-10-23 | 2025-11-05 | 2025-11-18 |  |  | Tempo Energized | 127 |  |  | 2025-12-03 | [9 empty] | BoQ Submitted | 2 |  | BK ENGINEERING | #REF!
PH010333 | NS-TER24-B370 | HT_MP_BrgySabangan-Bato_Galimuyod_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Galimuyod | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010400 | NS-TER24-B378 | HT_MP_BrgyCamangaan_SISON_PANGASINAN | Marilyn | LUELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Sison | 0 | 16.1582 | 120.495 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-30 | 2025-02-09 | 2025-01-10 |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-15 | 2025-10-11 |  |  | Tempo Energized |  |  | TEMPO TO COOP Enenrgized | 2025-09-15 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 | 2025-09-23 | 2025-09-29 |  |  | Line Construction Completed | 11 |  | #N/A | #REF!
PH150164 | NS-TER24-B381 | HT_MP_BrgyLangbaban_SanIsidro_Abra | Arjay | ABRECO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Abra | San Isidro | 0 | 17.4615 | 120.6014 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-13 | 2025-01-08 |  |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-23 | 2025-10-23 |  |  | Tempo Energized |  |  | 10/5/25: Waiting for Tempo Energization; Tempo CFEI released | 2025-11-18 | 2025-12-10 | 2025-12-10 | FTAPPQ0014151 | 2025-12-12 | FTAPPO0013266 |  |  |  |  | PO Issued | 28 | 10/7/25: Waiting BoQ Approval | #N/A | #REF!
PH020219 | NS-TER24-B390 | HT_MP_BrgyNamuccayan_SANTONINO_CAGAYAN | Marilyn | CAGELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Santo Niño | 0 | 0 | 0 | a.4. LOI to possible lessor | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010328 | NS-TER24-B393 | 208WT_BrgyDadaeman_Pasuquin_IlocosNorte | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-10-02 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-10-20 | 2025-11-17 | 2025-11-28 |  |  | Tempo Energized | 117 |  |  | 2025-12-03 | [9 empty] | BoQ Submitted | 2 |  | BK ENGINEERING | #REF!
PH010384 | NS-TER24-B399 | HT_MP_BrgyMatue-Butarag_GregoriodelPilar_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Gregorio del Pilar | 0 | 0 | 0 | h. Pending GT TSSR Approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010457 | NS-TER24-B437 | HT_MP_BrgyMalimpin_Dasol_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Dasol | 0 | 0 | 0 | c. Ongoing candidate pre-approval | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010380 | NS-TER24-B445 | HT_MP_BrgyDan-ar_Santiago_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Santiago | 0 | 0 | 0 | a.2. On-hold by GT | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH010351 | NS-TER24-B461 | HT_MP_BrgySurngit_SanJuan(Lapog)_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | San Juan | 0 | 17.7539 | 120.4315 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-09 | 2025-08-06 | 28/07/2025 |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | 2025-10-21 | 2025-10-23 | 2025-10-30 |  |  | Tempo Energized | 146 |  |  | 2025-09-15 | 2025-09-25 | 2025-09-30 | FTAPPQ0012674 | 2025-10-03 | FTAPPO0011939 |  |  |  |  | PO Issued | 7 |  | #N/A | #REF!
PH150212 | NS-TER24-B465 | HT_MP1_Anabel_Sadanga_MountainProvince | Arjay | 0 | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | 0 | 0 | 0 | a.4. LOI to possible lessor | 0 | #REF! | #REF! | #REF! |  | a.2. Long lead time | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH020220 | NS-TER24-B478 | HT_MP_BrgyPaddaya_APARRI_CAGAYAN | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Aparri | 0 | 18.3251 | 121.7331 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012901 | 2025-10-06 | FTAPPO0012036 |  | 2025-09-15 | 2025-10-11 |  |  | Tempo Energized |  |  | 10/6/25: Waiting for TTC energization; Transformer Testing 10/15/25 10/5/25: PQ raised, takeover from Northflash | 2025-10-01 | 2025-10-15 | 2025-10-15 | FTAPPQ0013136 | 2025-10-28 | FTAPPO0012305 |  |  |  |  | PO Issued | 9 | 10/6/26: Waiting Signed Staking sheet release/ Waiver for permanent construction | #N/A | #REF!
PH150213 | NS-TER24-B482 | HT_MP_Banguitan_Besao_MountainProvince | Arjay | 0 | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Besao | 0 | 0 | 0 | a.4. LOI to possible lessor | 0 | #REF! | #REF! | #REF! |  | a.2. Long lead time | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010458 | NS-TER24-B484 | HT_MP_BrgyTara_BOLINAO_PANGASINAN | Marilyn | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Bolinao | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030857 | NS-TER24-B49 | HT_MP_BrgyAtate_PalayanCity_NuevaEcija | CJ | NEECO II – Area 2 | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | City of Palayan (Capital) | 0 | 15.4672 | 120.6535 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-14 | 2025-03-05 | 2025-02-06 | 2025-08-05 | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-04-21 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-09-16 | 2025-09-16 | 2025-09-17 | FTAPPQ0012502 | 2025-09-23 | FTAPPO0011727 | 2025-10-06 | 2025-10-07 | 2025-09-23 | 2025-10-08 | Permanent Energized | 172 | 10/12/2025: ENERGIZED. 10/5/2025: Awaiting NTP for LC sched. | #N/A
PH150155 | NS-TER24-B509 | HT_MP_BrgyColabaoan_SanJuan_Abra | Arjay | ABRECO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Abra | San Juan | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-09-26 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-10-15 | 2025-11-26 | 2025-12-10 |  |  | Tempo Energized | 105 |  |  | 2025-11-18 | 2025-12-10 | 2025-12-10 | FTAPPQ0014151 | 2025-12-12 | FTAPPO0013266 |  |  |  |  | PO Issued | 2 |  | BK ENGINEERING | #REF!
PH010332 | NS-TER24-B55 | HT_MP_BrgyPuro_Magsingal_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Magsingal | 0 | 17.6839 | 120.3585 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-29 |  | 13/07/2025 | 2025-08-20 | #REF! |  | BK Engineering Services | 2025-07-29 | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 | 2025-10-23 | 2025-10-30 | 2025-11-06 |  |  | Tempo Energized | 139 |  |  | 2025-08-05 | 2025-09-04 | 2025-09-05 | FTAPPQ0012260 | 2025-09-08 | FTAPPO0011460 | 2025-10-08 | 2025-10-16 | 2025-11-24 | 2025-11-27 | Permanent Energized | 32 | Waiting line con schedule. | #N/A | #REF!
PH010459 | NS-TER24-B568 | HT_MP_BrgyBaligayan_SANQUINTIN_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | San Quintin | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030824 | NS-TER24-B57 | HT_MP_SanJuandeValdez_SanJose_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | San Jose | 0 | 15.4987 | 120.5134 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-02 |  | 27/08/2025 |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-04-09 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-11-14 | 2025-12-15 | 2025-12-15 | FTAPPQ0014218 | 2025-12-18 | FTAPPO0013321 |  |  |  |  | PO Issued | 184 | 10/20/2026: Awaiting coop BOM. | #N/A
PH020208 | NS-TER24-B59 | HT_MP_BrgyCentroV(Mina)_CLAVERIA_CAGAYAN | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Claveria | 0 | 18.6089 | 121.0874 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-18 | 2025-11-07 | 2025-04-09 |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-10-16 | FTAPPQ0013158 | 2025-10-20 | FTAPPO0012291 | 2025-10-17 | 2025-11-18 | 2025-11-25 |  |  | Tempo Energized | 120 |  |  | 2025-10-27 | 2025-11-06 | 2025-11-06 | FTAPPQ0013533 | 2025-11-10 | FTAPPO0012683 |  |  |  |  | PO Issued | 25 |  | #N/A | #REF!
PH010345 | NS-TER24-B64 | HT_MP_BrgyLanao_Bangui_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Bangui | 0 | 18.5325 | 120.7963 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 |  | 2025-12-09 |  | #REF! |  | BK Engineering Services | 2025-09-05 | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 | 2025-10-22 | 2025-10-24 | 2025-11-05 |  |  | Tempo Energized | 140 |  |  | 2025-09-12 | 2025-10-09 | 2025-10-09 | FTAPPQ0013022 | 2025-10-13 | FTAPPO0012152 |  |  |  |  | PO Issued | 1 | 10/17/25: RoW ongoing 10/7/25: Waiting BoQ Approval | #N/A | #REF!
PH150180 | NS-TER24-B640 | HT_MP_BrgyAnninipan_Flora_Apayao | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Apayao | Flora | 0 | 18.1675 | 121.4458 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-07-25 | 2025-12-08 |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 |  |  |  |  | COOP Surveyed |  |  |  | 2025-11-17 | 2025-11-24 | 2025-11-24 | FTAPPQ0013864 | 2025-11-26 | FTAPPO0012993 |  |  |  |  | PO Issued | 32 |  | #N/A | #REF!
PH150156 | NS-TER24-B700 | HT_MP_BrgySipaProper_SantaMArcela_Apayao | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Apayao | Santa Marcela | 0 | 18.2492 | 121.4164 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-14 |  |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-07-21 | 2025-11-03 | FTAPPQ0013447 | 2025-11-04 | FTAPPO0012560 | [5 empty] | PO Issued | FALSE |  |  | 2025-11-17 | 2025-11-24 | 2025-11-24 | FTAPPQ0013864 | 2025-11-26 | FTAPPO0012993 |  |  |  |  | PO Issued | 81 |  | #N/A | #REF!
PH150178 | NS-TER24-B706 | HT_MP_BrgySwan_Pudtol_Apayao | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Apayao | Pudtol | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! |  | Bangayan Electrical Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | BANGAYAN | #REF!
PH010334 | NS-TER24-B73 | HT_MP_BrgyBungcag_Dingras_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Dingras | 0 | 18.1189 | 120.689 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-22 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-10-20 | 2025-10-27 | 2025-11-04 |  |  | Tempo Energized | 141 |  |  | 2025-12-03 | 2026-01-26 | 2026-01-26 | FTAPPQ0014814 | [6 empty] | PQ Raised | 2 |  | BK ENGINEERING | #REF!
PH020187 | NS-TER24-B75 | HT_MP_BrgyDarapidap_DupaxDelNorte_NuevaVizcaya | Arjay | NUVELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | 0 | 16.3193 | 121.0535 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-25 |  |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 | 2025-09-15 | 2025-10-01 |  |  | Tempo Energized |  |  |  | 2025-09-26 | 2025-10-20 | 2025-10-20 | FTAPPQ0013223 | 2025-10-20 | FTAPPO0012350 |  |  |  |  | PO Issued | 14 |  | #N/A | #REF!
PH150154 | NS-TER24-B76 | HT_MP_BrgyCudog_LAGAWE_IFUGAO | Marilyn | IFELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Ifugao | Lagawe (Capital) | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Carlson Electrical Supply and Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | CARLSON | #REF!
PH030896 | NS-TER24-B770 | HT_MP_BrgyDibacong_Casiguran_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Casiguran | 0 | 16.2428 | 122.0778 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | w. For OP application | RTB | Yes | 2025-07-14 |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012299 | 2025-09-09 | FTAPPO0011515 | 2025-09-16 |  | 2025-12-05 |  |  | Tempo Energized |  | Original BP, EP needed. Requested to SAQ team. | 10/20/2025: Awaiting hardcopy of permits, for submission to AURELCO. 10/12/2025: Applied TTC, for temperament solution | 2025-09-03 | 2025-09-29 | 2025-09-29 | FTAPPQ0012845 | 2025-10-03 | FTAPPO0011986 |  |  |  |  | PO Issued |  | 10/20/2025: Postcon permits needed. For transformer testing. 10/6/2025: Waiting for NTP release for Construction | #N/A | CFEI, OP
PH150162 | NS-TER24-B80 | HT_MP_BrgyPadangitan_Danglas_Abra | Arjay | ABRECO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Abra | Danglas | 0 | 17.647 | 120.6575 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-13 |  | 2025-08-09 |  | #REF! |  | BK Engineering Services | 2025-06-20 | 2025-11-03 | FTAPPQ0013446 | 2025-11-04 | FTAPPO0012561 | 2025-11-07 | 2025-11-26 | 2025-12-10 |  |  | Tempo Energized | 105 |  |  | 2025-11-18 | 2025-12-10 | 2025-12-10 | FTAPPQ0014151 | 2025-12-12 | FTAPPO0013266 |  |  |  |  | PO Issued | 112 |  | #N/A | #REF!
PH030861 | NS-TER24-B81 | HT_MP_BrgyPoblacionWest_Pantabangan_NuevaEcija | CJ | PAMES | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | Pantabangan | Purok 3 | 15.8182 | 121.1368 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-25 |  |  |  | #REF! |  | MPS Construction and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0012312 | 2025-09-09 | FTAPPO0011522 | 2025-09-16 | 2025-09-15 | 2025-09-23 |  |  | Tempo Energized |  |  | 9/27/2025: Energized 9/23/2025: Temporary power applied. For coop JTSS schedule once weather is okay. | 2025-09-05 | 2025-09-30 | 2025-10-09 | FTAPPQ0013018 | 2025-10-13 | FTAPPO0012150 |  |  |  |  | PO Issued |  | 10/20/2025: Awaiting postcon permits. 10/12/2025: for submission of COOP application | #N/A | POSTCON PERMITS NEEDED
PH030898 | NS-TER24-B810 | HT_MP_BrgyGupa_Dipaculao_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Dipaculao | 0 | 15.8769 | 121.5442 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-07-14 |  | 29/09/2025 |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012299 | 2025-09-09 | FTAPPO0011515 | 2025-09-16 | 2025-10-10 | 2025-10-16 |  |  | Tempo Energized |  | Original BP, EP needed. Requested to SAQ team. | 10/20/2025: TTC energized. 10/12/2025: Applied TTC, for temperament solution | 2025-09-03 | 2025-09-29 | 2025-09-29 | FTAPPQ0012845 | 2025-10-03 | FTAPPO0011986 |  |  |  |  | PO Issued |  | 10/20/2025: Postcon permits needed. For transformer testing. 10/6/2025: Waiting for NTP release for Construction | #N/A | CFEI, OP
PH030902 | NS-TER24-B829 | HT_MP_BrgyDiniog_Dilasag_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Dilasag | 0 | 16.3586 | 122.2132 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-30 |  | 23/09/2025 |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012299 | 2025-09-09 | FTAPPO0011515 | 2025-09-16 | 2025-10-09 | 2025-10-15 |  |  | Tempo Energized |  | Original BP, EP needed. Requested to SAQ team. | 10/15/2025: TTC Energized. 10/12/2025: Applied TTC, for temperament solution. For inspection prior to energization. | 2025-09-03 | 2025-10-03 | 2025-10-06 | FTAPPQ0012902 | 2025-10-06 | FTAPPO0012035 |  |  |  |  | PO Issued |  | 10/20/2025: Postcon permits needed. For transformer testing. 10/6/2025: Waiting for NTP release for Construction | #N/A | CFEI, OP
PH150214 | NS-TER24-B831 | HT_MP2_Maducayan_Natonin_MountainProvince | Arjay | 0 | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Natonin | 0 | 0 | 0 | b. Candidate Secured | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030899 | NS-TER24-B832 | HT_MP_BrgyDibaraybay_Dinalungan_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Dinalungan | 0 | 16.1493 | 121.943 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-11 |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-08-27 | 2025-10-13 | FTAPPQ0013085 | 2025-10-15 | FTAPPO0012250 | 2025-09-16 | 2025-10-09 | 2025-12-05 |  |  | Tempo Energized | 110 | Original BP, EP needed. Requested to SAQ team. | 10/20/2025: Applied TTC. JTSS done, LC done, for energization once restoration in the area is done due to typhoon. 10/12/2025: Applied TTC, for temperament solution | 2025-09-03 | 2025-09-29 | 2025-09-29 | FTAPPQ0012845 | 2025-10-03 | FTAPPO0011986 | 2025-09-02 | 2025-09-03 |  |  | Line Construction Completed | 37 | 10/20/2025: Postcon permits needed. For transformer testing. 10/6/2025: Waiting for NTP release for Construction | #N/A | CFEI, OP
PH030897 | NS-TER24-B834 | HT_MP_BrgySimbahan_Dinalungan_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Dinalungan | 0 | 16.1299 | 121.8918 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-30 |  | 29/09/2025 |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012299 | 2025-09-09 | FTAPPO0011515 | 2025-09-16 | 2025-10-13 | 2025-11-30 |  |  | Tempo Energized |  | Original BP, EP needed. Requested to SAQ team. | 10/20/2025: Applied TTC. JTSS done, LC done, for energization once restoration in the area is done due to typhoon. 10/12/2025: Applied TTC, for temperament solution | 2025-09-03 | 2025-09-29 | 2025-09-29 | FTAPPQ0012845 | 2025-10-03 | FTAPPO0011986 |  |  |  |  | PO Issued |  | 10/20/2025: Postcon permits needed. For transformer testing. 10/6/2025: Waiting for NTP release for Construction | #N/A | CFEI, OP
PH030900 | NS-TER24-B836 | HT_MP_BrgyTinib_Casiguran_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Casiguran | 0 | 16.271 | 122.101 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-04 |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013008 | 2025-10-13 | FTAPPO0012160 |  |  | 2025-12-05 |  |  | Tempo Energized | 110 | Original BP, EP needed. Requested to SAQ team. | 10/20/2025: Awaiting hardcopy of permits, for submission to AURELCO. 10/12/2025: Applied TTC, for temperament solution | [10 empty] | Vendor Allocated | 2 |  | BANGAYAN | CFEI, OP
PH150172 | NS-TER24-B85 | HT_MP_BrgyLiwanEast_Rizal_Kalinga | Marilyn | KAELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Kalinga | Rizal | 0 | 17.5141 | 121.6241 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-08-25 |  |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 | 2025-11-25 | 2025-12-06 |  | Yes | Tempo Energized |  | work stopage no permits | TEMPO TO COOP Enenrgized | 2026-01-12 | 2026-01-13 | 2026-01-13 | FTAPPQ0014563 | 2026-01-14 | FTAPPO0013683 |  |  |  |  | PO Issued | 32 | 10/13 Application applied waiting COOP SOA and staking sheet prior Submission of BOQ | #N/A | #REF!
PH030901 | NS-TER24-B860 | HT_MP_BrgyTabas_Casiguran_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Casiguran | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! |  | Dennis Electrical | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | CFEI, OP
PH030881 | NS-TER24-B874 | MP_ConsueloNorte_SANMARCELINO_ZAMBALES | CJ | ZAMECO II | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Zambales | San Marcelino | 0 | 14.9866 | 120.1444 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | MCEES CONSTRUCTION
PH030871 | NS-TER24-B888 | MP_SanJuan_SANTARITA_PAMPANGA | CJ | PELCO II | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | Santa Rita | 0 | 15.0077 | 120.625 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-07-31 |  | 30/09/2025 |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-08 | 2025-09-08 | FTAPPQ0012311 | 2025-09-09 | FTAPPO0011521 | 2025-09-16 |  |  |  | Yes | COOP Surveyed |  |  | 10/20/2025: still awaiting precon permits. 9/23/2025:Advanced build. Awaiting precon permits from SAQ. | 2025-10-15 | 2025-10-17 | 2025-10-17 | FTAPPQ0013210 | 2025-11-03 | FTAPPO0012324 |  |  |  |  | PO Issued |  | 10/20/2025 For tempo to coop application, awaiting postcon permits. | #N/A
PH030875 | NS-TER24-B891 | MP_SantaMonica_SANTARITA_PAMPANGA | CJ | PELCO II | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | Santa Rita | 0 | 14.9936 | 120.6102 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-31 |  |  |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-08 | 2025-09-08 | FTAPPQ0012311 | 2025-09-09 | FTAPPO0011521 | 2025-09-16 | 2025-09-15 | 2025-10-11 |  |  | Tempo Energized |  |  | 10/12/2025: TTC ENERGIZED. 9/23/2025: CME on hold. Lessor contract issue. | 2025-10-15 | 2025-10-17 | 2025-10-17 | FTAPPQ0013210 | 2025-11-03 | FTAPPO0012324 |  |  |  |  | PO Issued |  | 10/20/2025 For coop application, awaiting postcon permits. | #N/A
PH030860 | NS-TER24-B893 | MP1_BrgyNazareth_GeneralTinio_NuevaEcija | CJ | NEECO II – Area 2 | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | General Tinio | Lot 4 Blk 100 | 15.3949 | 121.0761 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 |  | 2025-06-08 | 2025-10-01 | #REF! |  | MPS Construction and Trading | 2025-08-29 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-09-05 | 2025-09-30 | 2025-10-09 | FTAPPQ0013018 | 2025-10-13 | FTAPPO0012150 | 2025-11-19 | 2025-11-22 | 2025-11-20 | 2025-11-28 | Permanent Energized | 1 | 10/20/2025:Still awaiting coop evaluation. 10/12/2025: For coop evaluation and JTSS schedule. 10/5/2025: Awaiting JTSS schedule | #N/A | pendingPQ raising approval; submitted complete documents
PH010323 | NS-TER24-B895 | MP_BrgyBusiingNorte_SanIldefonso_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | San Ildefonso | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010402 | NS-TER24-B904 | HT_MP_BrgyAloleng_AGNO_PANGASINAN | Marilyn | PANELCO I | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Agno | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | [5 empty] | PO Issued | FALSE |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | FTAPPQ0014069 | 2025-12-04 | FTAPPO0013167 |  |  |  |  | PO Issued | 2 |  | Larc Telecoms Inc. | #REF!
PH010354 | NS-TER24-B906 | HT_MP_BrgyAlitaya01_MANGALDAN_PANGASINAN | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Mangaldan | 0 | 0 | 0 | e.1. Pending JTSS Actual | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! |  | LARC | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010393 | NS-TER24-B908 | HT_MP_BrgyBayoyong_BAISITA_PANGASINAN | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Basista | 0 | 15.865 | 120.3795 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-28 |  |  | 2025-12-05 | #REF! |  | Larc Telecoms, Inc. | 2025-09-15 | 2025-10-16 | FTAPPQ0013162 | 2025-10-20 | FTAPPO0012293 | 2025-10-06 | 2025-10-17 | 2025-10-24 |  |  | Tempo Energized | 152 |  | 10/20 waiting for energization schedule for TTC 10/13 Waiting for TTC PO issuance 10/6 COOp accept for TTC application | 2025-09-22 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 |  |  |  |  | PO Issued | 4 | 10/13 Waiting NTP for Line cons | #N/A | #REF!
PH010394 | NS-TER24-B909 | HT_MP_BrgyPatacbo_BASISTA_PANGASINAN | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Basista | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes |  |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 |  | Larc Telecoms Inc. | #REF!
PH010462 | NS-TER24-B912 | HT_MP_Brgy_Pogo_BAUTISTA_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Bautista | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010463 | NS-TER24-B913 | HT_MP_BrgyVillanueva_BAUTSITA_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Bautista | 0 | 0 | 0 | f. TSSR submitted to DNE & PMO | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010452 | NS-TER24-B92 | HT_MP_BrgySanJose_AGUILAR_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Aguilar | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | e.3. TSSR submitted to SAQ, awaiting VO input | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH150149 | NS-TER24-B93 | HT_MP1_BrgyPinukpukJunction_Pinukpuk_Kalinga | Marilyn | KAELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! |  | Carlson Electrical Supply and Services | [10 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A | #REF!
PH030867 | NS-TER24-B94 | HT_MP_Iba_SanJose_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | San Jose | 0 | 15.4744 | 120.4333 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-09-24 |  |  |  | #REF! |  | MPS Construction and Trading | 2025-10-08 | 2025-10-09 | FTAPPQ0013013 | 2025-10-13 | FTAPPO0012154 | 2025-11-21 | 2025-11-19 | 2025-11-27 |  |  | Tempo Energized | 118 |  |  | 2025-11-12 | 2025-11-25 | 2025-11-25 | FTAPPQ0013896 | 2025-11-26 | FTAPPO0012994 |  |  |  |  | PO Issued | 2 | 10/20/2025: For TTC application | MPS
PH030878 | NS-TER24-C241 | HT_MP_BrgyDona_Orani_Bataan | CJ | PENELCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bataan | Orani | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | MCEES CONSTRUCTION
PH030883 | NS-TER24-C246 | HT_MP_BrgyGeneral Lim (Kaput)_Orion_Bataan | CJ | PENELCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bataan | Orion | 0 | 14.6232 | 120.5277 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-02 |  |  |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-10-08 | 2025-10-09 | FTAPPQ0013012 | 2025-10-13 | FTAPPO0012155 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 |  | MCEES CONSTRUCTION
PH030884 | NS-TER24-C248 | HT_MP_BrgyDuale_Limay_Bataan | CJ | PENELCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bataan | Limay | 0 | 14.5463 | 120.5668 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-15 | 2025-12-09 |  |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-09-08 | direct to Permanent | 2025-09-09 | FTAPPO0011520 | 2025-09-16 |  |  | Yes | Yes | COOP Surveyed |  | Lacking PreCon Permits | 10/5/25: Advance Build; No active COL; Cannot proceed works | [10 empty] | Vendor Allocated |  | for submission of BOM | #N/A
PH030876 | NS-TER24-C252 | HT_MP_BrgyBalagtas(Pob.)_Orion_Bataan | CJ | PENELCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bataan | Pilar | 0 | 14.6313 | 120.5705 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-09 | 2025-06-09 |  |  | #REF! |  | Larc Telecoms Inc. | 2025-09-08 | 2025-09-08 | direct to Permanent | 2025-09-09 | FTAPPO0011520 | 2025-09-16 |  |  | Yes | Yes | COOP Surveyed |  | Lacking PreCon Permits | 10/5/25: Advance Build; No active COL; Cannot proceed works | 2025-10-29 | 2025-10-29 | 2025-10-29 | FTAPPQ0013390 | 2025-11-03 | FTAPPO0012506 |  |  |  |  | PO Issued |  | for submission of BOM | #N/A
PH031094 | NS-TER24-C255 | HT_MP_BrgyBagongSilang_SANMIGUEL_BULACAN | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | San Miguel | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH031095 | NS-TER24-C256 | HT_MP_BrgyPaco_SANRAFAEL_BULACAN | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | San Rafael | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH031096 | NS-TER24-C261 | HT_MP_BrgyCalasag_SANILDEFONSO_BULACAN | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | San Ildefonso | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH031097 | NS-TER24-C262 | HT_MP_BrgyBatasanMatanda_SANMIGUEL_BULACAN | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | San Miguel | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH031098 | NS-TER24-C278 | HT_MP_BrgyPoblacion_NORZAGARAY_BULACAN | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | Angat | 0 | 0 | 0 | a.2. On-hold by GT | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH031099 | NS-TER24-C286 | HT_MP_BrgyRealdeCacarong_PANDI_BULACAN | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | Pandi | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030847 | NS-TER24-C291 | HT_MP_BrgyPanginay_BALAGTAS_BULACAN | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Balagtas | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | a.1. For PSH | 0 | [5 empty] | #REF! |  | Golden Design Konstrukt and Trading | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | Golden
PH010327 | NS-TER24-C293 | HT_MP_BrgyCali_Dingras_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Dingras | 0 | 18.07 | 120.6862 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-04 |  | 16/09/2025 |  | #REF! |  | BK Engineering Services | 2025-09-05 | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 | 2025-10-22 | 2025-10-24 | 2025-11-04 |  |  | Tempo Energized | 141 |  |  | 2025-09-12 | 2025-10-20 | 2025-10-20 | FTAPPQ0013222 | 2025-10-20 | FTAPPO0012349 |  |  |  |  | PO Issued | 28 | 10/7/25: Waiting BoQ Approval | #N/A | #REF!
PH010376 | NS-TER24-C294 | HT_MP_BrgySanRoque_Sarrat_ILOCOSNORTE | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Sarrat | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-22 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-10-20 | 2025-11-17 | 2025-12-02 |  |  | Tempo Energized | 113 |  |  | 2025-12-03 | [9 empty] | BoQ Submitted | 2 |  | BK ENGINEERING | #REF!
PH010322 | NS-TER24-C295 | HT_MP_BrgyPandan_Caoayan_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Caoayan | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p.2 LGU Applied- Advance build | ADV. RTB | Yes |  |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-16 | FTAPPQ0013159 | 2025-10-20 | FTAPPO0012292 |  |  |  |  | No BP in ST | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 |  | BK ENGINEERING | #REF!
PH010346 | NS-TER24-C296 | HT_MP_BrgyCaterman_CandonCity_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | City of Candon | 0 | 0 | 0 | h. Pending GT TSSR Approval | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH030856 | NS-TER24-C317 | HT_MP_BrgyCasongsong_Guimba_NuevaEcija | CJ | NEECO II – Area 1 | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | Guimba | 0 | 15.6736 | 120.6535 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-24 | 2025-03-05 | 30/05/2025 | 2025-08-05 | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-05-01 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-10-02 | 2025-10-17 | 2025-10-17 | FTAPPQ0013215 | 2025-10-20 | FTAPPO0012325 | 2025-11-28 | 2025-12-03 | 2025-11-30 | 2025-12-18 | Permanent Energized | 8 | 10/20/2025: Awaiting NTP from coop. 10/12/2025: Awaiting BOM negotiation approval. For PQ raising and NTP. | #N/A | BOM negotiation and NTP
PH030853 | NS-TER24-C319 | HT_MP_BrgySantoRosario_SantoDomingo_NuevaEcija | CJ | NEECO II – Area 1 | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | 0 | 15.6629 | 120.8591 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-29 |  | 22/06/2025 | 2025-07-16 | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-19 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-09-26 | 2025-10-07 | 2025-10-07 | FTAPPQ0012971 | 2025-10-08 | FTAPPO0012098 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-12-03 | Permanent Energized | 2 | 10/20/2025:For material inspection and evaluation. Awaiting NTP. 10/6/25: BoQ waiting vendor acceptance | #N/A | NTP, Material inspection
PH030855 | NS-TER24-C321 | HT_MP_BrgySantaRita_SantoDomingo_NuevaEcija | CJ | NEECO II – Area 1 | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | 0 | 15.6208 | 120.6535 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-29 | 2025-03-04 | 2025-11-06 | 2025-07-16 | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-19 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-09-26 | 2025-10-07 | 2025-10-07 | FTAPPQ0012971 | 2025-10-08 | FTAPPO0012098 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-28 | Permanent Energized | 2 | 10/20/2025:For material inspection and evaluation. Awaiting NTP. 10/6/25: BoQ waiting vendor acceptance | #N/A | NTP, Material inspection
PH030852 | NS-TER24-C325 | HT_MP_BrgyCaanawan_SanJoseCity_NuevaEcija | CJ | SAJELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | San Jose City | 0 | 15.763 | 120.9566 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-06-05 |  |  |  | #REF! |  | MPS Construction and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0012312 | 2025-09-09 | FTAPPO0011522 | 2025-09-16 | 2025-09-15 | 2025-10-06 |  |  | Tempo Energized |  |  | 10/5/25: For energization 10/6/25; rescheduled due to typhoon Paolo | 2025-09-05 | 2025-09-30 | 2025-10-09 | FTAPPQ0013018 | 2025-10-13 | FTAPPO0012150 |  |  |  |  | PO Issued |  | 10/20/2025: Awaiting postcon permits. | #N/A | POSTCON PERMITS NEEDED
PH030850 | NS-TER24-C332 | HT_MP_BrgyCainginTabingIlog_Guimba_NuevaEcija | CJ | NEECO II – Area 1 | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | Guimba | 0 | 0 | 0 | a.2. On-hold by GT | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH030854 | NS-TER24-C338 | HT_MP_BrgySunson_Aliaga_NuevaEcija | CJ | NEECO II – Area 1 | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | Aliaga | Purok 1 | 15.535 | 120.8858 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 |  | 2025-01-09 | 2025-09-26 | #REF! |  | MPS Construction and Trading | 2025-08-29 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-09-05 | 2025-09-30 | 2025-10-09 | FTAPPQ0013018 | 2025-10-13 | FTAPPO0012150 |  |  |  |  | PO Issued | 1 | 10/20/2025: Applied. For schedule of inspection | #N/A | pendingPQ raising approval; submitted complete documents
PH030837 | NS-TER24-C341 | HT_MP_BrgyTalipapa_CabanatuanCity_NuevaEcija | CJ | CELCOR | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | 0 | 15.4732 | 120.9312 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-09 |  | 20/07/2025 |  | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-05-16 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 147 | 10/20/2025: Need CFEI prior to proceeding with the PP application | #N/A | POSTCON PERMITS NEEDED
PH030859 | NS-TER24-C350 | HT_MP_BrgyBatitang_Zaragoza_NuevaEcija | CJ | NEECO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | Zaragoza | 0 | 15.4022 | 120.8078 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-25 | 2025-09-08 |  |  | #REF! |  | MPS Construction and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0012312 | 2025-09-09 | FTAPPO0011522 | 2025-09-16 | 2025-10-08 | 2025-10-12 |  | Yes | Tempo Energized |  |  | 10/12/2025: TTC ENERGIZED. 10/5/25: TARELCO II recently just allowed tempo to COOP; ongoing | 2025-09-05 | 2025-09-30 | 2025-10-09 | FTAPPQ0013018 | 2025-10-13 | FTAPPO0012150 |  |  |  |  | PO Issued |  |  | #N/A | BoQ Approval pending; submitted complete documents
PH030863 | NS-TER24-C353 | HT_MP_BrgyLuyos_SanAntonio_NuevaEcija | CJ | NEECO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | San Antonio | 0 | 15.2837 | 120.8493 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-25 |  | 21/07/2025 |  | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-05-02 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-10-13 | 2025-10-27 | 2025-10-27 | FTAPPQ0013317 | 2025-11-03 | FTAPPO0012436 | 2025-11-26 | 2025-11-30 |  |  | Line Construction Completed | 161 | 10/20/2025: BOQ approved. PO issued. Awaiting NTP from coop. 10/12/2025: For BOQ submission. | #N/A
PH030858 | NS-TER24-C356 | HT_MP_BrgySantaCruz_GapanCity_NuevaEcija | CJ | NEECO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | City of Gapan | 0 | 15.2833 | 120.6535 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-28 |  | 18/06/2025 | 2025-09-05 | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-19 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-09-26 | 2025-09-30 | 2025-10-06 | FTAPPQ0012903 | 2025-10-06 | FTAPPO0012034 | 2025-11-28 | 2025-11-29 | 2025-12-05 | 2025-01-09 | Permanent Energized | 4 | 10/20/2025: Awaiting NTP from coop. | #N/A
PH030872 | NS-TER24-C372 | HT_MP_SanJuan_Macabebe_Pampanga | CJ | PELCO III | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | Macabebe | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030874 | NS-TER24-C377 | HT_MP_Lourdes_Minalin_Pampanga | CJ | PELCO III | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | Minalin | Purok 2 | 14.9672 | 120.7354 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-04 |  | 2025-08-08 | 2025-09-17 | #REF! |  | JRJA Builders Supply and Services Co. | 2025-08-11 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-08-18 | 2025-08-19 | 2025-10-06 | FTAPPQ0012925 | 2025-10-07 | FTAPPO0012058 |  |  |  |  | PO Issued | 3 | 10/20/2025: Awaiting coop SOA prior to trasnformer testing. 10/12/2025: For survey again with the coop prior to releasing of coop design. 10/5/2025: Secured clearance needed by the coop. Awaiting coop SOA and CFEI docs. | #N/A
PH010464 | NS-TER24-C378 | HT_MP_BrgyEstanza_LINGAYEN_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Lingayen (Capital) | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010465 | NS-TER24-C380 | HT_MP_BrgyAmancoro_BINMALEY_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Binmaley | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010466 | NS-TER24-C381 | HT_MP_BrgyPallas_BINMALEY_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Binmaley | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010467 | NS-TER24-C382 | HT_MP_BrgyAngarian_BUGALLON_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Bugallon | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | e.3. TSSR submitted to SAQ, awaiting VO input | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010468 | NS-TER24-C383 | HT_MP_BrgyCabayaoasan02_BUGALLON_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Lingayen (Capital) | 0 | 0 | 0 | d. Site re-hunting | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010360 | NS-TER24-C384 | HT_MP_BrgyTuliao_SANTABARBARA_PANGASINAN | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | San Fabian | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | LARC | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010469 | NS-TER24-C385 | HT_MP_BrgySanVicente_SANJACINTO_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010355 | NS-TER24-C386 | HT_MP_BrgyAlibago_SANTABARBARA_PANGASINAN | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Santa Barbara | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-26 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-09 | FTAPPQ0013011 | 2025-10-13 | FTAPPO0012156 | 2025-10-06 | 2025-11-25 | 2025-12-13 |  |  | Tempo Energized | 102 |  | 10/13 for completion of permits (FSEC and TEmpo CFEI | [6 empty] | 2025-12-05 | 2025-12-08 |  |  | Line Construction Completed | 2 | 10/13 waiting COOP SOA prior to submit the BOQ | Larc Telecoms Inc. | #REF!
PH010470 | NS-TER24-C387 | HT_MP_BrgyPayas_SANTABARBARA_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | f. TSSR submitted to DNE & PMO | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010471 | NS-TER24-C389 | HT_MP_BrgyNantangalan_POZORRUBIO_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | f. TSSR submitted to DNE & PMO | 0 | #REF! | #REF! | #REF! |  | f. TSSR submitted to DNE & PMO | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010403 | NS-TER24-C390 | HT_MP_BrgyVacante_BINALONAN_PANGASINAN | Marilyn | PANELCO III | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Binalonan | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-20 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | 2025-11-15 | 2025-11-25 | 2025-11-29 |  |  | Tempo Energized | 116 |  |  | 2025-12-03 | 2025-12-09 | 2025-12-09 | FTAPPQ0014131 | 2025-12-11 | FTAPPO0013250 | 2025-11-25 | 2025-12-05 |  |  | Line Construction Completed | 2 |  | Larc Telecoms Inc. | #REF!
PH010390 | NS-TER24-C391 | HT_MP_BrgyTebuel_MANAOAG_PANGASINAN | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Manaoag | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-11-05 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | 2026-12-15 |  |  |  |  | COOP Surveyed | #VALUE! | [12 empty] | Vendor Allocated | 2 |  | Larc Telecoms Inc. | #REF!
PH010472 | NS-TER24-C392 | HT_MP_BrgyPugaro_MANAOAG_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Manaoag | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010391 | NS-TER24-C394 | HT_MP_BrgyDomingoAlarcio_LAOAC_PANGASINAN | Marilyn | PANELCO III | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Laoac | 0 | 16.0196 | 120.5505 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-25 | 2025-11-08 |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-15 | 2025-09-29 |  |  | Tempo Energized |  |  |  | 2025-09-15 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 |  |  |  |  | PO Issued | 4 |  | #N/A | #REF!
PH010473 | NS-TER24-C395 | HT_MP_BrgyLabitWest_URDANETA_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010474 | NS-TER24-C396 | HT_MP_BrgyCaramutan_VILASIS_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010475 | NS-TER24-C399 | HT_MP_BrgySalud_NATIVIDAD_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Natividad | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010476 | NS-TER24-C400 | HT_MP_BrgySanAntonio-Arzadon_SANMANUEL_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010399 | NS-TER24-C401 | HT_MP_BrgySamon_SANTAMARIA_PANGASINAN | Marilyn | PANELCO III | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Santa Maria | 0 | 15.9295 | 120.6498 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-08-20 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-15 | 2025-10-31 |  |  | Tempo Energized |  |  | 10/31/TTC ENERGIZED 10/20 waiting for energization schedule for TTC 10/13 Waiting schedule of energization 10/9/25: Waiting energization schedule 10/5/25: COOP applied; waiting COOP Assessment | 2025-11-25 | 2025-11-26 | 2025-11-26 | FTAPPQ0013918 | 2025-11-27 | FTAPPO0013026 |  |  |  |  | PO Issued | 32 | 10/13 waiting COOP SOA prior to submit the BOQ | #N/A | #REF!
PH010404 | NS-TER24-C402 | HT_MP_BrgyPaitan_SANTAMARIA_PANGASINAN | Marilyn | PANELCO III | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Santa Maria | 0 | 15.9628 | 120.6786 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-19 | 2025-04-07 | 14/08/2025 | 2025-09-09 | #REF! |  | Larc Telecoms, Inc. | 2025-09-15 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | [5 empty] | PO Issued | FALSE |  | 10/13 for Permanet power | 2025-09-22 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 | 2025-09-29 | 2025-10-02 |  |  | Line Construction Completed | 11 | 10/13 waiting for clearance prior energization 10/8 Waiting for energization schedule pending due to unpaid electricity bill | #N/A | #REF!
PH010477 | NS-TER24-C403 | HT_MP_BrgyBolintaguen_SANQUINTIN_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | San Quintin | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010478 | NS-TER24-C404 | HT_MP_BrgyCacandungan_NATIVIDAD_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Natividad | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010479 | NS-TER24-C406 | HT_MP_BrgyCanarem_NATIVIDAD_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Natividad | 0 | 0 | 0 | c. Ongoing candidate pre-approval | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010480 | NS-TER24-C408 | HT_MP_BrgyTamayo_SANCARLOS_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | City of San Carlos | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010481 | NS-TER24-C409 | HT_MP_BrgySalinap_SANCARLOS_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | City of San Carlos | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010482 | NS-TER24-C410 | HT_MP_BrgyBacnar_SANCARLOS_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | City of San Carlos | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010363 | NS-TER24-C411 | HT_MP_BrgyCawayanBogtong_MALASIQUI_PANGASINAN | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Malasiqui | 0 | 0 | 0 | e.1. Pending JTSS Actual | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! |  | LARC | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010358 | NS-TER24-C412 | HT_MP_BrgyAnolid_MALASIQUI_PANGASINAN | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Malasiqui | 0 | 15.8993 | 120.4059 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-07-31 | 2025-06-09 |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-09-08 | 2025-09-08 | FTAPPQ0012310 | 2025-09-09 | FTAPPO0011520 | 2025-09-16 | 2025-09-15 | 2025-10-24 |  |  | Tempo Energized |  |  | 10/20 waiting for energization schedule for TTC 10/9/25; Waiting Tempo Energization | 2025-09-22 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 | 2025-09-30 | 2025-10-02 |  |  | Line Construction Completed | 8 | 10/13 waiting for clearance prior energization 10/8 Waiting for energization schedule pending due to unpaid electricity bill | #N/A | #REF!
PH010389 | NS-TER24-C413 | HT_MP_BrgyBituag_URBIZTONDO_PANGASINAN | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Urbiztondo | 0 | 15.8336 | 120.3817 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-09-09 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-09 | FTAPPQ0013011 | 2025-10-13 | FTAPPO0012156 | 2025-10-09 | 2025-11-26 | 2025-12-05 |  |  | Tempo Energized | 110 |  | 10/13 ongoing securing tempo CFEI permits | 2025-12-03 | 2025-12-03 | 2025-12-03 | FTAPPQ0014069 | 2025-12-04 | FTAPPO0013167 |  |  |  |  | PO Issued | 2 | 10/13 waiting COOP SOA prior to submit the BOQ | Larc Telecoms Inc. | #REF!
PH010483 | NS-TER24-C414 | HT_MP_BrgyCaranglaan_ALCALA_PANGASINAN | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | Alcala | 0 | 0 | 0 | e.1. Pending JTSS Actual | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010484 | NS-TER24-C416 | HT_MP_BrgySanNicolas_VILLASIS_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | c. Ongoing candidate pre-approval | 0 | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010485 | NS-TER24-C420 | HT_MP_BrgyMaseil-seil_UMINGAN_PANGASINAN |  | 0 | BTS 8 | T2 | LUZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010405 | NS-TER24-C421 | HT_MP_BrgyZaragoza_BOLINAO_PANGASINAN | Marilyn | PANELCO I | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Bolinao | 0 | 16.2574 | 119.8915 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-09-15 |  |  |  | #REF! |  | Larc Telecoms, Inc. | 2025-10-08 | 2025-10-09 | FTAPPQ0013011 | 2025-10-13 | FTAPPO0012156 | 2025-10-09 |  |  |  |  | COOP Surveyed | #VALUE! |  | 10/13 ongoing securing tempo CFEI permits | 2025-12-03 | 2025-12-03 | 2025-12-03 | FTAPPQ0014069 | 2025-12-04 | FTAPPO0013167 |  |  |  |  | PO Issued | 2 | 10/13 waiting COOP SOA prior to submit the BOQ | Larc Telecoms Inc. | #REF!
PH010411 | NS-TER24-C425 | HT_MP_BrgyAsanSur_SISON_PANGASINAN | Marilyn | LUELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Sison | Purok 6 | 16.1491 | 120.5228 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-16 | 2025-11-06 | 22/08/2025 | 2025-10-01 | #REF! |  | Larc Telecoms, Inc. | 2025-09-15 | 2025-10-16 | FTAPPQ0013162 | 2025-10-20 | FTAPPO0012293 | 2025-09-16 | 2025-10-17 | 2025-11-05 |  |  | Tempo Energized | 140 | TTC PO issuance | 10/13 FOR TTC PO issuance due to transformer availability | 2025-09-22 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 | 2025-09-23 | 2025-09-29 | 2025-11-15 | 2025-12-09 | Permanent Energized | 11 | 10/ 13 Waiting for transformer availability | #N/A | #REF!
PH010410 | NS-TER24-C427 | HT_MP_BrgyAngatel_URBIZTONDO_PANGASINAN | Marilyn | CENPELCO | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | Urbiztondo | 0 | 15.8154 | 120.3395 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 | 2025-08-06 | 14/08/2025 | 2025-09-05 | #REF! |  | Larc Telecoms, Inc. | 2025-09-15 | 2025-10-22 | FTAPPQ0013286 | 2025-10-28 | FTAPPO0012398 | 2025-09-16 | 2025-10-10 | 2025-10-17 |  |  | Tempo Energized | 159 |  | 10/13 for Permanet power | 2025-09-22 | 2025-09-24 | 2025-10-06 | FTAPPQ0012947 | 2025-10-09 | FTAPPO0012099 | 2025-10-15 |  |  |  | Line Construction Completed | 11 | 10/13 waiting for clearance prior energization 10/8 Waiting for energization schedule pending due to unpaid electricity bill | #N/A | #REF!
PH030823 | NS-TER24-C429 | HT_MP_Mabilog_Concepcion_Tarlac | CJ | TARELCO II | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Concepcion | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH030829 | NS-TER24-C431 | HT_MP_Libueg_Camiling_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Camiling | 0 | 15.7038 | 120.4203 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-11 |  |  |  | #REF! |  | MPS Construction and Trading | 2025-10-08 | 2025-10-09 | FTAPPQ0013013 | 2025-10-13 | FTAPPO0012154 | 2025-11-20 | 2025-11-19 | 2025-11-25 |  |  | Tempo Energized | 120 |  |  | 2025-11-12 | 2025-11-25 | 2025-11-25 | FTAPPQ0013900 | 2025-11-26 | FTAPPO0013007 |  |  |  |  | PO Issued | 2 | 10/20/2025: For TTC application | MPS
PH030815 | NS-TER24-C433 | HT_MP_Cabaruan_SantaIgnacia_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Camiling | 0 | 15.6421 | 120.435 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-25 | 2025-08-07 | 21/09/2025 |  | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-07-02 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-10-17 | 2025-10-21 | 2025-10-21 | FTAPPQ0013258 | 2025-10-27 | FTAPPO0012390 |  |  |  |  | PO Issued | 100 | 10/20/2025: For vendor BOM approval. 10/12/2025: Awaiting coop BOM. | #N/A
PH030812 | NS-TER24-C434 | HT_MP_Tubectubang_Moncada_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Moncada | 0 | 15.7588 | 120.5722 | a.2. On-hold by GT | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | Yes | 2025-04-10 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH030817 | NS-TER24-C436 | HT_MP_Santa LuciaWest_Moncada_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Moncada | 0 | 15.6946 | 120.5507 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-14 | 2025-07-05 | 2025-11-07 | 2025-08-05 | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-04-21 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-11-14 | 2025-12-15 | 2025-12-15 | FTAPPQ0014218 | 2025-12-18 | FTAPPO0013321 |  |  |  |  | PO Issued | 172 | 10/20/2026: Awaiting coop BOM. | #N/A
PH030813 | NS-TER24-C437 | HT_MP_Canan_Paniqui_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Paniqui | 0 | 15.6851 | 120.5937 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-30 |  | 30/07/2025 | 2025-10-01 | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-06-06 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-10-20 | 2025-11-07 | 2025-11-07 | FTAPPQ0013558 | 2025-11-10 | FATPPO0012696 |  |  |  |  | PO Issued | 126 | 10/20/2025: For vendor BOM approval. 10/12/2025: Awaiting coop BOM. | #N/A
PH030816 | NS-TER24-C438 | HT_MP_Acocolao_Paniqui_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Paniqui | 0 | 15.6508 | 120.5555 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-30 | 2025-05-06 | 26/07/2025 | 2025-10-01 | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-06-06 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-11-14 | 2025-12-15 | 2025-12-15 | FTAPPQ0014218 | 2025-12-18 | FTAPPO0013321 |  |  |  |  | PO Issued | 126 | 10/20/2026: Awaiting coop BOM. | #N/A
PH030820 | NS-TER24-C439 | HT_MP_Apsayan_Gerona_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Gerona | 0 | 15.6134 | 120.587 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-07-31 |  |  |  | #REF! |  | JRJA Builders Supply and Services Co. | 2025-09-08 | 2025-09-08 | FTAPPQ0012308 | 2025-09-09 | FTAPPO0011519 | 2025-09-16 | 2025-09-15 | 2025-09-29 |  |  | Tempo Energized |  |  | 9/29/2025: Energized. 9/23/2025: Temporary power applied. JTSS done. For line construction once weather is ok. | [10 empty] | Vendor Allocated |  | 10/20/2026: Awaiting coop BOM. | #N/A
PH030831 | NS-TER24-C440 | HT_MP_Toledo_Ramos_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Ramos | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH030805 | NS-TER24-C441 | HT_MP_Cardona_Gerona_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Gerona | 0 | 15.5778 | 120.5891 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-14 |  | 30/06/2025 | 2025-08-05 | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-09-15 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-09-22 | 2025-09-30 | 2025-09-29 | FTAPPQ0012843 | 2025-10-02 | FTAPPO0011982 | 2025-10-22 | 2025-10-25 | 2025-12-06 | 2025-12-11 | Permanent Energized | 8 | 10/20/2025: For material inspection and NTP. 5/2025: Awaiting NTP from coop | #N/A
PH030810 | NS-TER24-C442 | HT_MP_VillaPaz_Gerona_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Gerona | 0 | 15.5611 | 120.5913 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-14 |  | 30/05/2025 | 2025-08-05 | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-09-15 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-09-22 | 2025-09-26 | 2025-10-06 | FTAPPQ0012904 | 2025-10-06 | FTAPPO0012033 | 2025-10-23 | 2025-10-29 | 2025-12-06 | 2025-12-11 | Permanent Energized | 4 | 10/20/2025: For material inspection and NTP. 5/2025: Awaiting NTP from coop | #N/A
PH030803 | NS-TER24-C444 | HT_MP_SanJacinto_Victoria_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Victoria | 0 | 15.5439 | 120.6711 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 | 2025-08-07 | 2025-03-08 | 2025-09-09 | #REF! |  | C.S ENRIQUEZ (CSEMSCORP Contractors, Fabricators) Inc. | 2025-09-20 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-10-17 | 2025-10-17 | 2025-10-17 | FTAPPQ0013215 | 2025-10-20 | FTAPPO0012325 | 2025-11-26 | 2025-12-12 | 2025-12-12 | 2025-12-22 | Permanent Energized | 8 | 10/20/2025: For material inspection and NTP. 5/2025: Awaiting NTP from coop | #N/A
PH030800 | NS-TER24-C445 | HT_MP_Trinidad(Trinidad Primero)_CityOfTarlac(Capital)_Tarlac | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 15.5069 | 120.6281 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-07-25 | 2025-11-08 |  |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-08 | 2025-09-08 | FTAPPQ0012311 | 2025-09-09 | FTAPPO0011521 | 2025-09-23 | 2025-09-15 | 2025-10-21 |  |  | Tempo Energized |  | Survey Schedule | 10/20/2025: For energization. 10/12/2025: For final inspection of the coop prior to coop BOM. 9/23/2025: Temporary power applied. For coop JTSS schedule once weather is okay. | [10 empty] | Vendor Allocated |  | 10/20/2026: For TTC energization. Awaiting postcon permits | #N/A | POSTCON PERMITS NEEDED
PH030822 | NS-TER24-C446 | HT_MP_Tibag_CityOfTarlac(Capital)_Tarlac | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 15.4817 | 120.5544 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-07-25 | 2025-11-08 | 27/09/2025 |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-08 | 2025-09-08 | FTAPPQ0012311 | 2025-09-09 | FTAPPO0011521 | 2025-09-23 | 2025-09-15 | 2025-10-21 |  |  | Tempo Energized |  | Survey Schedule | 10/20/2025: For energization. 10/12/2025: For final inspection of the coop prior to coop BOM. 9/23/2025: Temporary power applied. For coop JTSS schedule once weather is okay. | [10 empty] | Vendor Allocated |  | 10/20/2026: For TTC energization. Awaiting postcon permits | #N/A | POSTCON PERMITS NEEDED
PH030887 | NS-TER24-C450 | HT_MP_EastDirita_SanAntonio_Zambales | CJ | ZAMECO II | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Zambales | San Antonio | 0 | 0 | 0 | d. Site re-hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | MCEES CONSTRUCTION
PH060483 | NS-TER24-D128 | BrgyBaybay_MAKATO_AKLAN_MACRO2024 | Ralph | #N/A | BTS 8 | T6 | VIS | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060455 | NS-TER24-D131 | T6_NewSite_4_250_200004 | Ralph | AKELCO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Aklan | Batan | Purok Centro | 11.5501 | 122.5495 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-13 |  | 15/06/2025 | 2025-07-11 | #REF! |  | ALT Electrical Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-06-27 | 2025-06-27 |  | 2025-06-30 | [5 empty] | PO Issued | 102 |  | #N/A
PH060482 | NS-TER24-D133 | BrgySan Ramon_MALINAO_AKLAN_MACRO2024 | Ralph | 0 | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Aklan | Malinao | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060486 | NS-TER24-D297 | BrgySan Fernando_MIAGAO_ILOILO_MACRO2024 | Ralph | #N/A | BTS 8 | T6 | VIS | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060485 | NS-TER24-D327 | BrgySan Roque_MALINAO_AKLAN_MACRO2024 | Ralph | #N/A | BTS 8 | T6 | VIS | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-10-21 |  |  |  | #REF! |  | ALT Electrical Engineering Services | 2025-10-27 | 2025-10-27 | FTAPPQ0013329 | 2025-11-03 | FTAPPO0012435 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A
PH060484 | NS-TER24-D363 | BrgyAtabay_TOBIAS FORNIER (DAO)_ANTIQUE_MACRO2024 | Ralph | #N/A | BTS 8 | T6 | VIS | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-10-17 |  |  |  | #REF! |  | ALT Electrical Engineering Services | 2025-10-27 | 2025-10-27 | FTAPPQ0013329 | 2025-11-03 | FTAPPO0012435 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A
PH110550 | NS-TER24-D893 | Brgy.MatinaCrossing03_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110542 | NS-TER24-D894 | Brgy.WilfredoAquino_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110570 | NS-TER24-D895 | 2023_Masterplan_Additional_Nomination_10 | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | Purok 1, Mudiang | 7.1869 | 125.6212 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-08-06 | 2025-10-08 |  |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-17 | [8 empty] | BoQ Approved | 23 |  | #N/A
PH110552 | NS-TER24-D896 | Brgy.Tibungco_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.196 | 125.6386 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-06 |  |  |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-17 | [8 empty] | BoQ Approved | 23 |  | #N/A
PH110626 | NS-TER24-D897 | Brgy.Talandang03_DavaoCity_DavaoDelSur | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | p. LGU Applied | 0 | #REF! | #REF! | #REF! |  | p.2 LGU Applied- Advance build | ADV. RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110544 | NS-TER24-D903 | Brgy.Bucana05_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p.2 LGU Applied- Advance build | ADV. RTB | Yes | 2025-10-02 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110576 | NS-TER24-D904 | Brgy.Bucana06_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110551 | NS-TER24-D905 | Brgy.Talomo(Pob.)09_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 7.0514 | 125.5577 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed | #VALUE! |  | #N/A
PH110549 | NS-TER24-D906 | Brgy.MatinaAplaya03_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | #66 Garnett St., Sto. Niño | 7.0559 | 125.5708 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-06 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110543 | NS-TER24-D911 | Brgy.Barangay14-B(Pob.)_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110575 | NS-TER24-D912 | Brgy.Gov.PacianoBangoy02_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110555 | NS-TER24-D913 | Brgy.VicenteHizonSr.06_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110546 | NS-TER24-D914 | Brgy.Buhangin(Pob.)06_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130175 | NS-TER24-D931 | Brgy.Aurora01_SantaJosefa_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | Santa Josefa | Purok 4 | 8.011 | 126.0178 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-05-20 | 2025-02-06 | 2025-01-08 |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-11 | 2025-09-09 |  | 2025-09-12 | [5 empty] | PO Issued | 28 |  | #N/A
PH130162 | NS-TER24-D943 | Brgy.Poblacion_Magallanes_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | Magallanes | 0 | 9.0202 | 125.5182 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-19 |  | 29/08/2025 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-14 | 2025-08-15 |  | 2025-08-18 | [5 empty] | PO Issued | 53 |  | #N/A
PH090226 | NS-TER24-D959 | Brgy.Sinunoc_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | a.8. PSH done- For re-hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140188 | NS-TER24-D973 | Brgy.Maslabeng_Buluan_Maguindanao | Marlone | MAGELCO | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140190 | NS-TER24-D988 | Brgy.Elian_DatuSaudi-Ampatuan_Maguindanao | Marlone | MAGELCO | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140189 | NS-TER24-D993 | Brgy.Landasan(Sarmiento)01_Parang_Maguindanao | Marlone | MAGELCO | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | Parang | De Jesus Zone | 7.3418 | 124.2479 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-07 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140246 | NS-TER24-D995 | Brgy.Pandag_Pandag_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140256 | NS-TER24-E03 | Brgy.Pageda_Talitay_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | a.8. PSH done- For re-hunting | 0 | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140253 | NS-TER24-E08 | Brgy.Buayan_DatuPiang_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140251 | NS-TER24-E102 | Brgy.Buliok02_Pagalungan_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140209 | NS-TER24-E106 | Brgy.PandanNiog_Pangutaran_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Pangutaran | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140235 | NS-TER24-E107 | Brgy.Tingkangan_Lugus_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Lugus | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140207 | NS-TER24-E108 | Brgy.Silangkan_Parang_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Parang | 0 | 5.9784 | 120.8896 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-04 | 2025-12-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140199 | NS-TER24-E112 | Brgy.Su-uh_OldPanamao_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Old Panamao | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140214 | NS-TER24-E114 | Brgy.Pang02_KalingalanCaluang_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Kalingalan Caluang | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140196 | NS-TER24-E115 | Brgy.Angilan_Omar_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Omar | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140208 | NS-TER24-E116 | Brgy.Bawisan_Parang_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Parang | 0 | 5.929 | 120.88 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-21 | 2025-04-08 | 19/09/2025 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140198 | NS-TER24-E117 | Brgy.Anuling_Patikul_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Patikul | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140215 | NS-TER24-E118 | Brgy.BualoLahi_Maimbung_Sulu | Marlone | SULECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Sulu | Maimbung | 0 | 5.925 | 121.0057 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-07-31 | 2025-04-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140205 | NS-TER24-E127 | Brgy.Ungus-ungus_Sibutu_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | Sibutu | 0 | 4.663 | 119.4746 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-09-05 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140204 | NS-TER24-E137 | Brgy.ManukMangkaw_Simunul_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | Simunul | 0 | 4.8138 | 119.8398 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-25 | 2025-06-08 | 25/09/2025 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140216 | NS-TER24-E141 | Brgy.Talisay_Sibutu_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | Sibutu | 0 | 4.8565 | 119.4532 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-25 |  | 26/09/2025 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140203 | NS-TER24-E142 | Brgy.Pagasinan_Simunul_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | Simunul | 0 | 4.8889 | 119.7956 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-07-25 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140236 | NS-TER24-E145 | Brgy.TapianSukah_Tandubas_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | Tandubas | 0 | 5.1369 | 120.3228 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140233 | NS-TER24-E146 | Brgy.TongTampakan_SouthUbian_Tawi-Tawi | Marlone | TAWELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Tawi-Tawi | South Ubian | 0 | 5.1885 | 120.4932 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | a.2. Long lead time | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140254 | NS-TER24-E193 | Brgy.NuroPoblacion_Upi_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140267 | NS-TER24-E194 | Brgy.Mirab01_Upi_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140248 | NS-TER24-E284 | Brgy.Iganagampong_DatuUnsay_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | 0 | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140252 | NS-TER24-E354 | Brgy.Tulunan_DatuAnggalMidtimbang_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | e. Approved candidates-Awaiting JTSS schedule | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140247 | NS-TER24-E390 | Brgy.Bulod02_Gen.S.K.Pendatun_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | a.8. PSH done- For re-hunting | 0 | #REF! | #REF! | #REF! |  | f. TSSR submitted to DNE & PMO | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090251 | NS-TER24-E407 | Brgy.Manalipa02_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090227 | NS-TER24-E421 | Brgy.Curuan02_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 7.2045 | 122.2265 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-18 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090229 | NS-TER24-E437 | Brgy.Tagasilay_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 7.3025 | 122.2581 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH090252 | NS-TER24-E463 | Brgy.Tumalutab_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140237 | NS-TER24-E476 | Brgy.MahayahayUpper(ZoneII)01_Maluso_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | Maluso | 0 | 0 | 0 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140238 | NS-TER24-E478 | Brgy.Guiong01_Sumisip_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | Sumisip | 0 | 0 | 0 | a.10 For Justi submission to GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140200 | NS-TER24-E480 | Brgy.UpperBato-bato_LamitanCity(Capital)_Basilan | Marlone | 0 | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Lamitan (Capital) | Purok 1 | 6.6497 | 122.1545 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-04 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140231 | NS-TER24-E484 | Brgy.Sumagdang02_IsabelaCity_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 0 | 0 | e. Approved candidates-Awaiting JTSS schedule | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140230 | NS-TER24-E485 | Brgy.SantaBarbara_IsabelaCity_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 6.7353 | 121.95 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140212 | NS-TER24-E486 | Brgy.TablasUsew_Tuburan_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | Tuburan | 0 | 6.6087 | 122.1922 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-19 |  |  | 2025-07-16 | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-07 | 2025-07-07 |  | 2025-07-10 | [5 empty] | PO Issued | 92 |  | #N/A
PH130178 | NS-TER24-E488 | Brgy.Gosoon_Carmen_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | Carmen | P-3 | 9.0823 | 125.2156 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-05 |  | 26/07/2025 |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-30 | 2025-07-29 |  | 2025-08-01 | [5 empty] | PO Issued | 70 |  | #N/A
PH130174 | NS-TER24-E492 | Brgy.Pianing_ButuanCity(Capital)_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | City of Butuan (Capital) | 0 | 8.9908 | 125.6427 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-08 | 2025-07-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140229 | NS-TER24-E529 | Brgy.Kumalarang_IsabelaCity_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 6.6711 | 121.9366 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-07 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140213 | NS-TER24-E530 | Brgy.Cabunbata_IsabelaCity_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 6.6699 | 121.9662 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-22 |  | 2025-08-09 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140239 | NS-TER24-E531 | Brgy.Lumbang_IsabelaCity_Basilan | Marlone | 0 | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 6.6387 | 121.9513 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-18 |  | 2025-05-09 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-08 | 2025-09-06 |  | 2025-09-09 | [5 empty] | PO Issued | 31 |  | #N/A
PH140232 | NS-TER24-E532 | Brgy.Calvario_IsabelaCity_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 6.6494 | 121.9916 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-18 |  | 2025-11-09 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110571 | NS-TER24-E564 | T7_NewSite_7_58_350302 | Marlone | NORDECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Norte | 0 | 0 | 7.3046 | 125.6984 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-08-27 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110557 | NS-TER24-E580 | Brgy.Cogon_IslandGardenCityOfSamal_DavaoDelNorte | Marlone | NORDECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Norte | Island Garden City of Samal | Lot E-14-D | 7.1533 | 125.7149 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-03-08 |  | 31/07/2025 |  | #REF! |  | C-8 Construction Services | [5 empty] | 2025-04-23 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-07-14 | 2025-07-13 |  | 2025-07-16 | [5 empty] | PO Issued | 86 |  | #N/A
PH110629 | NS-TER24-E594 | Brgy.NewKatipunan01_SantoTomas_DavaoDelNorte | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Norte | 0 | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-22 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110630 | NS-TER24-E618 | Brgy.Cabaywa_Asuncion(Saug)_DavaoDelNorte | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Norte | 0 | 0 | 7.5655 | 125.7572 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-09 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110580 | NS-TER24-E786 | Brgy.Batuganding_Sarangani_DavaoOccidental | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | Sarangani | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110600 | NS-TER24-E796 | Brgy.Nuing02_JoseAbadSantos(Trinidad)_DavaoOccidental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110601 | NS-TER24-E800 | Brgy.Patulang_JoseAbadSantos(Trinidad)_DavaoOccidental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110602 | NS-TER24-E801 | Brgy.Kalbay_JoseAbadSantos(Trinidad)_DavaoOccidental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110603 | NS-TER24-E803 | Brgy.Tabayon_JoseAbadSantos(Trinidad)_DavaoOccidental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110604 | NS-TER24-E805 | Brgy.CaburanSmall(Pob.)_JoseAbadSantos(Trinidad)_DavaoOccidental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110566 | NS-TER24-E810 | Brgy.Talagutong(Pob.)_DonMarcelino_DavaoOccidental | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110605 | NS-TER24-E812 | Brgy.Lagumit_Malita(Capital)_DavaoOccidental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 6.2733 | 125.5854 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH110609 | NS-TER24-E880 | Brgy.DonSalvadorLopez,Sr._MatiCity(Capital)_DavaoOriental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Oriental | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140259 | NS-TER24-E91 | Brgy.Dinganen03_Buldon_Maguindanao | Marlone | 0 | BTS 8 | T7 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Maguindanao | 0 | 0 | 0 | 0 | c. Ongoing candidate pre-approval | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110623 | NS-TER24-E927 | Brgy.Batobato(Pob.)_SanIsidro_DavaoOriental | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Oriental | San Isidro | Purok Makogihon 3, Katipunan | 6.8353 | 126.1005 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-15 |  |  |  | #REF! |  | SG Dynamics Construction | [10 empty] | BP Secured | FALSE |  |  | 2025-09-27 | 2025-09-27 | 2025-09-29 |  | 2025-10-02 | [5 empty] | PO Issued | 8 |  | #N/A
PH120366 | NS-TER24-F114 | Brgy.Kiyaab_Antipas_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | 0 | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120363 | NS-TER24-F120 | Brgy.Pangao-an_Magpet_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Magpet | Purok 2 | 7.1132 | 125.1562 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-07-10 |  | 2025-06-09 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120344 | NS-TER24-F125 | Brgy.Bao02_Alamada_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Alamada | L2B11 | 7.3889 | 124.6459 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-14 |  | 2025-10-05 |  | #REF! |  | Angkat Construction and Supplies | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-06-04 | 2025-06-04 |  | 2025-06-07 | [5 empty] | PO Issued | 125 |  | #N/A
PH120379 | NS-TER24-F127 | Brgy.Buayan_M'Lang_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | 0 | 0 | 0 | 0 | t. BP secured | 0 | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-10-04 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120380 | NS-TER24-F143 | Brgy.Marbel_Matalam_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Matalam | 0 | 7.1219 | 124.9249 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-07-25 | 2025-11-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120361 | NS-TER24-F144 | Brgy.Dalapitan02_Matalam_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Matalam | Purok Langka | 7.0416 | 124.8976 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-27 |  | 29/08/2025 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120339 | NS-TER24-F147 | Brgy.Taluntalunan_Makilala_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | Makilala | 0 | 6.9553 | 125.0602 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-05 | 2025-09-07 |  |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-30 | 2025-07-29 |  | 2025-08-01 | [5 empty] | PO Issued | 70 |  | #N/A
PH130156 | NS-TER24-F160 | Brgy.Caloc-an03_Magallanes_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | Magallanes | 0 | 9.0588 | 125.533 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-07 | 2025-08-04 | 16/05/2025 |  | #REF! |  | Angkat Construction and Supplies | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-25 | 2025-05-23 |  | 2025-05-26 | [5 empty] | PO Issued | 137 |  | #N/A
PH130176 | NS-TER24-F161 | Brgy.Basilisa_RemediosT.Romualdez_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | 0 | 9.0658 | 125.5795 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-26 |  | 22/08/2025 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-14 | 2025-07-14 |  | 2025-07-17 | [5 empty] | PO Issued | 85 |  | #N/A
PH130147 | NS-TER24-F164 | Brgy.Comagascas_CabadbaranCity_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | 0 | 9.1342 | 125.5569 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-09 |  | 25/09/2025 |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130142 | NS-TER24-F165 | Brgy.Calibunan_CabadbaranCity_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | 0 | 9.11 | 125.5296 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-07-21 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130136 | NS-TER24-F171 | Brgy.Kinamlutan_ButuanCity_AgusanDelNorte | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | City of Butuan (Capital) | Brgy. Kinamlutan, Butuan City, Agusan Del Norte | 8.9179 | 125.5212 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | r.2. BP applied-Advance Build | ADV. RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130152 | NS-TER24-F192 | Brgy.SanIsidro_SanFrancisco_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | San Francisco | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130160 | NS-TER24-F196 | Brgy.Guadalupe_Esperanza_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | Esperanza | 0 | 8.5821 | 125.7084 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-11 | 2025-07-07 |  |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-03 | 2025-09-01 |  | 2025-09-04 | [5 empty] | PO Issued | 36 |  | #N/A
PH100381 | NS-TER24-F200 | Brgy.SantoNiño_ManoloFortich_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Zone 2 | 8.4326 | 124.8646 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-05-27 | 2025-11-06 | 26/08/2025 |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-20 | 2025-08-23 |  | 2025-08-26 | [5 empty] | PO Issued | 45 |  | #N/A
PH100342 | NS-TER24-F207 | Brgy.Simaya_MalaybalayCity(Capital)_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay (Capital) | Purok 1 | 8.0138 | 125.1574 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-04-10 |  | 26/07/2025 |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-13 | 2025-05-12 |  | 2025-05-15 | [5 empty] | PO Issued | 148 |  | #N/A
PH100314 | NS-TER24-F215 | Brgy.Kinawe_Libona_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Libona | Lot 3 | 8.3377 | 124.7025 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-28 | 2025-08-04 | 23/05/2025 | 2025-06-09 | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-04-30 | 2025-05-03 |  | 2025-05-06 | [5 empty] | PO Issued | 157 |  | #N/A
PH100343 | NS-TER24-F216 | Brgy.Lingion_ManoloFortich_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Zone 2 | 8.4004 | 124.8878 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-07 | 2025-07-08 | 19/09/2025 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-07 | 2025-07-06 |  | 2025-07-09 | [5 empty] | PO Issued | 93 |  | #N/A
PH100316 | NS-TER24-F218 | Brgy.Baclayon_Lantapan_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Lantapan | 0 | 8.0126 | 125.0022 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-27 | 2025-08-04 | 22/05/2025 | 2025-09-26 | #REF! |  | Angkat Construction and Supplies | [5 empty] | 2025-04-30 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-05-25 | 2025-05-23 |  | 2025-05-26 | [5 empty] | PO Issued | 137 |  | #N/A
PH130171 | NS-TER24-F234 | Brgy.SantaCruz(Pob.)_Loreto_DinagatIslands | Marlone | DIELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Dinagat Islands | Loreto | Purok 1, Mabini Street | 10.3586 | 125.5794 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-05-26 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090219 | NS-TER24-F274 | Brgy.Poblacion(Titay)_Titay_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Titay | 0 | 7.8676 | 122.5535 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-31 |  | 27/07/2025 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-10 | 2025-09-08 |  | 2025-09-11 | [5 empty] | PO Issued | 29 |  | #N/A
PH090240 | NS-TER24-F275 | Brgy.Poblacion_Naga_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Naga | 0 | 0 | 0 | a. Ongoing site hunting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH090207 | NS-TER24-F278 | Brgy.Lintangan_Sibuco_ZamboangaDelNorte | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Brgy.Lintangan Sibuco, ZamboangaDelNorte | 7.2159 | 121.9496 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH090208 | NS-TER24-F279 | Brgy.Sicayab01_DipologCity(Capital)_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | City of Dipolog (Capital) | 0 | 0 | 0 | a. Ongoing site hunting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH090217 | NS-TER24-F282 | Brgy.Imelda_Labason_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Labason | Brgy. Imelda, Labason, Zamboanga Del Norte | 8.0603 | 122.5106 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-08-15 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090220 | NS-TER24-F283 | Brgy.Bitoon_Sindangan_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sindangan | 0 | 8.2563 | 122.9857 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-08-22 | 2025-06-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090214 | NS-TER24-F284 | Brgy.Goleo_Sindangan_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sindangan | 0 | 8.2278 | 123.0029 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-16 |  | 2025-01-09 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-15 | 2025-09-14 |  | 2025-09-17 | [5 empty] | PO Issued | 23 |  | #N/A
PH090241 | NS-TER24-F291 | Brgy.Baluran01_Tungawan_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Tungawan | 0 | 7.6236 | 122.4476 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-09-05 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090242 | NS-TER24-F292 | Brgy.Tigbanuang_Tungawan_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Tungawan | Sitio Catulang | 7.5763 | 122.4222 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-07 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090237 | NS-TER24-F299 | Brgy.Caparan_Ipil(Capital)_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil (Capital) | Purok Santan | 7.7432 | 122.542 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-03 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090236 | NS-TER24-F319 | Brgy.Coloran_Siay_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Siay | Purok 5, Sitio Coloy | 7.695 | 122.8904 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-25 | 2025-01-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090245 | NS-TER24-F330 | Brgy.Pling_Buug_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | 0 | 7.7254 | 123.0357 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-10 |  |  |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-28 | 2025-08-30 |  | 2025-09-02 | [5 empty] | PO Issued | 38 |  | #N/A
PH090246 | NS-TER24-F339 | Brgy.Pamintayan_Buug_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | 0 | 7.6866 | 123.0788 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 | 2025-11-07 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090247 | NS-TER24-F342 | Brgy.Songcuya_Diplahan_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Diplahan | 0 | 7.7264 | 122.9685 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-31 | 2025-07-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090248 | NS-TER24-F347 | Brgy.Balangao_Diplahan_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Diplahan | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090250 | NS-TER24-F360 | Brgy.Balungisan_Payao_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Payao | Purok 1 | 7.5867 | 122.8691 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-21 | 2025-07-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100333 | NS-TER24-F379 | Brgy.Tenazas_Lala_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Lala | 0 | 7.9394 | 123.7745 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-09-05 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100334 | NS-TER24-F381 | Brgy.Bulod_Tubod(Capital)_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Tubod (Capital) | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100350 | NS-TER24-F383 | Brgy.Rebucon_Kolambugan_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Kolambugan | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100341 | NS-TER24-F384 | Brgy.Balagatasa_Maigo_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Maigo | 0 | 0 | 0 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100330 | NS-TER24-F385 | Brgy.Binuni_Bacolod_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Bacolod | 0 | 8.1924 | 124.0386 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-10 |  |  |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | 2025-09-27 | [9 empty] | BoQ Submitted | 13 |  | #N/A
PH100292 | NS-TER24-F389 | Brgy.Maria-Cristina_Baloi_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Purok 6 | 8.1722 | 124.2042 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-05-27 | 2025-02-07 |  |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-17 | [8 empty] | BoQ Approved | 23 |  | #N/A
PH100347 | NS-TER24-F396 | Brgy.BansarvilII_SultanNagaDimaporo(Karomatan)_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100340 | NS-TER24-F408 | Brgy.KalangananEast_Pantar_LanaoDelNorte | Marlone | LASURECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Pantar | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100335 | NS-TER24-F409 | Brgy.Tawanan_Pantar_LanaoDelNorte | Marlone | LASURECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Pantar | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100361 | NS-TER24-F410 | Brgy.Inagongan_Tagoloan_LanaoDelNorte | Marlone | LASURECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Tagoloan | Brgy. Inagongan, Tagoloan, Lanao Del Norte | 8.1681 | 124.2702 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100338 | NS-TER24-F411 | Brgy.UpperHinaplanon_IliganCity_LanaoDelNorte | Marlone | ILPI | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Brgy. Bonbonon, Iligan City, Lanao del Norte | 8.2666 | 124.2908 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140210 | NS-TER24-F430 | Brgy.Bagoaingud_Tugaya_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | Tugaya | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140218 | NS-TER24-F431 | Brgy.Borakis_Balindong(Watu)_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | Balindong | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140228 | NS-TER24-F433 | Brgy.Bagoaingud_Saguiaran_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | Saguiaran | 0 | 8.0188 | 124.2525 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-07 |  |  |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-29 | 2025-08-30 |  | 2025-09-02 | [5 empty] | PO Issued | 38 |  | #N/A
PH140194 | NS-TER24-F434 | Brgy.Dulay_MarawiCity(Capital)_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | City of Marawi (Capital) | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140227 | NS-TER24-F444 | Brgy.Bobo_Piagapo_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | Piagapo | 0 | 8.01 | 124.2352 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-14 |  |  |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-02 | 2025-09-01 |  | 2025-09-04 | [5 empty] | PO Issued | 36 |  | #N/A
PH140195 | NS-TER24-F445 | Brgy.Toros_MarawiCity(Capital)_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | City of Marawi (Capital) | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140202 | NS-TER24-F449 | Brgy.Pagayawan_Bubong_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | Bubong | 0 | 0 | 0 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH140217 | NS-TER24-F450 | Brgy.Frankfort_Bumbaran_LanaoDelSur | Marlone | Bumbaran | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | Amai Manabilang | 0 | 7.7863 | 124.6796 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-09-05 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140260 | NS-TER24-F469 | Brgy.Dalipuga_Lumbatan_LanaoDelSur | Marlone | 0 | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140226 | NS-TER24-F472 | Brgy.Cabasaran02_MarawiCity(Capital)_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | City of Marawi (Capital) | 0 | 0 | 0 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100321 | NS-TER24-F486 | Brgy.Pan-ay_Clarin_MisamisOccidental | Marlone | MOELCI II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Occidental | Clarin | 0 | 8.2217 | 123.8565 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130181 | NS-TER24-F490 | Brgy.Himamaug_Tagana-An_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | Tagana-An | Purok 4 | 9.7164 | 125.5709 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-04 |  | 28/08/2025 |  | #REF! |  | SGDynamics Construction OPC | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-28 | 2025-08-30 |  | 2025-09-02 | [5 empty] | PO Issued | 38 |  | #N/A
PH130159 | NS-TER24-F494 | Brgy.Matin-ao_Mainit_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | Mainit | 0 | 9.5486 | 125.4806 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 | 2025-02-07 | 14/08/2025 |  | #REF! |  | SGDynamics Construction OPC | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-14 | 2025-07-13 |  | 2025-07-16 | [5 empty] | PO Issued | 86 |  | #N/A
PH130163 | NS-TER24-F495 | Brgy.Cansayong_Malimono_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | Malimono | Purok 1 | 9.5756 | 125.4156 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-09-05 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130151 | NS-TER24-F501 | Brgy.Poblacion(Alegria)_Alegria_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | Alegria | 0 | 9.4681 | 125.5734 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-25 |  | 18/09/2025 |  | #REF! |  | SGDynamics Construction OPC | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-02 | 2025-09-01 |  | 2025-09-04 | [5 empty] | PO Issued | 36 |  | #N/A
PH130167 | NS-TER24-F506 | Brgy.Magsaysay(Pob.)_Placer_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | Placer | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-22 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130154 | NS-TER24-F507 | Brgy.Magpayang_Mainit_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | Mainit | Purok 5 | 9.5332 | 125.5622 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-13 | 2025-12-07 | 25/08/2025 |  | #REF! |  | SGDynamics Construction OPC | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-14 | 2025-07-13 |  | 2025-07-16 | [5 empty] | PO Issued | 86 |  | #N/A
PH130161 | NS-TER24-F508 | Brgy.Orok_SurigaoCity(Capital)_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | City of Surigao (Capital) | 0 | 9.7662 | 125.5321 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-09-23 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130168 | NS-TER24-F509 | Brgy.SanIsidro_Gigaquit_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | Gigaquit | 0 | 9.5599 | 125.6784 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-21 |  | 2025-09-05 | 2025-09-26 | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-27 | 2025-05-26 |  | 2025-05-29 | [5 empty] | PO Issued | 134 |  | #N/A
PH120355 | NS-TER24-F51 | Brgy.Katubao_Kiamba_Sarangani | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sarangani | 0 | 0 | 0 | 0 | p. LGU Applied | 0 | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130165 | NS-TER24-F513 | Brgy.Tidman_Hinatuan_SurigaoDelSur | Marlone | SURSECO I | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Hinatuan | 0 | 8.2992 | 126.3731 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-07-18 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130173 | NS-TER24-F514 | Brgy.Sumo-sumo_Tago_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Tago | Purok Maliwanag | 8.9774 | 126.2392 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-07 |  | 2025-10-08 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-06-26 | 2025-06-27 |  | 2025-06-30 | [5 empty] | PO Issued | 102 |  | #N/A
PH130164 | NS-TER24-F517 | Brgy.Tambis_Barobo_SurigaoDelSur | Marlone | SURSECO I | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Barobo | Purok 1 | 8.5371 | 126.0521 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-16 |  | 22/06/2025 |  | #REF! |  | Angkat Construction and Supplies | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-06-26 | 2025-06-27 |  | 2025-06-30 | [5 empty] | PO Issued | 102 |  | #N/A
PH130166 | NS-TER24-F520 | Brgy.Hornasan_SanAgustin_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | San Agustin | Purok 3 | 8.7604 | 126.2363 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-08 |  | 26/04/2025 | 2025-09-26 | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-04-23 | 2025-04-22 |  | 2025-04-25 | [5 empty] | PO Issued | 168 |  | #N/A
PH130138 | NS-TER24-F521 | Brgy.Parang_Cantilan_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Cantilan | 0 | 9.2822 | 125.9434 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-14 |  | 25/08/2025 |  | #REF! |  | Angkat Construction and Supplies | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-10 | 2025-09-08 |  | 2025-09-11 | [5 empty] | PO Issued | 29 |  | #N/A
PH130155 | NS-TER24-F522 | Brgy.Rizal_Barobo_SurigaoDelSur | Marlone | SURSECO I | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Barobo | 0 | 8.5359 | 126.1651 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-06-25 | 2025-07-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130149 | NS-TER24-F524 | Brgy.Mabua_TandagCity(Capital)_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | City of Tandag (Capital) | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-09-26 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130169 | NS-TER24-F539 | Brgy.Anibongan_Lianga_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Barobo | 0 | 8.5596 | 126.1175 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-07-25 | 2025-07-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130172 | NS-TER24-F547 | Brgy.Tigao_Cortes_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Cortes | Purok-6 | 9.208 | 126.1743 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-05 |  | 28/08/2025 |  | #REF! |  | C-8 Construction Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-29 | 2025-08-04 |  | 2025-08-07 | [5 empty] | PO Issued | 64 |  | #N/A
PH120375 | NS-TER24-F56 | Brgy.DatuDani_Kiamba_Sarangani | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sarangani | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | p.2 LGU Applied- Advance build | ADV. RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130182 | NS-TER24-F585 | Brgy.PortLamon_Hinatuan_SurigaoDelSur | Marlone | SURSECO I | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Hinatuan | 0 | 8.4667 | 126.3747 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130144 | NS-TER24-F591 | Brgy.Barcelona_Lingig_SurigaoDelSur | Marlone | SURSECO I | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | Lingig | Purok 2 | 8.1589 | 126.4334 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-27 |  | 2025-08-08 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-23 | 2025-07-20 |  | 2025-07-23 | [5 empty] | PO Issued | 79 |  | #N/A
PH120377 | NS-TER24-F599 | Brgy.Pamantingan_Esperanza_SultanKudarat | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120360 | NS-TER24-F602 | Brgy.Tambak_Lambayong(MarianoMarcos)_SultanKudarat | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | 0 | 0 | 6.7276 | 124.6308 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-08-27 | 2025-11-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120359 | NS-TER24-F622 | Brgy.Tamnag(Pob.)_Lutayan_SultanKudarat | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | 0 | 0 | 0 | 0 | p. LGU Applied | 0 | #REF! | #REF! | #REF! |  | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120347 | NS-TER24-F624 | T7_SULTAN KUDARAT_ISULAN (CAPITAL)_3 | Marlone | SUKELCO | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | 0 | 0 | 6.6336 | 124.5957 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-08-27 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH120346 | NS-TER24-F625 | Brgy.Kraan_Palimbang_SultanKudarat | Marlone | SUKELCO | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sultan Kudarat | 0 | 0 | 6.1199 | 124.3544 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-08-27 | 2025-11-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100311 | NS-TER24-F628 | Brgy.Liboran_Baungon_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Baungon | Purok 3 | 8.3526 | 124.6519 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-21 | 2025-03-04 | 19/06/2025 |  | #REF! |  | Diomon Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-04-30 | 2025-05-03 |  | 2025-05-06 | [5 empty] | PO Issued | 157 |  | #N/A
PH100319 | NS-TER24-F635 | Brgy.Maambong_Libona_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Libona | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100306 | NS-TER24-F637 | Brgy.Alae_Libona_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Libona | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100352 | NS-TER24-F640 | Brgy.Kibenton_Impasug-Ong_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Impasug-ong | Purok 4 | 8.1998 | 124.9723 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-14 |  | 22/06/2025 |  | #REF! |  | Angkat Construction and Supplies | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-06-26 | 2025-06-27 |  | 2025-06-30 | [5 empty] | PO Issued | 102 |  | #N/A
PH100371 | NS-TER24-F642 | Brgy.Iba_Cabanglasan_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Cabanglasan | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-24 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100299 | NS-TER24-F644 | Brgy.Mandaing_Cabanglasan_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Cabanglasan | Lot 193-C | 8.0382 | 125.2867 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-27 | 2025-08-04 | 23/06/2025 |  | #REF! |  | Jolo Engineering Services | [5 empty] | 2025-04-22 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-04-27 | 2025-04-26 |  | 2025-04-29 | [5 empty] | PO Issued | 164 |  | #N/A
PH100304 | NS-TER24-F645 | Brgy.Lumbayao_CityOfValencia_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Valencia | 0 | 0 | 0 | e. Approved candidates-Awaiting JTSS schedule | L - Under pre-construction | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100297 | NS-TER24-F646 | Brgy.Kahapunan_CityOfValencia_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Valencia | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120376 | NS-TER24-F65 | Brgy.Kalaong_Maitum_Sarangani | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Sarangani | 0 | 0 | 0 | 0 | c. Ongoing candidate pre-approval | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100310 | NS-TER24-F650 | Brgy.Natulongan_Kibawe_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Kibawe | Purok 2 | 7.5328 | 125.0233 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-03-08 |  | 2025-05-06 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-07 | 2025-05-06 |  | 2025-05-09 | [5 empty] | PO Issued | 154 |  | #N/A
PH120364 | NS-TER24-F86 | Brgy.LibunganTorreta_Pigkawayan_NorthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | 0 | 0 | 0 | 0 | t. BP secured | 0 | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 0 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100373 | NS-TER24-G370 | LGUVIP_BrgyLaoSantaCruz_Plaridel_MisOcc | Marlone | MOELCI I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Occidental | Plaridel | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | [5 empty] | #REF! |  | Ampere Jole Electrical Supply | 2025-10-27 | 2025-10-27 | FTAPPQ0013323 | 2025-11-03 | FTAPPO0012431 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | #VALUE! |  | #N/A
PH100301 | NS-TER24-G371 | LGUVIP_BrgyPuntod_Plaridel_MisOcc | Marlone | MOELCI I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Occidental | Plaridel | 0 | 8.6099 | 123.6855 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-28 |  | 27/06/2025 |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-29 | 2025-07-27 |  | 2025-07-30 | [5 empty] | PO Issued | 72 |  | #N/A
PH060458 | NS-TER24-G372 | LGUVIP_BrgyConsing_EnriqueBMagalona_NegrosOccidental_MACRO_COV2023 | Ralph | NONECO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | Enrique B. Magalona | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | [5 empty] | #REF! |  | Tripower Elecrical Services | 2025-10-27 | 2025-10-27 | FTAPPQ0013328 | 2025-11-03 | FTAPPO0012434 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | #VALUE! |  | #N/A
PH060459 | NS-TER24-G373 | LGUVIP_BrgyIgpalge_Anini-y_Antique_MACRO_COV2023 | Ralph | ANTECO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Antique | Anini-Y | 0 | 10.464 | 121.9848 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-21 | 2025-03-06 | 13/07/2025 | 2025-07-22 | #REF! |  | ALT Electrical Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-06-27 | 2025-06-27 |  | 2025-06-30 | [5 empty] | PO Issued | 102 |  | #N/A
PH070439 | NS-TER24-G374 | LGUVIP_BrgyTultugan_Calape_Bohol_MACRO_COV2023 | Ralph | BOHECO I | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Bohol | Calape | Brgy. Tultogan, Calape, Bohol | 9.8712 | 123.8553 | h. Pending GT TSSR Approval | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-22 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH070440 | NS-TER24-G375 | LGUVIP_BrgyTinibgan_Calape_Bohol_MACRO_COV2023 | Ralph | BOHECO I | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Bohol | Calape | 0 | 9.8767 | 123.9024 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-30 | 2025-07-05 | 17/08/2025 | 2025-09-15 | #REF! |  | Abba Electricware Corp. | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-08 | 2025-07-11 |  | 2025-07-14 | [5 empty] | PO Issued | 88 |  | #N/A
PH100324 | NS-TER24-G438 | T8_RgPM_Shout_8.023934_124.978143 | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Lantapan | Purok 4 | 8.025 | 124.9831 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-20 | 2025-03-04 | 26/05/2025 | 2025-09-26 | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-07 | 2025-05-06 |  | 2025-05-09 | [5 empty] | PO Issued | 154 |  | #N/A
PH100283 | NS-TER24-G452 | T8_RgPM_Shout_8.471424_124.698236 | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100300 | NS-TER24-G455 | T8_RgPM_Shout_7.66546_125.1088 | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Quezon | Purok 4 | 7.6646 | 125.1092 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-12 |  | 2025-09-05 | 2025-10-01 | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-07 | 2025-05-06 |  | 2025-05-09 | [5 empty] | PO Issued | 154 |  | #N/A
PH010357 | NS-TER24-G460 | BonuanGueset | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Larc Telecoms, Inc. | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH100290 | NS-TER24-G462 | T8_RgPM_Shout_8.441293_124.8191 | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Lot 423-4, Zone 5 | 8.4403 | 124.8179 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-15 |  | 2025-10-07 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-05-14 | 2025-05-12 |  | 2025-05-15 | [5 empty] | PO Issued | 148 |  | #N/A
PH030862 | NS-TER24-G464 | New Site Required-3_15.5597_120.9459 | CJ | NEECO II – Area 1 | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Nueva Ecija | Talavera | 0 | 15.4672 | 120.6535 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-07-16 | 2025-06-08 |  |  | #REF! |  | MPS Construction and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0012312 | 2025-09-09 | FTAPPO0011522 | 2025-09-23 | 2025-09-24 | 2025-10-24 |  |  | Tempo Energized |  | BOM from COOP | 10/12/2025: Awaiting coop BOM and design. 10/5/2025: Waiting coop assessment if we can still apply for TTC or direct to PP. | 2025-10-13 | 2025-10-20 | 2025-10-20 | FTAPPQ0013224 | 2025-11-06 | FTAPPO0012352 |  |  |  |  | PO Issued |  | 10/20/2025: For TTC application | #N/A | BoQ Approval pending; submitted complete documents
PH100284 | NS-TER24-G482 | T8_RgPM_Shout_8.468747_124.59055 | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 8.468 | 124.5907 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-08-22 | 2025-09-09 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100345 | NS-TER24-G488 | T8_RgPM_Shout_7.980178_123.793048 | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Lala | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100375 | NS-TER24-G489 | T8_RgPM_Shout_8.385536_124.8093 | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Purok 18, MARB Homes, Menzi | 8.3851 | 124.8079 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-05-27 | 2025-04-06 | 2025-12-07 |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-07 | 2025-07-06 |  | 2025-07-09 | [5 empty] | PO Issued | 93 |  | #N/A
PH100295 | NS-TER24-G491 | T8_RgPM_Shout_8.473043_124.661724 | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100302 | NS-TER24-G503 | T8_RgPM_Shout_8.42412_124.671796 | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 8.4239 | 124.6718 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-08-25 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100285 | NS-TER24-G516 | T8_RgPM_Shout_8.48959_124.598592 | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 8.4911 | 124.5992 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100287 | NS-TER24-G528 | T8_RgPM_Shout_8.514414_124.635297 | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030833 | NS-TER24-G530 | BrgyPitabunan_Concepcion_Tarlac | CJ | TARELCO II | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Concepcion | Purok Visayaz | 15.3392 | 120.6539 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-03-19 |  | 24/05/2025 | 2025-07-16 | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-03-26 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-11-20 | [9 empty] | BoQ Submitted | 198 | 10/20/2025: Awaiting NTP. | #N/A | NTP
PH150159 | NS-TER24-G539 | New Site Required -1_16.84466_121.48563 | Marilyn | IFELCO | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Ifugao | Alfonso Lista | Purok 2 | 16.8452 | 121.5003 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | w. For OP application | RTB | Yes | 2025-08-09 |  |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 |  |  |  |  | COOP Surveyed |  |  | Ongoing seciuring tempo CFEI | [10 empty] | Vendor Allocated | 32 | 10/13 Application applied waiting COOP SOA and staking sheet prior Submission of BOQ | #N/A | #REF!
PH140211 | NS-TER24-G542 | T8_RgPM_Shout_6.71095_121.977218 | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 0 | 0 | n. Ongoing brgy permitting | L - Under pre-construction | #REF! | #REF! | #REF! |  | o. with Brgy clearance | For Zone Application | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030893 | NS-TER24-G618 | ColumbanCollege_BrgyBaretto_OlongapoCity_Zambales | CJ | OEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Zambales | City of Olongapo | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! |  | p. LGU Applied | For BP Application | [5 empty] | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | MCEES CONSTRUCTION
PH030832 | NS-TER24-G644 | BrgySanVicente_SanManuel_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | San Manuel | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | g. JTSS Done- Pending TSSR submission | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150161 | NS-TER24-G645 | FarNorthLuzonGenHosp_BrgyQuirino_Luna_Apayao | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Cordillera Administrative Region (CAR) | Apayao | Luna | 0 | 0 | 0 | d. Site re-hunting | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | BANGAYAN | #REF!
PH140220 | NS-TER24-G654 | BPSVillage_Malabang_LDS | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | Malabang | 0 | 7.5817 | 124.0732 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-08-25 |  |  |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | 2025-09-26 | 2025-10-02 | [8 empty] | BoQ Approved | 8 |  | #N/A
PH090221 | NS-TER24-G655 | 2023Capsite_BrgyJosePBrillantesSr(Old Lituban)_SIOCON_ZDN | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Siocon | 2023Capsite_BrgyJosePBrillantesSr(Old Lituban)_SIOCON_ZDN | 7.7078 | 122.146 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-10-02 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100357 | NS-TER24-G660 | LDNPH_Brgy.Sagadan (Sagadan Lower)_Baroy_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Baroy | 0 | 0 | 0 | a.1. For Re-Site Hunting (Option Disapproved) | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100358 | NS-TER24-G663 | KPH_Brgy.Maranding_Lala_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Lala | 0 | 7.9169 | 123.7733 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-05 |  |  |  | #REF! |  | Jolo Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-28 | 2025-08-30 |  | 2025-09-02 | [5 empty] | PO Issued | 38 |  | #N/A
PH020186 | NS-TER24-G671 | NewGattaranMuncipalHall_BrgyDummun_Gattaran_Cagayan | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Gattaran | 0 | 18.0424 | 121.6419 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-11 |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-10-16 | FTAPPQ0013158 | 2025-10-20 | FTAPPO0012291 | [5 empty] | PO Issued | FALSE |  |  | 2025-10-27 | 2025-11-06 | 2025-11-06 | FTAPPQ0013533 | 2025-11-10 | FTAPPO0012683 |  |  |  |  | PO Issued | 25 |  | #N/A | #REF!
PH100392 | NS-TER24-G674 | VPGH_Brgy.Poblacion_ValenciaCity_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Valencia | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090253 | NS-TER24-G675 | DJRMH_Brgy.Banonong (Pob.)_Dapitan_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | City of Dapitan | 0 | 8.6395 | 123.4177 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH130186 | NS-TER24-G677 | ASTMMC_Brgy.Telaje_Tandag_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | City of Tandag (Capital) | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | r. BP applied | For BP release | [5 empty] | #REF! |  | Diomon Electrical Services | [10 empty] | Not yet endorsed | FALSE |  |  | TBC | 2025-09-11 | 2025-09-12 |  | 2025-09-15 | [5 empty] | PO Issued | 25 |  | #N/A
PH140245 | NS-TER24-G679 | BGH_Brgy.Binuangan_IsabelaCity_Basilan | Marlone | BASELCO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Basilan | City of Isabela | 0 | 0 | 0 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090254 | NS-TER24-G680 | DGTHMC_Brgy.Tenan_Ipil_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil (Capital) | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.2. Long lead time | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130187 | NS-TER24-G681 | SFDH_Brgy.Hubang_SanFrancisco_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | San Francisco | P-4 | 8.5187 | 125.9643 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-15 |  | 27/06/2025 |  | #REF! |  | C-8 Construction Services | [5 empty] | 2025-07-29 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-06-16 | 2025-06-17 |  | 2025-06-20 | [5 empty] | PO Issued | 112 |  | #N/A
PH100383 | NS-TER24-G720 | MHARS_Brgy.Gango_OzamisCity_MisamisOccidental | Marlone | MOELCI II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Occidental | City of Ozamiz | 0 | 0 | 0 | a.9. PSH Done- For GT final disposition | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.2. Long lead time | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100384 | NS-TER24-G722 | LGH_Brgy.Poblacion_ValenciaCity_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Valencia | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100385 | NS-TER24-G723 | CDH_Brgy.Bunawan_Calamba_MisamisOccidental | Marlone | MOELCI I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Occidental | Calamba | 0 | 8.5581 | 123.636 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | Yes | 2025-08-09 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH140240 | NS-TER24-G726 | Brgy.Sagonsongan_MarawiCity_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | City of Marawi (Capital) | 0 | 8.0177 | 124.2689 | a.1. For Re-Site Hunting (Option Disapproved) | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140241 | NS-TER24-G727 | Brgy.Beyaba-Damag_MarawiCity_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | City of Marawi (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH100386 | NS-TER24-G729 | Brgy.Tangueguiron02_Tubod_LanaoDelNorte | Marlone | LANECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Lanao del Norte | Tubod (Capital) | 0 | 8.0637 | 123.8133 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-07-22 |  |  |  | #REF! |  | BC Ubarco Engineering Consultancy | [10 empty] | BP Secured | FALSE |  |  | 2025-09-27 | [9 empty] | BoQ Submitted | 13 |  | #N/A
PH030870 | NS-TER24-G772 | TarlacProvincialHospital_TarlacCity | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010385 | NS-TER24-G775 | BrgySanIsidro_SanJuan(Lapog)_IlocosSur_Shout | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | San Juan | 0 | 17.7154 | 120.4243 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-09-11 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-12-08 | 2025-12-19 | 2025-12-23 |  | No BP in ST | Tempo Energized | 92 |  |  | 2025-12-03 | [9 empty] | BoQ Submitted | 2 |  | BK ENGINEERING | #REF!
PH010386 | NS-TER24-G776 | BrgyCatagtaguen_Banna_IlocosNorte_Shout | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Banna | 0 | 17.9723 | 120.6602 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes | 2025-09-11 |  |  |  | #REF! |  | BK Engineering Services | 2025-10-08 | 2025-10-09 | FTAPPQ0013009 | 2025-10-13 | FTAPPO0012158 | 2025-10-20 | 2025-11-10 | 2025-11-20 |  |  | Tempo Energized | 125 |  |  | 2025-12-03 | [9 empty] | BoQ Submitted | 2 |  | BK ENGINEERING | #REF!
PH010387 | NS-TER24-G779 | BgyNo.1_San Lorenzo (Pob.)_Laoag_IlocosNorte_Shout | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | City of Laoag (Capital) | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH010388 | NS-TER24-G782 | BrgyCalambeg_Piddig_IlocosNorte_Shout | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Piddig | 0 | 18.1862 | 120.7207 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-25 | 2025-01-08 | 19/09/2025 |  | #REF! |  | BK Engineering Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012304 | 2025-09-09 | FTAPPO0011516 | 2025-09-16 | 2025-09-15 | 2025-09-01 |  |  | Tempo Energized |  |  | #N/A | 2025-09-07 | 2025-10-30 | 2025-10-30 | FTAPPQ0013399 | 2025-10-31 | FTAPPO0012507 |  |  |  |  | PO Issued | 33 | 10/7/25: Waiting BoQ Approval & Submission of Signed Staking Sheet | #N/A | #REF!
PH030888 | NS-TER24-G784 | Cohort_BrgyPundaquit_SanAntonio_Zambales | CJ | ZAMECO II | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Zambales | San Antonio | 0 | 14.9357 | 120.0691 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-08 | 2025-04-08 | 25/08/2025 | 2025-09-22 | #REF! |  | MPS Construction and Trading | 2025-07-15 |  | direct to Permanent | [7 empty] | Vendor Allocated | FALSE |  |  | 2025-11-12 | 2025-11-25 | 2025-11-25 | FTAPPQ0013896 | 2025-11-26 | FTAPPO0012994 |  |  |  |  | PO Issued | 87 | 10/20/2025: Awaiting coop JTSS. Awaiting BOM approval | #N/A
PH030895 | NS-TER24-G786 | SeaBreezeAnvaya_Brgy.Mabayo_Morong_Bataan | CJ | PENELCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bataan | Morong | 0 | 0 | 0 | h. Pending GT TSSR Approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH020192 | NS-TER24-G790 | BrgyQuirino(Pob.)_Bagabag_NuevaVizcaya_Shout | Arjay | NUVELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Nueva Vizcaya | Bagabag | 0 | 16.5905 | 121.2486 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-07-25 | 2025-12-09 |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012306 | 2025-09-09 | FTAPPO0011517 | 2025-09-16 | 2025-09-15 | 2025-10-06 |  |  | Tempo Energized |  |  |  | 2025-09-26 | 2025-10-20 | 2025-10-20 | FTAPPQ0013223 | 2025-10-20 | FTAPPO0012350 |  |  |  |  | PO Issued | 14 |  | #N/A | #REF!
PH020193 | NS-TER24-G791 | BrgyPalacian_Aglipay_Quirino_Shout | Marilyn | QUIRELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Quirino | Aglipay | 0 | 16.4533 | 121.629 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-05-19 |  |  |  | #REF! |  | Carlson Electrical Supply and Services | 2025-09-08 | 2025-10-16 | FTAPPQ0013160 | 2025-10-20 | FTAPPO0012290 | 2025-10-03 | 2025-10-27 | 2025-10-30 |  |  | Tempo Energized | 146 |  | For issuance of TTC PO while waiting for Permit | 2025-09-15 | 2025-10-20 | 2025-10-20 | FTAPPQ0013231 | 2025-10-20 | FTAPPO0012354 | 2025-10-30 |  |  |  | Line Construction Started | 25 | 10/13 Application applied waiting COOP SOA and staking sheet prior Submission of BOQ | #N/A | #REF!
PH030903 | NS-TER24-G792 | BrgyLual_Casiguran_Aurora | CJ | AURELCO | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Aurora | Casiguran | 0 | 16.2716 | 122.1247 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-11 | 2025-09-07 |  |  | #REF! |  | Bangayan Electrical Services | 2025-08-27 | 2025-10-13 | FTAPPQ0013085 | 2025-10-15 | FTAPPO0012250 |  |  | 2025-12-15 |  |  | Tempo Energized | 100 | Original BP, EP needed. Requested to SAQ team. | 10/20/2025: Awaiting hardcopy of permits, for submission to AURELCO. 10/12/2025: Applied TTC, for temperament solution | 2025-09-03 | 2025-09-29 | 2025-09-29 | FTAPPQ0012845 | 2025-10-03 | FTAPPO0011986 |  |  |  |  | PO Issued | 7 | 10/20/2025: Postcon permits needed. For transformer testing. 10/6/2025: Waiting for NTP release for Construction | #N/A | CFEI, OP
PH020201 | NS-TER24-G793 | NewSite_BrgyDabubuGrande_SanAgustin_Isabela | Marilyn | QUIRELCO | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | San Agustin | Purok 6 | 16.446 | 121.7797 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-10 |  | 13/08/2025 |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-06-17 | 2025-10-13 | FTAPPQ0013093 | 2025-10-15 | FTAPPO0012248 | 2025-10-06 |  |  |  |  | COOP Surveyed | #VALUE! | For TTC PO issuance | [11 empty] | Vendor Allocated | 115 | 10/13 Survey done waiting for COOP SOA prior BOQ submission | #N/A | #REF!
PH020202 | NS-TER24-G794 | NewSite_BrgyCabaruan_Naguilian_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | Naguilian | 0 | 0 | 0 | f. TSSR submitted to DNE & PMO | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | t. BP secured | RTB | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH020203 | NS-TER24-G795 | NewSite_BrgyFuragui_Solana_Cagayan | Marilyn | CAGELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Solana | 0 | 0 | 0 | f. TSSR submitted to DNE & PMO | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A | #REF!
PH020204 | NS-TER24-G796 | NewSite_Cabeseria27(Abuan)_IlaganCity_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | City of Ilagan (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH020221 | NS-TER24-G797 | BrgyAsinga-Via_Baggao_Cagayan_Shout | Marilyn | CAGELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Baggao | 0 | 0 | 0 | p. LGU Applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-11-18 |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-10-08 | 2025-10-16 | FTAPPQ0013158 | 2025-10-20 | FTAPPO0012291 | 2025-10-17 |  |  |  |  | COOP Surveyed | #VALUE! | [12 empty] | Vendor Allocated | 2 |  | BANGAYAN | #REF!
PH020222 | NS-TER24-G799 | BrgyZone III (Pob.)_SanMariano_Isabela_Shout | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | San Mariano | 0 | 16.987 | 122.0154 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-03 |  | 15/09/2025 |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-01 | 2025-10-13 | FTAPPQ0013093 | 2025-10-15 | FTAPPO0012248 | 2025-10-10 | 2025-11-10 | 2026-12-19 |  |  | Tempo Energized | -269 | For TTC PO issuance | 10/13 - Line con done for transformer testing . 10/4 For application of Tempo CFEI and COOP application tempo permanent facilities | 2025-09-08 | 2025-09-19 | 2025-09-26 | FTAPPQ0012666 | 2025-09-29 | FTAPPO0011865 | 2025-10-10 | 2025-10-13 |  |  | Line Construction Completed | 11 | 10/20 Line COn Done waiting for COOP SOA 10/5 For line con and awaiting released of SOA 10/8 Line con done transformr testing and COOP SOA | #N/A | #REF!
PH020223 | NS-TER24-G800 | BrgySanta Filomena_Abulug_Cagayan_Shout | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Abulug | Purok 4 | 18.4268 | 121.4674 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-05-09 | 2025-12-06 | 27/07/2025 |  | #REF! |  | Bangayan Electrical Services | 2025-09-24 | 2025-11-03 | FTAPPQ0013445 | 2025-11-04 | FTAPPO0012562 | 2025-10-17 | 2025-11-18 | 2025-11-25 |  |  | Tempo Energized | 120 |  | 10/6/25: Waiting for Tempo Permit release | 2025-10-01 | 2025-10-15 | 2025-10-15 | FTAPPQ0013136 | 2025-10-28 | FTAPPO0012305 |  |  |  |  | PO Issued | 9 | 10/6/26: Waiting Signed Staking sheet release/ Waiver for permanent construction | #N/A | #REF!
PH020224 | NS-TER24-G801 | BrgyLangagan_SanchezMira_Cagayan_Shout | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Purok 3 | 18.5497 | 121.2476 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | v. Site Dev Complete Awaiting ABP | RTB | Yes | 2025-06-19 | 2025-12-09 |  |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012901 | 2025-10-06 | FTAPPO0012036 | 2025-09-30 | 2025-09-15 | 2025-10-30 |  |  | Tempo Energized |  |  | 10/6/25: Waiting for TTC energization; Transformer Testing 10/15/25 10/5/25: PQ raised, takeover from Northflash | 2025-10-01 | 2025-10-15 | 2025-10-15 | FTAPPQ0013136 | 2025-10-28 | FTAPPO0012305 |  |  |  |  | PO Issued | 9 | 10/6/26: Waiting Signed Staking sheet release/ Waiver for permanent construction | #N/A | #REF!
PH020225 | NS-TER24-G802 | BrgyVillamarzo_Cordon_Isabela_Shout | Marilyn | ISELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | Cordon | Zone 5 | 16.7276 | 121.4577 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! | Yes | u. RTB | RTB | Yes | 2025-06-30 | 2025-12-08 |  |  | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0012307 | 2025-09-09 | FTAPPO0011518 | 2025-09-23 | 2025-10-10 |  |  |  | Tempo Permit Released |  |  | 10/13 Bill deposit and contract release for payment10/6/25: Tempo CFEI and FSEC secured \, For TTC permanent facilities. Bill deposit SOA for release | 2025-09-23 | [9 empty] | BoQ Submitted | 32 | 10/13 Bill deposit and contract release for payment10/6/25: Tempo CFEI and FSEC secured \, For TTC permanent facilities. Bill deposit SOA for release | #N/A | #REF!
PH020226 | NS-TER24-G803 | BrgyBagu_Pamplona_Cagayan_Shout | Arjay | CAGELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Cagayan | Pamplona | Purok 3 | 18.4258 | 121.3573 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! | Yes | x. OP Applied | RTB | Yes | 2025-06-11 |  |  |  | #REF! |  | Bangayan Electrical Services | 2025-09-08 | 2025-09-08 | FTAPPQ0012901 | 2025-10-06 | FTAPPO0012036 | 2025-09-10 | 2025-09-15 | 2025-10-22 |  |  | Tempo Energized |  |  | 10/6/25: Waiting for TTC energization; Transformer Testing 10/15/25 10/5/25: PQ raised, takeover from Northflash | 2025-10-01 | 2025-10-15 | 2025-10-15 | FTAPPQ0013136 | 2025-10-28 | FTAPPO0012305 |  |  |  |  | PO Issued | 9 | 10/6/26: Waiting Signed Staking sheet release/ Waiver for permanent construction | #N/A | #REF!
PH020227 | NS-TER24-G804 | NewSite_BrgyCabeseria27(Abuan)_IlaganCity_Isabela | Marilyn | ISELCO II | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | City of Ilagan (Capital) | 0 | 17.0861 | 122.0089 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-06-23 |  |  | 2025-12-05 | #REF! |  | Golden Design Konstrukt and Trading | 2025-09-08 | 2025-09-08 | FTAPPQ0013014 | 2025-09-09 | FTAPPO0011518 | 2025-09-23 |  |  |  |  | COOP Surveyed |  |  | 11/17 Line con done waiting for SOA 10/13 - Ongoing line con 10/4 For application of Tempo CFEI and COOP application tempo permanent facilities | 2025-09-11 | 2025-09-25 | 2025-10-09 | FTAPPQ0013014 | 2025-10-13 | FTAPPO0012149 | 2025-10-13 | 2025-11-18 |  |  | Line Construction Completed | 1 | 10/13 ongoing for line con | #N/A | #REF!
PH030909 | NS-TER24-G828 | SFO_BTS_New_2_Panipuan_SanFernandoCity_Pampanga | CJ | SFELAPCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of San Fernando (Capital) | 0 | 15.1207 | 120.6303 | r. BP applied | L - Under pre-construction | #REF! | #REF! | #REF! |  | u. RTB | RTB | Yes |  |  |  |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-10-08 | 2025-10-16 | FTAPPQ0013163 | 2025-10-20 | FTAPPO0012288 | 2025-11-24 |  |  |  |  | COOP Surveyed | #VALUE! | PRECON PERMITS NEEDED | 10/20/2025: No precon yet. | 2026-01-14 | 2026-01-26 | 2026-01-26 | [7 empty] | PQ Raised | 2 | 10/20/2025: Awaiting permits. | MCEES CONSTRUCTION
PH030910 | NS-TER24-G830 | SFO_BTS_New_3_Maimpis_SanFernandoCity_Pampanga | CJ | PELCO III | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of San Fernando (Capital) | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030911 | NS-TER24-G831 | SFO_BTS_New_4_DelRosario_SanFernandoCity_Pampanga | CJ | PELCO III | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of San Fernando (Capital) | 0 | 0 | 0 | c. Ongoing candidate pre-approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030913 | NS-TER24-G834 | SJDM_BTS_New_1_Muzon_SanJoseDelMonteCity_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | 0 | 0 | 0 | d. Site re-hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.4. RE-SH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030914 | NS-TER24-G835 | StaMaria_BTS_New_1_Catmon_SantaMaria_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Santa Maria | 0 | 14.8264 | 121.0182 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-08-06 | 2025-04-09 |  |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-08 | 2025-09-08 | FTAPPQ0012311 | 2025-09-09 | FTAPPO0011521 | 2025-09-16 |  |  |  | Yes | COOP Surveyed |  |  | 9/23/2025:Advanced build. Awaiting precon permits from SAQ. | [10 empty] | Vendor Allocated |  |  | #N/A
PH030915 | NS-TER24-G836 | StaMaria_BTS_New_2_Bulac_SantaMaria_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Santa Maria | 0 | 14.8474 | 121.0291 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | t. BP secured | RTB | Yes | 2025-08-28 |  |  |  | #REF! |  | MCEES CONSTRUCTION AND GENERAL MERCHANDISE | 2025-09-08 | 2025-09-08 | FTAPPQ0012311 | 2025-09-09 | FTAPPO0011521 | 2025-09-16 |  |  |  | Yes | COOP Surveyed |  |  | 9/23/2025:Advanced build. Awaiting precon permits from SAQ. | [10 empty] | Vendor Allocated |  |  | #N/A
PH030916 | NS-TER24-G837 | StaMaria_BTS_New_3_PulongBuhangin_SantaMaria_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Santa Maria | 0 | 14.8831 | 121.0151 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-08-06 | 2025-03-09 |  |  | #REF! |  | JRJA Builders Supply and Services Co. | 2025-09-08 | 2025-09-08 | FTAPPQ0012308 | 2025-09-09 | FTAPPO0011519 | 2025-09-16 |  |  |  | Yes | COOP Surveyed |  |  | 9/23/2025:Advanced build. Awaiting precon permits from SAQ. | 2025-09-05 | 2025-10-28 | 2025-10-29 | FTAPPQ0013379 | 2025-11-03 | FTAPPO0012504 |  |  |  |  | PO Issued |  |  | #N/A
PH030917 | NS-TER24-G840 | Meycauayan_BTS_New_1_Pantoc_Meycauayan_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | City of Meycauayan | 0 | 0 | 0 | o. with Brgy clearance | L - Under pre-construction | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! |  | GPA | 2025-10-08 | [9 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated | 2 |  | GPA
PH030919 | NS-TER24-G843 | Malolos_BTS_SS_New_1_Longos_MalolosCity_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | City of Malolos (Capital) | 0 | 0 | 0 | a.8. PSH done- For re-hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030921 | NS-TER24-G845 | Guiguinto_BTS_New_2_Tiaong_Guiguinto_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Guiguinto | 0 | 14.8468 | 120.8897 | t. BP secured | H - Pending Excavation Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-09-20 | 2025-06-09 |  |  | #REF! |  | GPA | 2025-10-08 | 2025-10-09 | FTAPPQ0013010 | 2025-10-13 | FTAPPO0012157 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated | 2 |  | GPA
PH120370 | NS-TER25-A010 | SEAIT_Brgy.CrossingRubber_Tupi_SouthCotabato | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | Tupi | 0 | 6.3477 | 124.9356 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-07-10 |  |  | 2025-09-30 | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100410 | NS-TER25-A019 | Brgy.Tugaya_ValenciaCity_Bukidnon | Marlone | 0 | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | 0 | 0 | 0 | 0 | t. BP secured | L - Under pre-construction | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-09-24 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH090265 | NS-TER25-A020 | Brgy.Lumayang03_ZamboangaCity_ZamboangaDelSur | Marlone | 0 | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | 0 | 0 | 0 | 0 | p. LGU Applied | 0 | #REF! | #REF! | #REF! |  | p.2 LGU Applied- Advance build | ADV. RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090263 | NS-TER25-A023 | Brgy.Cabaluay02_ZamboangaCity_ZamboangaDelSur | Marlone | 0 | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | 0 | 0 | 0 | 0 | n. Ongoing brgy permitting | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090264 | NS-TER25-A024 | Brgy.Capisan_ZamboangaCity_ZamboangaDelSur | Marlone | 0 | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | 0 | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100402 | NS-TER25-A031 | Brgy.Aposkahoy_Claveria_MisOr | Marlone | 0 | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130203 | NS-TER25-A039 | Brgy.Poblacion_BayuganCity_ADS | Marlone | 0 | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Purok 7 Ballete St. | 8.7204 | 125.7575 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-07-25 | 2025-01-08 |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH100403 | NS-TER25-A047 | Brgy.Kalipay_Gingoog_MisOr | Marlone | 0 | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | 0 | 0 | 0 | 0 | a. Ongoing site hunting | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100404 | NS-TER25-A051 | Brgy.Kalabugao_Impasugong_Bukidnon | Marlone | 0 | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | 0 | 0 | 0 | 0 | o. with Brgy clearance | 0 | #REF! | #REF! | #REF! |  | t. BP secured | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090266 | NS-TER25-A157 | Brgy.Pasobolong02_ZamboangaCity_ZamboangaDelSur | Marlone | 0 | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | g. JTSS Done- Pending TSSR submission | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090267 | NS-TER25-A160 | Brgy. Malagutay03_ZamboangaCity_ZamboangaDelSur | Marlone | 0 | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | a.1. For Re-Site Hunting (Option Disapproved) | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090268 | NS-TER25-A161 | Brgy.Vitali08_ZamboangaCity_ZamboangaDelSur | Marlone | 0 | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | a. Ongoing site hunting | 0 | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH001011 | OWO-2019-049 | C5ORTIGAS_Reloc | CJ | MERALCO | BTS 8 | T3 | NLZ | National Capital Region (NCR) | NCR, Second District (Not a Province) | City of Pasig | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110583 | OWO-2019-067 | NCMALL_Reloc | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | 0 | 0 | 0 | a.7. Problematic sites/Potential return sites | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060466 | OWO-2020-116 | FARMER_Reloc | Ralph | NEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Dos Hermanas, Talisay City, Negros Occidental | 10.7425 | 123.0395 | a. Ongoing site hunting | L - Under pre-construction | #REF! | #REF! | #REF! |  | a.3. for Final dispo | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH001007 | OWO-2021-037 | JAGUIAVE_Reloc | CJ | MERALCO | BTS 8 | T4 | NLZ | National Capital Region (NCR) | NCR, Fourth District (Not a Province) | City of Las Piñas | 0 | 0 | 0 | h. Pending GT TSSR Approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH001009 | OWO-2021-043 | GENLUISQCBYN_Reloc | CJ | MERALCO | BTS 8 | T3 | NLZ | National Capital Region (NCR) | NCR, Second District (Not a Province) | Quezon City | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH001008 | OWO-2021-061 | SMCTUNASMUNTI_Reloc | CJ | MERALCO | BTS 8 | T4 | NLZ | National Capital Region (NCR) | NCR, Fourth District (Not a Province) | City of Muntinlupa | 0 | 0 | 0 | h. Pending GT TSSR Approval | L - Under pre-construction | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060395 | OWO-2021-066 | GAIANT_Reloc | Ralph | ANTECO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Antique | San Jose (Capital) | 0 | 10.7412 | 121.9486 | t. BP secured | A - Energized | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-04 |  | 2025-08-09 |  | #REF! |  | ALT Electrical Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-06-27 | 2025-06-27 |  | 2025-06-30 | [5 empty] | PO Issued | 102 |  | #N/A
PH001010 | OWO-2021-067 | VASRAQC_Reloc | CJ | MERALCO | BTS 8 | T3 | NLZ | National Capital Region (NCR) | NCR, Second District (Not a Province) | Quezon City | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH031090 | OWO-2022-036 | ANGELES_Reloc |  | #N/A | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of Angeles | 0 | 0 | 0 | #N/A | #N/A | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120383 | OWO-2025-088 | KIDAP3_Reloc | Marlone | 0 | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan (Capital) | 0 | 0 | 0 | h. Pending GT TSSR Approval | 0 | #REF! | #REF! | #REF! |  | u. RTB | RTB | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110631 | OWO-2025-090 | PANACA_Reloc | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | 0 | 0 | 0 | b. Candidate Secured | 0 | #REF! | #REF! | #REF! |  | h. Pending GT TSSR Approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110632 | OWO-2025-103 | EDENTO_Reloc | Marlone | 0 | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | City of Davao | 0 | 0 | 0 | e.2. TSSR endorsed to CM, awaiting Site Inspection Checklist | 0 | #REF! | #REF! | #REF! |  | n. Ongoing brgy permitting | Ongoing Brgy. Permitting | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH031114 | OWO-2025-112 | SMCPULOB1BUL_Reloc | CJ | 0 | BTS 8 | T2 | LUZ | Region III (Central Luzon) | Bulacan | Santa Maria | 0 | 0 | 0 | a. Ongoing site hunting | 0 | #REF! | #REF! | #REF! |  | c. Ongoing candidate pre-approval | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010503 | OWO-2025-115 | DAGUPANSW_Reloc | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | a. Ongoing site hunting | 0 | #REF! | #REF! | #REF! |  | a.1. For PSH | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010504 | OWO-2025-116 | LUCAOPGSN_Reloc | Arjay | 0 | BTS 8 | T2 | LUZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | a. Ongoing site hunting | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH001018 | NS-NTG19-Q10 | 2025_T3_TCO_JerichoSt_BrgyBagongSilangan_QuezonCity_MACRO |  | #N/A | BTS 8 | T3 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | g. JTSS Done- Pending TSSR submission | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150211 | NS-TER24-B339 | HT_MP_Lubon_Tadian_MountainProvince | Arjay | #N/A | BTS 8 | T2 | LUZ | Cordillera Administrative Region (CAR) | Mountain Province | Tadian | 0 | 0 | 0 | #N/A | #N/A | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH401103 | OWO-2025-64 | SANTIAGOBARASRZL_Reloc | Marilyn | MERALCO | BTS 8 | T3 | LUZ | Region IV-A (CALABARZON) | Rizal | Baras | 0 | 0 | 0 | #N/A | #N/A | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! |  | GPA | [10 empty] | Vendor Allocated | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A
PH070511 | NS-BIZ20-A44 | BrgyUling_CITY OF NAGA_CEBU | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100354 | NS-BIZ20-F85 | Brgy.Banlag_ValenciaCity_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Valencia | 0 | 7.8377 | 125.1665 | z.1 Returned site | 0 | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH070517 | NS-NTG20-AC22 | BrgyTuyan_NagaCity_Cebu_2 | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070016 | NS-NTG20-AF16 | BrgyPulangbato_CebuCity_Cebu_3 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | Pulang Bato | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060476 | NS-NTG20-N24 | BrgyRobles(Pob)_LaCastellana_NegrosOccidental(2) | Ralph | 0 | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060480 | NS-NTG22-D43 | MTF_BrgyKumaliskis_SalvadorBenedicto_NegrosOccidental_MACRO_COV2022 | Ralph | 0 | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070461 | NS-NTG19-C33 | BrgySawangCalero_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070471 | NS-NTG19-C38 | CebuNormalUniversity(CNU)_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070469 | NS-NTG20-AB20 | StarmallTalisay_BrgyLawaanI_TalisayCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Talisay | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070507 | NS-NTG21-E20 | CansagaBridge_Consolacion_Cebu_HBM | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070435 | NS-NTG21-E51 | BrgyCentro(Pob.)_MandaueCity_Cebu_HBM_3 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070508 | NS-NTG21-F62 | MactanShrine_LapuLapuCity_Cebu_HBM | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | 0 | 0 | 0 | 0 | z.1 Returned site | 0 | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070429 | NS-NTG21-G31 | BrgyKasambagan_CebuCity_Cebu_HBM | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070448 | NS-NTG21-G32 | BrgyMabolo_CebuCity_Cebu_HBM | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.3228 | 123.9182 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH010353 | NS-NTG18-D33 | BrgyPantal_DagupanCity_Pangasinan | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Larc Telecoms, Inc. | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030834 | NS-NTG19-AB86 | BrgyRoosevelt_Dinalupihan_Bataan | CJ | PENELCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bataan | Dinalupihan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030846 | NS-NTG19-O97 | Puregold_McArthurHway_BrgyDau_MabalacatCity_Pampanga | CJ | AEC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | Mabalacat City | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030808 | NS-NTG19-U43 | NCCLEGO_BrgyAranguren_Capas_Tarlac | CJ | TARELCO II | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Capas | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030836 | NS-NTG20-G41 | NearHeritageHomes2_BrgyLomaDeGato_Marilao_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Marilao | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030835 | NS-NTG23-O44 | NearBulaonPav_BrgyBulaon_SanFernandoCity_Pampanga | CJ | PELCO III | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of San Fernando (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060462 | NS-NTG21-G68 | BrgyConcepcionMontes_IloiloCity_Iloilo_HBM | Ralph | MEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Iloilo | City of Iloilo (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010383 | NS-TER24-B371 | HT_MP1_BrgyUso_Suyo_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Suyo | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030873 | NS-TER24-B47 | HT_MP_BrgySantaCruz_HAGONOY_BULACAN | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Hagonoy | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030877 | NS-TER24-B82 | HT_MP_SanEsteban_Macabebe_Pampanga | CJ | PELCO III | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | Macabebe | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010329 | NS-TER24-B84 | 208WT_BrgyNagsabaran_SanJuan_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | San Juan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030841 | NS-TER24-C263 | HT_MP_BrgyMercado_HAGONOY_BULACAN | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | Hagonoy | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030885 | NS-TER24-C362 | HT_MP_Sapangbato_AngelesCity_Pampanga | CJ | CEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of Angeles | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030838 | NS-TER24-C365 | HT_MP_Quebiauan_SanFernando_Pampanga | CJ | PELCO III | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Pampanga | City of San Fernando (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070480 | NS-NTG18-L44 | BrgyBabag_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070431 | NS-NTG18-L46 | BrgyBakilid_MandaueCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070477 | NS-NTG19-A06 | 37SampaguitaSt_Kalunasan_Cebucity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH080346 | NS-NTG19-AA16 | BrgyCanlapwas(Pob.)_CatbaloganCity_WesternSamar | Ralph | SAMELCO II | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Samar | City of Catbalogan (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060423 | NS-NTG19-AB25 | BrgyZone 15_Talisay_NegrosOccidental | Ralph | NEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Brgy. Zone 15_Talisay_Negros Occidental | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070428 | NS-NTG19-AB45 | BrgyCabancalan_MandaueCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110573 | NS-NTG19-AG76 | 2023CapSite_BrgyGovPacianoBangoy_DavaoCity_DDS | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130153 | NS-NTG19-AH00 | Brgy.BagongLungsod(Pob.)_TandagCity(Capital)_SurigaoDelSur | Marlone | SURSECO II | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Sur | City of Tandag (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100081 | NS-NTG19-AH24 | Brgy.Carmen04_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | #N/A | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070443 | NS-NTG19-C13 | BrgyCamputhaw(Pob.)_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070452 | NS-NTG19-C14 | BrgyMabolo_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070441 | NS-NTG19-C17 | BrgyGuadalupe_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070457 | NS-NTG19-C19 | BrgyGuadalupe3_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070466 | NS-NTG19-C21 | BrgyPuntaPrincesa2_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070468 | NS-NTG19-C25 | BrgyQuiotPardo_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070446 | NS-NTG19-C28 | BrgyInayawan_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070447 | NS-NTG19-C32 | BrgyPardo(Pob.)_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070465 | NS-NTG19-E16 | BrgyMambaling2_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070436 | NS-NTG20-AA65 | VIS_BrgyCasili_Consolacion_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | Consolacion | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070007 | NS-NTG20-AF07 | BrgyBuhisan_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070031 | NS-NTG20-AF54 | BrgyGuadalupe_CebuCity_Cebu_7_MACRO | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | Sitio Hoya | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090211 | NS-NTG20-Q17 | Brgy.Miputak(Pob.)02_DipologCity(Capital)_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | City of Dipolog (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060451 | NS-NTG20-Z87 | BrgySambag_IloiloCity_Iloilo | Ralph | MEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Iloilo | City of Iloilo (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070472 | NS-NTG21-D56 | BrgyIbo_LapuLapuCity_Cebu_HBM_1 | Ralph | MECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070426 | NS-NTG21-D59 | BrgyCasuntingan_MandaueCity_Cebu_HBM_1 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070476 | NS-NTG21-D94 | BrgyMaribago_LapuLapuCity_Cebu_HBM_2 | Ralph | MECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060450 | NS-NTG21-E42 | DelgadoSt_VillaAnita_IloiloCity_Iloilo_HBM | Ralph | MEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Iloilo | City of Iloilo (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070430 | NS-NTG21-E70 | BrgyCanduman_MandaueCity_Cebu_HBM_1 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070442 | NS-NTG21-E73 | BrgyMaguikay_MandaueCity_Cebu_HBM | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070434 | NS-NTG21-F59 | BrgyIbabaoEstancia_MandaueCity_Cebu_HBM_1 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070433 | NS-NTG21-F71 | BrgyGuizo_MandaueCity_Cebu_HBM | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH080347 | NS-NTG21-G05 | Brgy42_TaclobanCity_Leyte_HBM | Ralph | LEYECO II | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Leyte | City of Tacloban (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070444 | NS-NTG21-G33 | BrgyLuz_CebuCity_Cebu_HBM | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070473 | NS-NTG21-G41 | BrgyCapitolSite(Pob.)_CebuCity_Cebu_HBM_2 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070459 | NS-NTG21-G42 | PleasantHomes_BrgyPuntaPrincesa_CebuCity_Cebu_HBM | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070464 | NS-NTG21-G44 | BrgyCarreta_CebuCity_Cebu_HBM | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070474 | NS-NTG21-G49 | ColonSt_CebuCity_Cebu_HBM | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070463 | NS-NTG21-G98 | BrgyCapitolSite(Pob.)_CebuCity_Cebu_HBM_3 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120348 | NS-NTG23-D32 | Brgy.Tambler03_GeneralSantosCity_SouthCotabato | Marlone | SOCOTECO II | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH120353 | NS-NTG23-Q22 | BrgyApopong02_GeneralSantosCity_SCOT | Marlone | SOCOTECO II | BTS 8 | T7 | MIN | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030814 | NS-TER24-C448 | HT_MP_Cut-cutII_CityOfTarlac(Capital)_Tarlac | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150169 | NS-TER24-G360 | BrgyBulalacao_Mankayan_Benguet | Marilyn | BENECO | BTS 8 | T2 | NLZ | Cordillera Administrative Region (CAR) | Benguet | Mankayan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH110545 | NS-TER24-D910 | Brgy.Barangay21-C(Pob.)_DavaoCity_DavaoDelSur | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao del Sur | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010356 | NS-TER24-G512 | Pantal 1 | Marilyn | DECORP | BTS 8 | T2 | NLZ | Region I (Ilocos Region) | Pangasinan | City of Dagupan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Larc Telecoms, Inc. | [10 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH110568 | NS-TER24-E806 | Brgy.Mangile_JoseAbadSantos(Trinidad)_DavaoOccidental | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110569 | NS-TER24-E809 | Brgy.Lanao_DonMarcelino_DavaoOccidental | Marlone | DASURECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Occidental | 0 | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090244 | NS-TER24-F307 | Brgy.DatuTumanggong_Tungawan_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Tungawan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100369 | NS-TER24-G477 | T8_RgPM_Shout_9.243646_124.689709 | Marlone | CAMELCO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Camiguin | Mambajao (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! | Yes | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | TSSR Approved | #VALUE! |  | #N/A
PH030879 | NS-NTG21-D29 | SMOLONGAPO_Outdoor_Coloc | CJ | OEDC | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Zambales | City of Olongapo | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100339 | NS-TER24-G537 | T8_RgPM_Shout_8.427537_124.62665 | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090234 | NS-TER24-G580 | Zambo_CBD_LaPurisimaStreet02_Zamboanga City | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090222 | NS-TER24-G584 | Zambo_CBD_ClaretSchool_Zamboanga City | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100393 | NS-TER24-G678 | CDOPGH_Brgy.29 (Pob.)_CagayanDeOro_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130184 | NS-TER24-G732 | Brgy.Lipata_SurigaoCity_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | City of Surigao (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH080315 | OWO-2021-065 | LEPARK_Reloc | Ralph | LEYECO II | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Leyte | City of Tacloban (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030905 | NS-NTG20-D87 | NearGrotto_BrgyGraceville_SJDM_Bulacan | CJ | MERALCO | BTS 8 | T2 | NLZ | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | 0 | 0 | 0 | z. Retracted by GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060467 | NS-NTG23-A06 | CROWN3_Malay_Aklan_TowerConversion | Ralph | AKELCO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Aklan | Malay | 0 | 0 | 0 | z. Retracted by GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070484 | NS-NTG23-A33 | ARPILI_Balamban_Cebu_TowerConversion | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | Balamban | 0 | 0 | 0 | z. Retracted by GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070486 | NS-NTG23-A72 | LEAR_LapuLapuCity_Cebu_TowerConversion | Ralph | MECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | 0 | 0 | 0 | z. Retracted by GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070485 | NS-NTG23-B79 | LARAPANJAGNABOH_TowerConversion | Ralph | BOHECO II | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Bohol | Jagna | 0 | 0 | 0 | z. Retracted by GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070487 | NS-NTG23-C04 | SANPEDDUEROBOH_TowerConversion | Ralph | BOHECO II | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Bohol | Duero | 0 | 0 | 0 | z. Retracted by GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH070387 | OWO-2023-041 | SMCOUT_RELOC | Ralph | NORECO II | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete (Capital) | SMCOUT_RELOC | 0 | 0 | z. Retracted by GT | #N/A | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH110584 | NS-NTG21-K09 | MATI_TowerConversion | Marlone | DORECO | BTS 8 | T7 | MIN | Region XI (Davao Region) | Davao Oriental | City of Mati (Capital) | 0 | 0 | 0 | z. Retracted by GT | L - Under pre-construction | #REF! | #REF! | #REF! |  | z. Retracted by GT | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030804 | NS-BIZ19-C64 | LasHaciendasGolfCourse_BrgyCentral_TarlacCIty_Tarlac | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030818 | NS-BIZ20-E83 | BrgySantaJuliana_Capas_Tarlac | CJ | TARELCO II | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Capas | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH020205 | NS-NTG19-AC18 | BRGYCARABATANCHICA_CAUAYANCITY_ISABELA | Marilyn | ISELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | City of Cauayan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | Vendor Allocated |  |  | #N/A | #REF!
PH010371 | NS-NTG23-O59 | BrgyBaruyen_Bangui_IlocosNorte_Windmills | Arjay | INEC | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Norte | Bangui | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030830 | NS-NTG23-O61 | BrgyMaligaya_TarlacCity_Tarlac_Shout | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030801 | NS-NTG23-O62 | MM_BrgySanRafael_TarlacCity_Tarlac_Shout | CJ | TEI | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | City of Tarlac (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030866 | NS-TER24-B241 | HT_MP_Pao_SanJose_Tarlac | CJ | TARELCO I | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | San Jose | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH010372 | NS-TER24-B311 | HT_MP1_BrgyCayus_Quirino(Angkaki)_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | Quirino | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH030806 | NS-TER24-B46 | Phase2BrgyCristoRey_Capas_Tarlac | CJ | TARELCO II | BTS 8 | T1 | NLZ | Region III (Central Luzon) | Tarlac | Capas | 0 | 0 | 0 | z.1 Returned site | J - Pending SKOM | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH020183 | NS-TER24-C301 | HT_MP_BrgyMarabuligI_CauayanCity_Isabela | Marilyn | ISELCO I | BTS 8 | T1 | NLZ | Region II (Cagayan Valley) | Isabela | City of Cauayan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! |  | Bangayan Electrical Services |  | 2025-12-30 | FTAPPQ0014360 | 2026-01-06 | FTAPPO0013487 | [5 empty] | PO Issued | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH010338 | NS-TER24-G603 | ISPSC_BrgyDarapidap_CandonCity_IlocosSur | Arjay | ISECO | BTS 8 | T1 | NLZ | Region I (Ilocos Region) | Ilocos Sur | City of Candon | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A | #REF!
PH130145 | NS-BIZ23-A38 | Brgy.Consuelo01_Bunawan_AgusanDelSur | Marlone | ASELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Sur | Bunawan | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090235 | NS-NTG19-J61 | Brgy.Guiwan02_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH060448 | NS-NTG19-K33 | BrgyTaculing_BacolodCity_NegrosOccidental(3) | Ralph | NEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | City of Bacolod (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100391 | NS-NTG20-AT67 | 2020Capsite_BrgyCamaman-an_CAGAYANDEORO_MOR | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130185 | NS-NTG21-A30 | BrgyJoseRizalPob.(Bgy. 25)_ButuanCity | Marlone | ANECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Agusan del Norte | City of Butuan (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100274 | NS-NTG21-A33 | Brgy.Puntod03_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090224 | NS-NTG21-C08 | Brgy.SantaBarbara_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100276 | NS-NTG21-L61 | Brgy.Kauswagan01_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH140197 | NS-NTG23-J88 | Brgy.Cadayonan_MarawiCity(Capital)_LanaoDelSur | Marlone | LASURECO | BTS 8 | T8 | MIN | Autonomous Region In Muslim Mindanao (ARMM) | Lanao del Sur | City of Marawi (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100312 | NS-TER24-A126 | Brgy.Poblacion_Claveria_MisamisOriental | Marlone | MORESCO II | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | Claveria | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100368 | NS-TER24-A271 | Brgy.Lumbia02_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100282 | NS-TER24-A476 | Brgy.Tablon04_CagayanDeOroCity(Capital)_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090232 | NS-TER24-D957 | Brgy.Tigtabon02_ZamboangaCity_ZamboangaDelSur | Marlone | ZAMCELCO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100322 | NS-TER24-F208 | Brgy.SanIsidro_ValenciaCity_Bukidnon | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | City of Valencia | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090212 | NS-TER24-F280 | Brgy.Dicayas_DipologCity(Capital)_ZamboangaDelNorte | Marlone | ZANECO | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | City of Dipolog (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090243 | NS-TER24-F296 | Brgy.Gango_RosellerLim_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Roseller Lim | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH090249 | NS-TER24-F356 | Brgy.Gandaan_Olutanga_ZamboangaSibugay | Marlone | ZAMSURECO II | BTS 8 | T8 | MIN | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Olutanga | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130177 | NS-TER24-F499 | Brgy.Quezon_SurigaoCity(Capital)_SurigaoDelNorte | Marlone | SURNECO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | City of Surigao (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100286 | NS-TER24-F631 | Brgy.Miarayon_Talakag_Bukidnon | Marlone | BUSECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Talakag | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100356 | NS-TER24-G404 | CMU_BRGY. DOLOGON_MARAMAG_BUKIDNON | Marlone | FIBECO | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Bukidnon | Maramag | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH130158 | NS-TER24-G647 | TouristRoad_Siargao Blue | Marlone | SIARELCO | BTS 8 | T8 | MIN | Region XIII (Caraga) | Surigao del Norte | General Luna | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH100359 | NS-TER24-G769 | TcoColoc_Brgy.Carmen02_CagayanDeOro_MisamisOriental | Marlone | MORESCO I | BTS 8 | T8 | MIN | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro (Capital) | 0 | 0 | 0 | z.1 Returned site | L - Under pre-construction | #REF! | #REF! | #REF! |  | z.1 Returned site | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH020196 | NS-BIZ18-F74 | BrgyTaggatSur_Claveria_Cagayan |  | #N/A | BTS 8 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150171 | NS-NTG22-D07 | NearGoldRiver_BrgyLoacan_Itogon_Benguet |  | #N/A | BTS 8 | T2 | NLZ | Cordillera Administrative Region (CAR) | Benguet | Itogon | 0 | 0 | 0 | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150174 | NS-TER24-B103 | HT_MP_BrgyPoblacion1_MAYOYAO_IFUGAO |  | #N/A | BTS 8 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150176 | NS-TER24-B127 | HT_MP_BrgyGohang_Banaue_Ifugao |  | #N/A | BTS 8 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150173 | NS-TER24-B78 | HT_MP_BrgySanta Maria_ALFONSO LISTA (POTIA)_IFUGAO |  | #N/A | BTS 8 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030906 | NS-TER24-C264 | HT_MP_BrgySanMiguel_HAGONOY_BULACAN |  | #N/A | BTS 8 | T2 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030907 | NS-TER24-C292 | HT_MP_BrgyAbanganNorte_MARILAO_BULACAN |  | #N/A | BTS 8 | T2 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150175 | NS-TER24-C456 | HT_MP_BrgyPoblacionWest_LAMUT_IFUGAO |  | #N/A | BTS 8 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH150177 | NS-TER24-G789 | BrgySalamague_Lamut_Ifugao_Shout |  | #N/A | BTS 8 | T1 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030908 | NS-TER24-G824 | SFO_BTS_New_1_PulungBulu_SanFernandoCity_Pampanga |  | #N/A | BTS 8 | T2 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030912 | NS-TER24-G832 | SFO_BTS_New_5_Calulut_SanFernandoCity_Pampanga |  | #N/A | BTS 8 | T2 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030918 | NS-TER24-G841 | Meycauayan_BTS_New_2_Saluysoy_Meycauayan_Bulacan |  | #N/A | BTS 8 | T2 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH030920 | NS-TER24-G844 | Guiguinto_BTS_New_1_SantaCruz_Guiguinto_Bulacan |  | #N/A | BTS 8 | T2 | NLZ | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! |  | 0 | 0 | [5 empty] | #REF! | [12 empty] | Not yet endorsed | FALSE | [12 empty] | Not yet endorsed |  |  | #N/A
PH080322 | NS-BIZ18-F55 | BrgyPurokD1(Pob.)_BoronganCity_EasternSamar | Ralph | ESAMELCO | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Eastern Samar | City of Borongan (Capital) | 0 | 11.6094 | 125.4308 | t. BP secured | D - Pending Site Development Completion | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-10 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH060479 | NS-NTG20-AQ27 | BrgyIntungcan_Pontevedra_Capiz | Ralph | 0 | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Capiz | 0 | 0 | 11.4186 | 122.8939 | t. BP secured | E - Pending Tower Erection Completion | #REF! | #REF! | #REF! |  | y. OP secured | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH080349 | OWO-2020-047 | SANPAS_Reloc | Ralph | SAMELCO II | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Samar | Santa Rita | 0 | 11.4175 | 125.003 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-02 | 2025-03-07 | 20/09/2025 |  | #REF! |  | AGB Construction and Supply | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-01 | 2025-08-04 |  | 2025-08-07 | [5 empty] | PO Issued | 64 |  | #N/A
PH080309 | OWO-2022-021 | IMARSAM_Reloc | Ralph | SAMELCO II | BTS 8 | T6 | VIS | Region VIII (Eastern Visayas) | Samar | Marabut | 0 | 11.1052 | 125.2151 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-04-30 | 2025-08-05 | 15/08/2025 | 2025-09-17 | #REF! |  | AGB Construction and Supply | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-07-24 | 2025-07-25 |  | 2025-07-28 |  |  | 2025-09-18 |  |  | Line Construction Completed | 22 |  | #N/A
PH070483 | NS-NTG21-D96 | BrgyCanjulao_LapuLapuCity_Cebu_HBM | Ralph | MECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | 0 | 10.2924 | 123.9474 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-18 |  | 26/08/2025 | 2025-09-09 | #REF! |  | Anneliv Telecom Services | [10 empty] | BP Secured | FALSE |  |  | 2025-09-11 | 2025-09-30 | 2025-09-27 |  | 2025-09-30 | [5 empty] | PO Issued | 10 |  | #N/A
PH070454 | NS-NTG20-AA68 | VIS_BrgySanIsidro_TalisayCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Talisay | 0 | 10.2563 | 123.846 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-21 |  | 2025-06-09 |  | #REF! |  | Jodan Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-01 | 2025-09-01 |  | 2025-09-04 | [5 empty] | PO Issued | 36 |  | #N/A
PH070032 | NS-NTG20-AF55 | BrgyKinasang-anPardo_CebuCity_Cebu | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Cebu (Capital) | 0 | 10.2859 | 123.8573 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-27 | 2025-03-07 |  | 2025-09-17 | #REF! |  | Jodan Electrical Services | [5 empty] | 2025-09-10 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | TBC | 2025-08-14 | 2025-08-15 |  | 2025-08-18 | [5 empty] | PO Issued | 53 |  | #N/A
PH070001 | NS-NTG20-AF01 | BrgyPaknaan_MandaueCity_Cebu_3 | Ralph | VECO | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Cebu | City of Mandaue | 0 | 10.3447 | 123.9517 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-23 |  | 17/08/2025 | 2025-09-17 | #REF! |  | Jodan Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-08-14 | 2025-08-15 |  | 2025-08-18 | [5 empty] | PO Issued | 53 |  | #N/A
PH070481 | NS-NTG21-D90 | BoholProvincialCapitol_TagbilaranCity_Bohol_HBM | Ralph | BLCI | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Bohol | City of Tagbilaran (Capital) | 0 | 9.6612 | 123.8615 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-07-15 |  | 13/09/2025 |  | #REF! |  | Abba Electricware Corp. | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-16 | 2025-09-13 |  | 2025-09-16 | [5 empty] | PO Issued | 24 |  | #N/A
PH060477 | NS-BIZ22-A79 | BrgySag-Ang_LaCastellana_NegrosOccidental_1_MACRO_COV2021 | Ralph | 0 | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | 0 | 0 | 10.3674 | 123.0275 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | x. OP Applied | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH060457 | NS-TER24-D140 | T6_NewSite_1_382_50032 | Ralph | NONECO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | Calatrava | 0 | 10.5814 | 123.4155 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-08-15 |  | 21/09/2025 | 2025-10-03 | #REF! |  | Tripower Electrical Services | [5 empty] | 2025-09-10 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | 2025-10-01 | 2025-10-02 | [8 empty] | BoQ Approved | 8 |  | #N/A
PH070509 | NS-NTG20-AA64 | BrgyLuca_TanjayCity_NegrosOriental | Ralph | 0 | BTS 8 | T6 | VIS | Region VII (Central Visayas) | Negros Oriental | 0 | 0 | 9.5222 | 123.1337 | t. BP secured | G - Pending Foundation Completion | #REF! | #REF! | #REF! |  | w. For OP application | RTB | Yes | 2025-09-11 |  |  |  | #REF! | [12 empty] | BP Secured | FALSE | [12 empty] | BP Secured | #VALUE! |  | #N/A
PH060461 | NS-NTG20-AF20 | BrgyBanago_Bacolod City(2) | Ralph | NEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | City of Bacolod (Capital) | Sibucao | 10.7128 | 122.9493 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-23 |  | 30/07/2025 | 2025-09-17 | #REF! |  | Tripower Electrical Services | [5 empty] | 2025-09-10 |  |  |  |  | COOP Surveyed | #VALUE! |  |  | 2025-09-08 | 2025-09-22 | 2025-09-27 |  | 2025-09-30 | [5 empty] | PO Issued | 10 |  | #N/A
PH060454 | NS-NTG20-L65 | BrgyBinubuhan_BagoCity_NegrosOccidental | Ralph | NEPC | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Negros Occidental | City of Bago | 0 | 10.4577 | 123.0213 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-26 | 2025-02-07 | 2025-06-08 | 2025-08-29 | #REF! |  | Tripower Electrical Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-16 | 2025-09-14 |  | 2025-09-17 | [5 empty] | PO Issued | 23 |  | #N/A
PH060463 | NS-NTG19-AB42 | BrgyCaticlan_Malay_Aklan | Ralph | AKELCO | BTS 8 | T6 | VIS | Region VI (Western Visayas) | Aklan | Malay | 0 | 11.9302 | 121.955 | t. BP secured | C - Pending Post-Con Permit Approval | #REF! | #REF! | #REF! | Yes | y. OP secured | RTB | Yes | 2025-06-14 |  | 2025-08-09 |  | #REF! |  | ALT Electrical Engineering Services | [10 empty] | BP Secured | FALSE |  |  | TBC | 2025-09-05 | 2025-09-06 |  | 2025-09-09 | [5 empty] | PO Issued | 31 |  | #N/A
`
Formulas:
Aging Days = IF([Tempo Energized]>0,(TODAY()-[Tempo Energized]),IF([Tempo Permit Released]>0,(TODAY()-[Tempo Permit Released]),IF([COOP Surveyed]>0,(TODAY()-[COOP Surveyed],IF([Tempo PO Issued]>0,(TODAY()-[Tempo PO Issued]),IF([Tempo]>0,(TODAY()-[Tempo]),IF([Vendor Allocated Date]>0,(TODAY()-[Vendor Allocated Date]),IF([BP secured]>0,(TODAY()-[BP secured])," "))))))))
Aging Days = IF([Tempo Energized]>0,(TODAY()-[Tempo Energized]),IF([Tempo Permit Released]>0,(TODAY()-[Tempo Permit Released]),IF([COOP Surveyed]>0,(TODAY()-[COOP Surveyed],IF([Tempo PO Issued]>0,(TODAY()-[Tempo PO Issued]),IF([Tempo]>0,(TODAY()-[Tempo]),IF([Grid Vendor]>0,(TODAY()-[Grid Vendor]),IF([BP secured]>0,(TODAY()-[BP secured])," "))))))))
Note on N19: Eden Medina:
Note on X56: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on X57: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on AU74: Eden Medina: CSEMSCORP
Note on X79: Eden Medina: per Sir Raphael's email - Nov.12,2025 advance RTB
Note on X82: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on X88: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on AG99: Eden Medina: 1st PQ Oct.10
Note on AH99: Eden Medina: 1st PQ under GPA -FTAPPQ0013067
Note on AI99: Eden Medina: 1st PO - Oct.14
Note on AJ99: Eden Medina: 1st PO under GPA - FTAPPO0012192
Note on X101: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on X102: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on AE102: Eden Medina: from TEC to ALS
Note on AG102: Eden Medina: Oct.22 - under TEC
Note on AH102: Eden Medina: from FTAPPQ0013280(TEC) to FTAPPQ0014035 (ALS)
Note on AI102: Eden Medina: Oct.28 under TEC
Note on AJ102: Eden Medina: from FTAPPO0012397(TEC) to
Note on X128: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on X151: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on AU209: Eden Medina: Oct.16
Note on X248: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on X256: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on X258: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on Y331: Eden Medina: Nov.25 - issue date Nov.26 - uploaded in ST
Note on X340: Eden Medina: per Sir Raphael's email - Nov.12,2025 advance RTB
Note on X347: Eden Medina: per Sir Raphael's email - Nov.12,2025 advance RTB
Note on Y377: Eden Medina: Nov.21 - date issued Nov.26 - uploaded to ST
Note on X378: Eden Medina: per Sir Raphael's email - Nov.12,2025
Note on X431: Eden Medina: email ref. from Abigael (Dec.12)
Note on X450: Eden Medina: per Sir Raphael's email - Nov.12,2025 advance RTB
Note on X474: Eden Medina: email received from Abigael - Oct.23
Note on Y475: Eden Medina: Nov.5 - date issued Nov.19 - date uploaded to ST
Note on Y502: Eden Medina: Apr.10 - issue date Apr.11 - uploaded to ST
Note on AU700: Eden Medina: Sep.30 - 1st approval for BOQ revision& no staking sheet yet
Note on AY736: Eden Medina: to cancel PH030888 from FTAPPO0012994 will create new PO with 50kVa requirement
Note on Y745: Eden Medina: Nov.18 - date issued and uploaded to ST
Note on X752: Eden Medina: per Sir Raphael's email - Nov.12,2025